****

**KAMPALA CAPITAL CITY AUTHORITY**

**Bidding Document**

**Volume 1: Bidding Procedures, Work’s Requirements and Conditions of Contract**

|  |
| --- |
| **Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP**  Lot 1: Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9km) |

**Project: The Greater Kampala Metropolitan Area Urban Development Program (GKMA-UDP)**

**Country:** Uganda

**Project ID: P175660**

**PDE:** Kampala Capital City Authority (KCCA)

**IFB Number:** KCCA-GKMA/WRKS/2025-2026/00008/1

**Issued on:** AUGUST 12, 2025

**PREFACE**

Ministry of Kampala Capital City & Metropolitan Affairs on behalf of **Kampala Capital City Authority (KCCA)** has prepared this Bidding Document for the Procurement of Works **for execution within KCCA under the GKMA-UDP.** Itis based on the Standard Bidding Document for the Procurement of Works under Open or Restricted Bidding issued by the Public Procurement and Disposal of Public Assets Authority dated **SEPTEMBER 2019**.

|  |  |
| --- | --- |
| **LIST OF ACRONYMS** |  |
| BDS | Bid Data Sheet |
| BEB | Best Evaluated Bidder |
| BS | Bid Security |
| BSD | Bid Securing Declaration |
| ESHS | Environmental, Social, Health and Safety |
| GCC | General Conditions of the Contract |
| ITB | Instruction to Bidders. |
| GKMA- UDP | Greater Kampala Metropolitan Area – Urban Development Program |
| JV | Joint Venture |
| NOBEB | Notice of Best Evaluated Bidder |
| PDE | Procuring and Disposing Entity |
| PPDA | Public Procurement and Disposal of Public Assets Authority |
| SBD | Standard Bidding Document |
| SCC | Special Conditions of the Contract |
| SOR | Statement of Requirements. |
| TCS | Technical Compliance Selection |

**Bidding Document**

**Table of Contents**

[**PART 1 - Bidding Procedures 10**](#_bookmark0)

[**Section 1: Instructions to Bidders 12**](#_bookmark1)

[**Section 2: Bid Data Sheet 30**](#_bookmark54)

[**Section 3: Evaluation Methodology and Criteria 34**](#_bookmark55)

[**Section 4: Bidding Forms 45**](#_bookmark56)

[**Section 5: Eligible Countries 84**](#_bookmark57)

[**PART 2 - Statement of Requirements 85**](#_bookmark58)

[**Section 6: Statement of Requirements 85**](#_bookmark59)

[**PART 3 - Contract 94**](#_bookmark69)

[**Section 7: General Conditions of Contract for the Procurement of Works 94**](#_bookmark70)

[**Section 8: Special Conditions of Contract 117**](#_bookmark146)

[**Section 9: Contract Forms 121**](#_bookmark147)

****

**KAMPALA CAPITAL CITY AUTHORITY**

**ABRIDGED BID NOTICE UNDER OPEN BIDDING**

**BID NOTICE**

1. **Kampala Capital C­­ity Authority (KCCA)** hereby invites sealed bids from eligible bidders for:

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Procurement Refer. No** | **Subject Matter of Procurement** | **Bid Security** |
| **Lot 1** | **KCCA-GKMA/**  **WRKS/2025-2026/00008/1** | **Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP**  **Lot 1: Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km)** | **UGX600,000,000** |
| Lot 2 | KCCA-GKMA/  WRKS/2025-2026/00009/2 | Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP  **Lot 2:** Bombo Road (Wandegeya to Bwaise – 2.55Km Dual lanes) | UGX.260,000,000 |
| Lot 3 | KCCA-GKMA/  WRKS/2025-2026/00010/3 | Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP  **Lot 3:** Yusuf Lule Road (1.32Km) and Binaisa Road (1.0Km) – Dual lanes | UGX.330,000,000 |

1. The Bidding document(s) shall be inspected and issued by the **Procurement & Disposal Department**, **Kampala Capital City Authority (KCCA), from 8.00am to 5.00pm** from Monday to Friday except on Public Holidays
2. The deadline for bid submission shall be on/before **10th September 2025, at 11.00am.**
3. Submission will strictly be through Physical submissions to the **Procurement & Disposal Department**, **Kampala Capital City Authority (KCCA) on/before 10th September 2025.**
4. **Below is a summary of the procurement schedule.**

|  |  |
| --- | --- |
| **Activity** | **Date** |
| (a) Publish bid notice | **12th August 2025** |
| (b) Pre-bid meeting | **20th August 2025 @ 11:00 am** |
| (c) Bid closing date | **10th September 2025 @ 11.00am.** |
| (d) Bid opening date | **10th September 2025 @ 11.30am.** |
| (e) Evaluation process | **10th September 2025 to 30th September 2025** |
| (f) Display and communication of best evaluated bidder notice | **3rd October 2025 to 17th October 2025** |
| (g) Contract signature | **28th November 2025** |

The detailed bid notice is available at the entities website: [www.kcca.go.ug](http://www.kcca.go.ug) and at [www.ppda.go.ug](http://www.ppda.go.ug)

**SCHEDULE FOR SITE VISITS PER LOT;**

|  |  |  |  |
| --- | --- | --- | --- |
| **SN** | **LOT NAME** | **DATE & TIME** | **CONTACT PERSON** |
| 1 | LOT 1 | 21st August, 2025 @11:00 am | Eng. Mirembe Nnassuuna (0761007617)  Eng. Nyende Hassan (0761007612) |
| 2 | LOT 2 | 22nd August, 2025 @11:00 am | Eng. Mirembe Nnassuuna (0761007617)  Eng. Nyende Hassan (0761007612) |
| 3 | LOT 3 | 25th August, 2025@ 11:00 am | Eng. Mirembe Nnassuuna (0761007617)  Eng. Nyende Hassan (0761007612) |

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**ACCOUNTING OFFICER**

**Standard Invitation to Bidders**

**BID NOTICE UNDER OPEN BIDDING**

****

**12th August 2025**

**Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP**

**Lot 1: Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km)** – KCCA-GKMA/WRKS/2025-2026/00008/1

1. **The Government of Uganda** through the Ministry of Kampala Capital City and Metropolitan Affairs (MKCC&MA) has received funding from the **World Bank/International Development Association (IDA)** to implement **the Greater Kampala Metropolitan Area-Urban Development Program (GKMA-UDP). Kampala Capital City Authority** as a participating entity has been allocated funds under the program for the Upgrading and Reconstruction of selected roads to bituminous standards.
2. Kampala Capital City Authority invites sealed bids from eligible bidders for the provision of the above works.
3. Bidding shall be conducted in accordance with the procedures contained in **the Public Procurement and Disposal of Public Assets Act, 2003 (the Act) – Order 2021** and the Regulations made under the Act, and is open to all eligible bidders.
4. Interested eligible bidders may obtain further information and inspect the bidding document **at the address given** at 7(d) **from 8:00 am to 5:00 pm** from Monday to Friday except on Public Holidays.
5. Bidding Documents in English may be purchased by interested bidders upon the submission of a written application to the address indicated in 7(d) below and upon payment of a non-refundable fee of **UGX 500,000** (Five Hundred Thousand Shillings) only, **per Lot**. The method of payment will be by obtaining a payment reference number (PRN) after which **a general receipt shall be issued from Kampala Capital City Authority.** The bidding document shall be issued by the Procurement and Disposal Department (PDD) upon presentation of the general receipt at the address given at 7(d).

Bids must be delivered to the address at 7(d) on or **before 10th September 2025, 11:00 am**. All bids must be accompanied by a bid security of Uganda Shillings: **(please refer to the table below)**.

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Procurement Refer. No** | **Subject Matter of Procurement** | **Bid Security** |
| **Lot 1** | **KCCA-GKMA/**  **WRKS/2025-2026/00008/1** | **Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP**  **Lot 1: Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km)** | **UGX600,000,000** |
| Lot 2 | KCCA-GKMA/  WRKS/2025-2026/00009/2 | Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP  **Lot 2:** Bombo Road 2 (Wandegeya to Bwaise 2.55Km Dual lanes) | UGX.260,000,000 |
| Lot 3 | KCCA-GKMA/  WRKS/2025-2026/00010/3 | Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP  **Lot 3:** Yusuf Lule Road (2.64Km) and Binaisa Road (2Km) – Dual lanes | UGX.330,000,000 |

Bid securities must be valid until **4th March 2026**. Late bids shall be rejected. Bids will be opened in the presence of the bidders’ representatives who choose to attend at the address below at 7(d) on **10th September 2025 starting at 11:30 a.m.**

1. There shall be a pre-bid meeting followed by site visits at **Kampala Capital City Authority Offices** starting at 11.00am on **20th August 2025** followed by site inspections to all roadson the dates indicated in the proposed schedule in this notice.
2. Bidders should note the following:
   1. *Documents* may be inspected at: **Procurement & Disposal Department**, **Kampala Capital City Authority, Plot 1-3 Apolo Kaggwa Road, P.O Box 7010, Kampala from 8.00am to 5.00pm from** Monday to Friday except on Public Holidays
   2. Documents will be issued from **Procurement & Disposal Department**, **Kampala Capital City AUthority, Plot 1-3 Apolo Kaggwa Road, P.O Box 7010, Kampala from 8.00am to 5.00pm from** Monday to Friday except on Public Holiday**.**
   3. Bids must be submitted **Physically to the Procurement & Disposal Department**, **Kampala Capital City Authority** on/before **10th September 2025 at 11:00 am**
   4. Address of bid opening: **Procurement and Disposal Department, Kampala Capital City Authority, Plot 1-3 Apolo Kaggwa Road, P.O Box 7010, Kampala on 10th September 2025 at 11:30 am**
   5. The Planned Procurement Schedule (subject to changes) is as follows:

| **Activity** | **Date** |
| --- | --- |
| (a) Publish bid notice | **12th August 2025** |
| (b) Pre-bid meeting | **20th August 2025 @11 am** |
| (c) Bid closing date | **10th September 2025 @ 11.00 am** |
| (d) Bid opening date | **10th September 2025 @ 11.30 am** |
| (e) Evaluation process | **10th September 2025 to 30th September 2025** |
| (f) Display and communication of best evaluated bidder notice | **3rd October 2025 to 17th October 2025** |
| (g) Contract signature | **28th November 2025** |
|  | |

**ACCOUNTING OFFICER**

**PART 1 - Bidding Procedures**

**Table of Clauses**

1. [**General 12**](#_bookmark2)
   1. [Scope of Bid 12](#_bookmark3)
   2. [Source of Funds 12](#_bookmark4)
   3. [Corrupt and Fraudulent Practices 12](#_bookmark5)
   4. [Eligible Bidders 13](#_bookmark6)
   5. [Qualification of the Bidder 15](#_bookmark7)
   6. [Joint Ventures, Consortia and Associations 15](#_bookmark8)
   7. [One Bid per Bidder 15](#_bookmark9)
   8. [Cost of Bidding 15](#_bookmark10)
   9. [Site Visit and Pre-Bid Meeting 15](#_bookmark11)
   10. [Reservation/Preference Schemes 16](#_bookmark12)
2. [**Bidding Document 16**](#_bookmark13)
3. [Content of Bidding Document 16](#_bookmark14)
4. [Clarification of Bidding Document 17](#_bookmark15)
5. [Amendment of Bidding Document 17](#_bookmark16)
6. [**Preparation of Bids 17**](#_bookmark17)
7. [Language of the Bid 17](#_bookmark18)
8. [Documents Comprising the Bid 17](#_bookmark19)
9. [Technical Documentation 18](#_bookmark20)
10. [Bid Prices and Discounts 18](#_bookmark21)
11. [Currencies of Bid and Payment 18](#_bookmark22)
12. [Bid Validity 19](#_bookmark23)
13. [Bid Security or Bid Securing Declaration 19](#_bookmark24)
14. [Alternative Bids 20](#_bookmark25)
15. [Format and Signing of Bid 21](#_bookmark26)
16. [**Submission and Opening of Bids 21**](#_bookmark27)
17. [Sealing and Marking of Bids 21](#_bookmark28)
18. [Deadline for Submission of Bids 22](#_bookmark29)
19. [Late Bids 22](#_bookmark30)
20. [Withdrawal and Replacement of Bids 22](#_bookmark31)
21. [Bid Opening 22](#_bookmark32)
22. [**Evaluation of Bids 23**](#_bookmark33)
23. [Confidentiality 23](#_bookmark34)
24. [Evaluation of Bids 23](#_bookmark35)
25. [Clarification and Changes to Bids 24](#_bookmark36)
26. [Compliance and Responsiveness of Bids 24](#_bookmark37)
27. [Nonconformities, Errors, and Omissions 24](#_bookmark38)
28. [Stages of Evaluation: Using the Technical Compliance Selection Evaluation Method](#_bookmark39) [25](#_bookmark39)
29. [Preliminary Examination of Bids – Eligibility and Administrative Compliance 25](#_bookmark40)
30. [Detailed Evaluation 26](#_bookmark41)
31. [Currency and Exchange Rate 26](#_bookmark42)
32. [Financial Comparison of Bids 26](#_bookmark43)
33. [Margin of Preference 27](#_bookmark44)
34. [Determination of Best Evaluated Bid 27](#_bookmark45)
35. [**Award of Contract 27**](#_bookmark46)
36. [Award Procedure and Notice of Best Evaluated Bidder 27](#_bookmark47)
37. [PDE’s Right to Accept Any Bid And to Reject Any or all Bids 28](#_bookmark48)
38. [Confirmation of Award 28](#_bookmark49)
39. [Signing and Effectiveness of Contract 28](#_bookmark50)
40. [Debriefing of Bidders 28](#_bookmark51)
41. [Performance Security 28](#_bookmark52)
42. [Administrative Review 29](#_bookmark53)

|  |  |  |
| --- | --- | --- |
| **Section 1: Instructions to Bidders** | | |
| **A. General** | | |
| **1. Scope of Bid** | | |
| 1.1 The Procuring and Disposing Entity (PDE), as defined in the Bid Data Sheet (BDS), invites bids for the construction of works, as described in the BDS. The name and procurement reference number of the Contract and number of lots in this Bidding Document are provided in the BDS. The Instructions to Bidders (ITB) should be read in conjunction with the BDS. | | |
| 1.2 The successful bidder will be expected to complete the works by the Intended Completion Date specified in the Special Conditions of Contract (SCC). | | |
| * 1. Throughout this bidding document:      1. the “Contractor” means the provider.      2. “day” means working day unless otherwise expressly stated herein and excludes the Government of Uganda public holidays and weekends.      3. “day works” means varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant.      4. the “Employer” means the procuring and disposing entity.      5. “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender based violence (GBV)), health and safety.      6. “in writing” means hand-written, type-written, printed or electronically made, and resulting in a permanent record. | | |
| **2. Source of Funds** | | |
| 2.1 The PDE has an approved budget towards the cost of the procurement named in the BDS. The PDE intends to use these funds to place a contract for which this Bidding Document is issued. | | |
| 2.2 Payments will be made directly by the PDE and shall be subject to the terms and conditions of the resulting contract placed by the PDE. | | |
| **3. Corrupt and Fraudulent Practices** | | |
| * 1. It is the Government of Uganda’s policy to require that PDEs, as well as bidders and Contractors, to observe the highest standards of ethics during procurement and the execution of contracts. In pursuit of this policy:      1. PPDA defines, for the purposes of this provision, the terms set forth below as follows:         1. “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value, to influence the action of a public official in the procurement process or in contract execution; | | |
| (ii) “fraudulent practice” means as any such practices under the code of ethics of the providers and not limited to misrepresentation of facts in order to influence a procurement or disposal process or the execution of a contract to the detriment of the procuring or disposing entity, and includes collusive practices among bidders prior to or after bid submission designed to establish bid prices at artificial non-competitive levels and to deprive the PDE of the benefits of free and open competition;   1. The PDE will reject a recommendation for award if the Bidder recommended for award has engaged in corrupt or fraudulent practices; and 2. PPDA shall suspend a provider from engaging in any public procurement proceedings for a stated period of time in accordance with the PPDA Act 2003 and the Regulations made under the Act, if the provider has engaged in corrupt or fraudulent practices. |
| 3.2 In pursuit of the policy defined in ITB Sub-Clause 3.1, the PDE may terminate a contract for works, or be ordered by the Public Procurement and Disposal of Public Assets Appeals Tribunal to cancel a contract, if it at any time determines that corrupt or fraudulent practices were engaged in by representatives of the PDE or of a Bidder or Contractor during the procurement or the execution of a contract. |
| 3.3 In further pursuit of the policy defined in ITB Sub-Clause 3.1, the PPDA requires representatives of both the PDE and of Bidders and Contractors to adhere to the relevant codes of ethical conduct. The Code of Ethical Conduct for Bidders and Providers as provided in the bidding forms shall be signed by the bidder and submitted together with the other bidding forms. |
| 3.4 Any communications between a bidder and the PDE related to matters of alleged fraud or corruption must be made in writing and addressed to the Accounting Officer of the PDE and copied to the PPDA. |
| **4. Eligible Bidders** |
| * 1. A Bidder, and all parties constituting the Bidder, shall meet the following criteria to be eligible to participate in public procurement:      1. The bidder has the legal capacity to enter into a contract with the PDE;      2. The bidder is not:         1. Insolvent;         2. In receivership;         3. Bankrupt; or         4. Being wound up      3. The bidder’s business activities have not been suspended;      4. The bidder is not the subject of legal proceedings for any of the circumstances in (b); and      5. The bidder has fulfilled his or her obligations to pay taxes and social security contributions.      6. The bidder is not a member of the Contracts Committee or an employee of the Procuring and Disposing Entity. |
| 4.2 A bidder may be a physical person or artificial person, such as an entity. A combination of persons can bid if they have an agreement to form a Joint Venture (JV), Consortium or Association. Such a bid shall include a Power of Attorney from each party authorizing a representative to conduct all business for and on behalf of the party during the bidding process, contract signature and contract execution. Each party to the JV, Consortium or Association shall be a signatory to the contract with the PDE and shall be jointly and severally liable. |
| 4.3 A bidder, and all parties constituting the bidder including sub-contractors, shall have the nationality of an eligible country, in accordance with Section 5, Eligible Countries. A bidder shall be deemed to have the nationality of a country if the bidder is a citizen or is constituted, incorporated, or registered and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors for any part of the Contract including related services. |
| * 1. A bidder shall not have a conflict of interest. Any bidder found to have a conflict of interest shall be disqualified. A bidder may be considered to have a conflict of interest with one or more parties in this bidding process, if the bidder:      1. Has controlling shareholding with another bidder; or      2. Receives or has received any direct or indirect subsidy from another bidder; or      3. Has the same authorized representative for purposes of this bidding process as another bidder; or |
| (d) Has a relationship with another bidder, directly or through common third parties, that puts the bidder in a position to have access to information about or influence the bid of another bidder, or influence the decisions of the PDE regarding this bidding process; or |
| 1. Submits more than one bid in this bidding process, except for alternative bids permitted under ITB 19. However, this does not limit the participation of subcontractors in more than one bid, or as Bidders and subcontractors simultaneously; or 2. Is associated, or has been associated in the past, directly or indirectly, with the consultant or any other entity that has prepared the design, specifications, and other documents for the Project or is being proposed as Project Manager for the Contract. A bidder that has been engaged by the PDE to provide consulting services for the preparation or supervision of the works, and any of its affiliates, shall not be eligible to bid. |
| 4.5 A bidder that is suspended by the PPDA shall not be eligible to participate in the bidding process. |
| 4.6 Government-owned enterprises shall be eligible only if they can establish that they are legally and financially autonomous and operate under commercial law. |
| 4.7 Bidders shall provide such evidence of their continued eligibility satisfactory to the PDE, as the PDE shall reasonably request. |
| 4.8 To establish eligibility in accordance with ITB 4, a bidder shall complete the eligibility declarations in the Bid Submission Sheet, included in Section 4, Bidding Forms and submit the documents required in Section 3, Evaluation Methodology and Criteria. |
| 4.9 A bidder whose circumstances in relation to eligibility change during a procurement process or during the implementation of a contract, shall immediately inform the PDE. |
| 4.10 All materials, equipment and services to be used in the performance of the contract shall have as their country of origin an eligible country in accordance with Section 5, Eligible Countries. |

|  |  |  |
| --- | --- | --- |
| **5. Qualification of the Bidder** | | |
| * 1. To establish its qualifications to perform the Contract, the bidder shall complete and submit:      1. The Qualification Form provided in Section 4, Bidding Forms; and      2. The information and documents stated in Section 3, Evaluation Methodology and Criteria. | | |
| 5.2 The qualifications of the best evaluated bidder will be assessed as part of a post- qualification in accordance with ITB 40. | | |
| **6. Joint Ventures, Consortia and Associations** | | |
| 6.1 Bids submitted by a JV, Consortium or Association shall include a copy of the Joint Venture, Consortium or Association Agreement signed by all parties to the Joint Venture, Consortium or Association Agreement. | | |
| 6.2 In addition to the requirements under ITB 15.1, bids submitted by a joint venture, consortium or association of two or more firms as partners shall comply with the following requirements, unless otherwise stated in the BDS: | | |
| (a) The bid shall include all the information listed in Section 3, Evaluation Methodology and Criteria for each partner; | | |
| (b) The bid shall be signed so as to be legally binding on all partners; | | |
| (c) All partners shall be jointly and severally liable for the implementation of the Contract in accordance with the Contract terms; | | |
| (d) One of the partners will be nominated as being in charge and receive instructions for and on behalf of any and all partners; and | | |
| (e) The implementation of the entire Contract shall be by the Joint Venture, consortium or association. | | |
| **7. One Bid per Bidder** | | |
| Each bidder shall submit only one bid, either individually or as a partner in a joint venture, consortium or association. A bidder who submits or participates in more than one bid (other than as a subcontractor or in cases of alternatives that have been permitted or requested) shall cause all the bids with the bidder’s participation to be rejected. | | |
| **8. Cost of Bidding** | | |
| The bidder shall bear all costs associated with the preparation and submission of his bid, and the PDE shall not be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. | | |
| **9. Site Visit and Pre-Bid Meeting** | | |
| * 1. The bidder, at the bidder’s own responsibility and risk, is encouraged to visit and examine the site of works and its surroundings and obtain all information that may be necessary for preparing the bid and entering into a contract for construction of the works. The costs of visiting the site shall be at the bidder’s own expense.   2. The bidder and any of its authorized personnel or agents shall be granted permission by the PDE to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the bidder, its personnel, and agents will release and indemnify the PDE and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. | | |
| * 1. If so indicated in the BDS, the PDE will hold a pre-bid meeting or site visit at the time, date and location specified in the BDS to clarify issues and to answer questions on any matter that may be raised at that stage.   2. Bidders may submit any questions in writing to the Entity prior to the date of the meeting and may also orally raise questions at the meeting.   3. Minutes of the pre-bid meeting, if any was held, including the text of the questions asked by bidders, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all bidders who have acquired the Bidding Documents. Any modification to the Bidding Documents that may become necessary as a result of the pre-bid meeting shall be made by the PDE exclusively through the issue of an Addendum pursuant to ITB 12 and not through the minutes of the pre-bid meeting. Unless otherwise indicated in the BDS, non-attendance at the site visit shall not cause disqualification of a Bidder.  1. **Reservation/Preference Schemes**    1. Unless otherwise specified in the BDS, reservation and/or preference schemes shall apply. Where the reservation and /or preference scheme~~s~~ applies, its application and detail shall be specified in Section 3, Evaluation Methodology and Criteria.    2. For the purpose of using the reservation schemes, bids will be classified in one of the categories specified under the Guideline on Reservation Schemes to promote Local Content and for preference schemes the PPDA Act, 2003 shall be applied. |

|  |
| --- |
| **B. Bidding Document** |
| **11. Content of Bidding Document** |
| 11.1 The Bidding Document consists of Parts 1, 2, and 3, which includes all the Sections indicated below, and should be read in conjunction with any addenda issued in accordance with ITB Clause 13. |
| **PART 1 Bidding Procedures**   * Section 1. Instructions to Bidders (ITB) * Section 2. Bid Data Sheet (BDS) * Section 3. Evaluation Methodology and Criteria * Section 4. Bidding Forms * Section 5. Eligible Countries   **PART 2 Statement of Requirements**   * Section 6. Statement of Requirements   **PART 3 Contract**   * Section 7. General Conditions of Contract (GCC) * Section 8. Special Conditions of Contract (SCC) * Section 9. Contract Forms |
| 11.2 Unless obtained directly from the Employer, the Employer is not responsible for the completeness of the Bidding Documents, responses to requests for clarification, the minutes of the pre-bid meeting (if any), or Addenda to the Bidding Documents. |

|  |
| --- |
| 11.3 The bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Document and to furnish with its bid all information and documentation required by the Bidding Documents. |
| **12. Clarification of Bidding Document** |
| A bidder requiring any clarification of the Bidding Document shall contact the PDE in writing at the PDE’s address indicated in the BDS. The PDE will respond in writing to any request for clarification, provided that such request is received no later than the date indicated in the BDS. The PDE shall forward copies of its response to all bidders who have acquired the Bidding Document directly from it, including a description of the inquiry but without identifying its source. Should the PDE deem it necessary to amend the Bidding Document as a result of a clarification, it shall do so following the procedure under ITB 13 and ITB 24.2. |
| **13. Amendment of Bidding Document** |
| * 1. At any time prior to the deadline for submission of bids, the PDE may amend the Bidding Document by issuing an addendum.   2. Any addendum issued shall be part of the Bidding Document and shall be communicated in writing to all who have obtained the Bidding Document directly from the PDE.   3. To give bidders reasonable time in which to take an addendum into account in preparing their bids, the PDE shall extend the deadline for submission of bids by a reasonable period in the event that less than one third of the bidding period remains after the issue date of the addendum. The PDE may, at its discretion, extend the deadline for the submission of bids, where more than one third of the bidding period remains after the date of issue of the addendum. |
| **C. Preparation of Bids** |
| **14. Language of the Bid** |
| * 1. The bid shall be in writing.   2. The bid, as well as all correspondence and documents relating to the bid exchanged between the bidder and the PDE, shall be written in **English.**   3. Supporting documents and printed literature that are part of the bid may be in another language provided they are accompanied by an accurate translation by a competent institution of the relevant passages to English. In which case, for purposes of interpretation of the bid, such translation shall govern. |
| **15. Documents Comprising the Bid** |
| 15.1 The bid submitted by the bidder shall comprise the following: |
| (a) The Bid Submission Sheet, in accordance with ITB 15.2; |
| (b) A Bid Security or a Bid Securing Declaration in accordance with ITB 20; |
| (c) Written confirmation authorising the signatory of the bid to commit the bidder, in accordance with ITB 22; |
| (d) Documentary evidence in accordance with ITB 4.8 establishing the bidder’s eligibility to bid; |
| (e) A priced Activity Schedule or Bill of Quantities in accordance with ITB 16 and 17; |

|  |  |  |
| --- | --- | --- |
| (f) The Qualification Form and Documents in accordance with ITB 5; | | |
| 1. Technical documentation (description of the proposed work method and schedule, including drawings and charts, as necessary) in accordance with ITB 16; 2. The Code of Ethical Conduct for Bidders and Providers in accordance with ITB 3.3; and | | |
| (i) Any other document(s) required in the BDS. | | |
| 15.2 The Bidder shall submit the Bid Submission Sheet using the form provided in Section 4, Bidding Forms. This form must be completed without any alterations to its format, and no substitutes shall be accepted. All blank spaces shall be filled in with the information requested. | | |
| **16. Technical Documentation** | | |
| 16 The bidder shall furnish technical documentation including a statement of work methods, equipment, personnel, schedule and any other information as stipulated in Section 4, Bidding Forms, in sufficient detail to demonstrate the adequacy of the bidder’s proposal to meet the work’s requirements and the completion time. | | |
| **17. Bid Prices and Discounts** | | |
| * 1. The prices and discounts quoted by the bidder in the Bid Submission Sheet and in the Priced Activity Schedules or Bills of Quantities submitted by the bidder shall conform to the requirements specified below.   2. The bidder shall fill in rates and prices for all items of the works described in the Bill of Quantities. If a Price Schedule shows items listed but not priced, their prices shall be assumed to be included in the prices of other items. Items not listed in the Price Schedule shall be assumed not to be included in the bid, and provided that the bid is substantially responsive, the corresponding adjustment shall be applied in accordance with ITB 32.3.   3. The price to be quoted in the Bid Submission Sheet shall be the total price of the bid, excluding any discounts offered. In the event that taxes are not exempt, the price must include any applicable taxes.   4. The bidder shall quote any discounts in the Bid Submission Sheet.   5. The total bid price shall be for the whole works based on the priced Activity Schedule or Bill of Quantities submitted by the bidder.   6. The lump sum price quoted by the bidder shall be subject to adjustment during the performance of the Contract if provided for in the SCC and the provisions of Clause 47 of the GCC. | | |
| **18. Currencies of Bid and Payment** | | |
| 18.1 Bid prices for works and related services originating in and outside Uganda shall be quoted in Uganda Shillings unless authorised by a competent authority. | | |
| 18.2 If authorised by the competent authority the Bidder shall utilise the rate of exchange specified in the BDS to express its offer. The source, date and type of exchange rate shall be indicated in ITB 36. | | |
| 18.3 If authorised by the competent authority, bidders shall indicate details of their expected foreign currency requirements in the Bid. Foreign currency requirements shall be indicated as a percentage of the bid price (excluding provisional sums) and shall be payable at the option of the bidder in up to three foreign currencies, unless otherwise stated in the BDS. | | |
| 18.4 If authorised by the competent authority, bidders may be required by the PDE to clarify their foreign currency requirements and to substantiate that the amounts included in the lump sum and in the SCC are reasonable and responsive to ITB 18.3. |
| **19. Bid Validity** |
| * 1. Bids shall remain valid until the date specified in the BDS. A bid valid for a shorter period shall be rejected by the PDE as non-compliant while a bid valid for a longer period than the date specified in the BDS shall not be rejected but shall only be valid until the date in the BDS.   2. The PDE shall make its best effort to complete the procurement process within the duration of the validity period specified in the BDS. A PDE must ensure the validity of bids, bid securities and bid securing declarations throughout the procurement process until contract signature. |
| 19.3 In exceptional circumstances, prior to the expiration of the bid validity period, the PDE may request Bidders to extend the period of validity of their bids. The request and the responses shall be made in writing. If a Bid Security or a Bid Securing Declaration is requested in accordance with ITB Clause 20, it shall also be extended for a period corresponding to the extension of the bid validity. A bidder may refuse to extend its bid validity period without forfeiting its Bid Security or Bid Securing Declaration. A bidder who extends the validity periods of its bid and bid security or bid securing declaration shall not be required or permitted to modify its bid. |
| **20. Bid Security or Bid Securing Declaration** |
| 20.1 The bidder shall furnish as part of its bid either a Bid Security or a Bid Securing Declaration as specified in the BDS in original form and, in the case of a Bid Security, in the amount and currency specified in the BDS**.** |
| 20.2 If a bid security is specified pursuant to ITB 20,1, the bid security shall be a demand guarantee in the amount specified in the BDS and denominated in Uganda Shillings or a freely convertible currency, and shall: |
| 1. Be issued by a reputable financial institution selected by the bidder from an eligible country. If the institution issuing the security is located outside Uganda, it shall be enforceable through a financial institution located in Uganda. 2. Be in the form of the bid security included in section 4, bidding forms; 3. Be discharged by the financial institution immediately upon written demand by the PDE in case the conditions stated in the bid security are invoked; 4. Be included in the bid and submitted in its original form - copies shall not be accepted. |
| 20.3 The Bid Security or Bid Securing Declaration shall be submitted using the appropriate form included in Section 4, Bidding Forms and shall be valid until the date specified in the BDS. |
| 20.4 Any bid not accompanied by appropriate Bid Security or Bid Securing Declaration, shall be rejected by the PDE as non-compliant. |
| 20.5 The Bid Security or Bid Securing Declaration of all bidders shall be returned as promptly as possible once the successful bidder has signed the contract and provided the required Performance Security and ESHS Performance Security where applicable |
| 20.6 The Bid Security or Bid-Securing Declaration of a JV, Consortium or Association must be issued in the names of all their members or partners. |
| 20.7 The Bid Security may be forfeited or the conditions of the Bid Securing Declaration executed in the following circumstances: |
| 1. If a bidder withdraws its bid during the period of bid validity specified by the Bidder in the Bid Submission Sheet, or during any extension thereto; 2. If a bidder fails to accept the correction of its bid price pursuant to ITB Sub-   Clause 32.5; or   1. If the successful bidder fails to: 2. Sign the Contract in accordance with ITB 45; 3. Furnish a Performance Security and if required in the BDS, the Environmental, Social, Health and Safety (ESHS) Performance Security in accordance with ITB 46.2. |
| **21. Alternative Bids** |
| 21.1 Bidders shall submit offers that comply with the requirements of the bidding documents, including the basic technical design as indicated in the drawings and specifications. Alternative bids shall not be considered unless they are permitted in the BDS. |
| * 1. Where permitted, alternative bids do not need to conform precisely to the Statement of Requirements (SORs), but must-      1. Meet the objectives and/or performance requirements prescribed in the SORS;      2. Be substantially within any delivery or completion schedule, budget or other performance parameters stated in the solicitation document;      3. Provide all information necessary for a complete evaluation of the alternative by the PDE, including design calculations, technical specifications, breakdown of prices, proposed construction methods and other relevant details; and      4. Clearly state the benefits of the alternative bid over any solution which conforms   precisely to the SORs, in terms of technical performance, price, operating costs or any other benefit. |
| * 1. A bidder may submit both a main bid which conforms precisely to the SORs and an alternative bid.   2. Where a bidder submits more than one bid, each bid shall be submitted as a completely separate bid and shall conform to the instructions for preparation and submission of bids in its own right, without any reliance on any other bid. In particular, each bid shall be separately signed, authorised, sealed, labelled and submitted in accordance with the instructions for submission of bids and shall be accompanied by a separate BS or BSD, if so required. Such bids shall be labelled “Main Bid” and “Alternative Bid”.   3. The evaluation of alternative bids shall use the same methodology, criteria and weights as the evaluation of main bids, except that the detailed technical evaluation shall take into account only the objectives and/or performance requirements prescribed in SORs. |

|  |
| --- |
| **22. Format and Signing of Bid** |
| 22.1 The bidder shall prepare one original of the documents comprising the bid as described in ITB Clause 14 and clearly mark it “ORIGINAL.” In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS, and clearly mark each of them “COPY.” In the event of any discrepancy between the original and the copies, the original shall prevail. |
| 22.2 The original and all copies of the bid shall be signed by the bidder in the event that he or she is a physical person personally submitting the bid and in any other event by a person duly authorised to sign on behalf of the bidder. This authorisation shall consist of a Power of Attorney which if signed in Uganda shall be registered with the competent authority and if signed outside Uganda, shall be notarized. The Power of Attorney shall be submitted in the bid. The name and position held by each person signing the authorisation must be typed or printed below the signature. All pages of the bid, except for un-amended printed literature, shall be signed or initialled by the person authorized to sign the bid. |
| * 1. The bid shall contain no alterations or additions, except those to comply with instructions issued by the PDE, or as necessary to correct errors made by the Bidder, in which case such corrections shall be initialed by the person or persons signing the Bid.   2. In the case of bids submitted by a JV, Consortium or Association, each member or partner shall nominate a representative through a power of attorney to conduct all business on its behalf during the bid preparation, bidding process and contract execution in case of award of the contract. Each representative duly nominated through the power of attorney shall commit each respective member or partner by executing a JV, Consortium or Association agreement providing; that the parties shall jointly submit a bid, naming the lead member or partner and authorizing the representative of the lead member or partner who was granted power of attorney to sign the bid.   3. Any inter-lineation, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the Bid. |
| **D. Submission and Opening of Bids** |
| **23. Sealing and Marking of Bids** |
| 23.1 The bidder shall enclose the original and each copy of the bid, in separate sealed envelopes or packages, duly marking the envelopes as “ORIGINAL” and “COPY.” These envelopes or packages containing the original and the copies shall then be enclosed in one single plain envelope or package securely sealed in such a manner that opening and resealing cannot be achieved undetected and shall be submitted as specified in the BDS. |
| * 1. The inner and outer envelopes shall:      1. Bear the name and address of the Bidder;      2. Be addressed to the PDE in accordance with ITB 23.1; |
| 1. Bear the Procurement Reference number of this bidding process; and 2. Bear a warning not to open before the time and date for bid opening, in accordance with ITB 23.1. |
| 23.3 If all envelopes are not sealed and marked as required, the PDE will assume no responsibility for the misplacement or premature opening of the bid. |

|  |
| --- |
| **24. Deadline for Submission of Bids** |
| 24.1 Bids must be received by the PDE at the address and no later than the date and time indicated in the BDS. When so specified in the BDS, bidders shall have the option of submitting their Bids electronically. Bidders submitting bids electronically shall follow the electronic bid submission procedures specified in the BDS. |
| 24.2 The PDE may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Documents in accordance with ITB 13, in which case all rights and obligations of the PDE and bidders previously subject to the deadline shall thereafter be subject to the as extended. |
| **25. Late Bids** |
| The PDE shall not consider any bid that arrives after the deadline for submission of bids, in accordance with ITB 24. Any bid received by the PDE after the deadline for submission of bids shall be declared late, rejected, and returned unopened to the bidder. |
| **26. Withdrawal and Replacement of Bids** |
| * 1. A bidder may withdraw or replace its bid after it has been submitted at any time before the deadline for submission of bids by sending a written notice, duly signed by an authorised representative, which shall include a copy of the authorisation in accordance with ITB 24.2. Any corresponding replacement of the bid must accompany the respective written notice. All notices must be:      1. Submitted in accordance with ITB 23 and 24 (except that withdrawals notices do not require copies), and in addition, the respective envelopes shall be clearly marked “Withdrawal,” or “REPLACEMENT,” and      2. Received by the Procuring and Disposing Entity prior to the deadline prescribed for submission of bids, in accordance with ITB Clause 24. |
| 26.2 Bids requested to be withdrawn in accordance with ITB Sub-Clause 24.1 shall be returned unopened to the Bidder. |
| * 1. No bid may be withdrawn or replaced in the interval between the deadline for submission of bids and the expiration of the period of bid validity specified by the Bidder in the Bid Submission Sheet or any extension thereof.   2. Bids may only be modified by withdrawal of the original bid and submission of a replacement bid in accordance with ITB Sub-Clause 26.1. Modifications submitted in any other way shall not be taken into account in the evaluation of bids. |
| 26.5 Bidders may only offer discounts to, or otherwise modify the prices of their bids, by withdrawing and replacing their bid in accordance with this clause, or by including the discount in the original bid submission in accordance with ITB 17. |
| **27. Bid Opening** |
| 27.1 The PDE shall conduct the bid opening in the presence of bidders` designated representatives who choose to attend, and at the address, date and time specified in the BDS. Any specific electronic bid opening procedures required if electronic Bidding is permitted in accordance with ITB 24.1 shall be as specified in the BDS. |
| 27.2 First, envelopes marked “WITHDRAWAL” shall be opened and read out and the envelope with the corresponding bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a |

|  |
| --- |
| valid authorisation to request the withdrawal and is read out at the bid opening.   * 1. All other envelopes including those marked “REPLACEMENT” shall be opened and the relevant details read out. Replacement bids shall be recorded as such on the record of the bid opening.   2. Only envelopes or packages that are opened and read out at the bid opening shall be evaluated. |
| 27.5 All other envelopes shall be opened one at a time, reading out: the name of the bidder; the bid price, per lot where applicable, including any discounts; the presence of a Bid Security or Bid Securing Declaration; and any other details as the Procuring and Disposing Entity may consider appropriate. No bid shall be rejected at the bid opening except for late bids, in accordance with ITB 25 |
| * 1. The PDE shall prepare a record of the bid opening that shall include, as a minimum: the name of the bidder and whether there is a withdrawal and/or replacement; the total bid price or the bid price per lot if applicable, including any discounts; the presence or absence of a Bid Security or Bid Securing Declaration, and whether a Power of Attorney was submitted. The bidders’ representatives who are present shall be requested to sign the record. The omission of a bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall upon request be distributed to bidders and displayed on the PDE’s Notice Board within one working day from the date of the bid opening for a minimum of seven (7) working days.   2. The original bids shall be kept in the custody of the Accounting Officer and where there is a discrepancy at evaluation of the bids, reference shall be made to the originals in the custody of the Accounting Officer. |
| **E. Evaluation of Bids** |
| **28. Confidentiality** |
| 28.1 Information relating to the examination, evaluation, comparison, and post-qualification of bids, and recommendation of contract award, shall not be disclosed to bidders or any other persons not officially concerned with such process until information detailing the Best Evaluated Bidder (BEB) is communicated to all Bidders. |
| 28.2 Any attempt by a Bidder to influence the PDE in the examination, evaluation, comparison, and post-qualification of the bids or contract award decisions may result in the rejection of its bid. |
| 28.3 Notwithstanding ITB 28.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the PDE on any matter related to the bidding process, it should do so in writing   1. **Evaluation of Bids**    1. The PDE shall use the criteria and methodologies listed in Section 3, Evaluation Methodology and Criteria. No other evaluation criteria or methodology shall be permitted. By applying the set criteria and methodology, the PDE shall determine the Best Evaluated Bid.    2. If this bidding document allows bidders to quote separate prices for different lots, the methodology to determine the Best Evaluated Bid for a lot shall be as specified in Section 3, Evaluation Methodology and Criteria. |

|  |  |  |
| --- | --- | --- |
| **30. Clarification and Changes to Bids** | | |
| 30.1 To assist in the examination, evaluation, comparison and post-qualification of the bids, the Procuring and Disposing Entity may, at its discretion, ask any bidder for a clarification of its Bid, including breakdowns of unit rates or prices. Any clarification submitted by a bidder that is not in response to a request by the PDE shall not be considered. The PDE’s request for clarification and the Bidder’s response shall be in writing and copied to all bidders for information purposes. No change in the prices or substance of the bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the PDE in the evaluation of the bids, in accordance with ITB 32. | | |
| 30.2 If a bidder does not provide clarifications of its Bid by the date and time set in the PDE’s request for clarification, its Bid may be rejected. | | |
| **31. Compliance and Responsiveness of Bids** | | |
| 31.1 The PDE’s determination of a bid’s compliance and responsiveness is to be based only on the contents of the bid itself with the exception of findings recorded in the Evaluation Report after a due diligence or post qualification. | | |
| * 1. A substantially compliant and responsive bid is one that conforms to all the terms, conditions, and specifications of the Bidding Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that:      1. Affects in any substantial way the scope, quality, or performance of the Works specified in the Contract; or | | |
| 1. Limits in any substantial way, inconsistent with the Bidding Document, the PDE’s rights or the Bidder’s obligations under the Contract; or 2. If rectified would unfairly affect the competitive position of other Bidders presenting substantially compliant and responsive bids. 3. Impacts the key factors of a procurement including cost, risk, time and quality and causes -    1. Unacceptable time schedules, where it is stated in the bidding document that time is of the essence;    2. Unacceptable alternative technical details, such as design, materials, workmanship, specifications, standards or methodologies; or unacceptable counter-bids with respect to key contract terms and conditions, such as payment terms, price adjustment, liquidated damages, sub-contracting or warranty. | | |
| 31.3 If a bid is not substantially compliant and responsive to the Bidding Document, it shall be rejected by the PDE and may not subsequently be made compliant and responsive by the Bidder by correction of the material deviation, reservation, or omission. | | |
| **32. Nonconformities, Errors, and Omissions** | | |
| 32.1 Provided that a bid is substantially compliant and responsive, the PDE may waive any non-conformity or omission in the bid that does not constitute a material deviation. | | |
| 32.2 Provided that a bid is substantially compliant and responsive, the PDE may request that the bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities or omissions in the bid related to documentation requirements. Such omission shall not be related to any aspect of the price of the bid. Failure of the Bidder to comply with the request may result in the V | | |
| 32.3 Provided that a bid is substantially compliant and responsive, the PDE shall rectify nonmaterial nonconformities or omissions. To this effect, the bid price shall be adjusted, for comparison purposes only, to reflect the price of the missing or non-conforming item or component. The cost of any missing items will be added to the bid price using the highest price from other bids submitted. |
| 32.4 Provided that the bid is substantially compliant and responsive, the PDE shall correct arithmetic errors on the following basis:   1. If there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the PDE there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected; 2. If there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected; and 3. If there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. |
| 32.5 If a bidder does not accept the correction of errors, the bid shall be rejected and the BS may be forfeited or conditions in the BSD executed. |
| **33.** **Stages of Evaluation: Using the Technical Compliance Selection Evaluation Method**  The evaluation of a bid for the procurement of works using the technical compliance evaluation method shall be conducted under the following stages: |
| **34. Preliminary Examination of Bids – Eligibility and Administrative Compliance** |
| 34.1 The PDE shall examine the legal documentation to establish the eligibility of the bidders and to verify the validity and authenticity of the documents submitted by the bidder. |
| * 1. If after the examination of eligibility, the PDE determines that the bid is not compliant, it shall reject the bid with the exception of rectification of omissions in accordance with ITB 32.2.   2. The PDE shall confirm that the following administrative compliance documents and information have been provided in the bid. If any of these documents or information is missing or contrary to the requirements in the bidding document, the bid shall be rejected.      1. The Bid Submission Sheet duly signed by the authorized representative of the bidder, including:         1. A brief description of the works and related services offered;         2. The total price of the bid; and         3. The appropriate duration of the bid validity;      2. The Price Schedule;      3. A Power of Attorney in accordance with ITB 22.2; and      4. An authentic Bid Security or Bid Securing Declaration, whichever is applicable, in the appropriate form and amount. |
| 34.4 Eligibility and administrative compliance shall be determined on a pass or fail basis and a bid which is not eligible or administratively compliant shall be rejected at the preliminary stage of evaluation |
| **35. Detailed Evaluation** |
| 35.1 The PDE shall examine the technical aspects of the Bid submitted in accordance with ITB 16, in particular, to confirm that all requirements of Section 6, SORs have been met without any material deviation, reservation or omission. |
| * 1. The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB Clause 5, to clarifications in accordance with ITB Clause 30 and the qualification criteria indicated in Section 3, Evaluation Methodology and Criteria.   2. If, after the examination of the terms, conditions and requirements, the PDE determines that the bid is not substantially responsive in accordance with ITB 31, it shall reject the bid. |
| **36. Currency and Exchange Rate** |
| * 1. The currency that shall be used for evaluation purposes for all bids shall be Uganda Shillings unless otherwise authorized by a competent authority.   2. The exchange rate shall be the prevailing Bank of Uganda exchange rate at the date of bid submission deadline. |
| **37. Financial Comparison of Bids** |
| 37.1 The PDE will evaluate and compare only the bids determined to be substantially responsive following detailed evaluation in accordance with ITB 37.3. |
| 37.2 To financially evaluate a bid, the PDE shall only use the criteria and methodologies defined in this clause and in Section 3, Evaluation Methodology and Criteria. No other criteria or methodology shall be permitted. |
| 37.3 To financially compare bids, the PDE shall: |
| 1. Correct any arithmetic errors in accordance with ITB 30.1; 2. Apply any discounts offered in accordance with ITB 17; |
| 1. Make adjustments for any deviation that is not a material deviation in accordance with ITB 32; 2. Convert all bids to a single currency in accordance with ITB 18; 3. Apply any margin of preference, in accordance with ITB 38; 4. Determine the total evaluated price of each bid. |
| 37.4 The PDE shall consider prices that appear to:   1. Be unbalanced; 2. Show a misunderstanding of the requirements; or 3. Be intended to front load earnings. |
| 37.5 The PDE reserves the right to accept or reject any variation, deviation, or alternative offer. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the bidding documents or otherwise result in unsolicited benefits for the PDE will not be taken into account in bid evaluation, unless otherwise specified in Section 3, Evaluation Methodology and Criteria. |
| 37.6 The estimated effect of any price adjustment conditions under Clause 47 of the GCC, |

|  |
| --- |
| during the period of implementation of the Contract, will not be taken into account in bid evaluation, unless otherwise indicated in Section 3, Evaluation Methodology and Criteria. |
| **38. Margin of Preference** |
| 38.1 Unless otherwise specified in the BDS, a margin of preference shall apply. Where a Margin of Preference applies, its application and detail shall be specified in Section 3, Evaluation Methodology and Criteria. |
| * 1. For the purpose of granting a margin of domestic preference, bids will be classified in one of three groups, as follows:      1. Group A: Bids from contractors incorporated or registered in Uganda with more than fifty percent of the bidder’s shareholding owned by Ugandan citizens or by the Government or a procuring and disposing entity of Uganda;      2. Group B: Bids from joint ventures, consortium or associations registered in Uganda and including a contractor qualifying under the conditions in paragraph (a) which holds more than fifty percent beneficiary interest in the joint venture, consortium or association; and      3. Group C: All other bids which do not qualify for preference under paragraphs (a) or (b). |
| * 1. Bidders claiming eligibility for a Margin of Preference must complete the declarations in the bid submission sheet and shall provide the following documentary evidence of their eligibility:      1. National Identity Card or copies of key passport pages to establish the nationality of the bidder or shareholder;      2. The relevant company forms or its equivalent indicating the shareholding percentages.  1. **Post-qualification Evaluation**    1. The PDE shall determine to its satisfaction whether the Bidder that is selected as having submitted the best evaluated bid is qualified to perform the Contract satisfactorily.    2. An affirmative determination shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the bid, in which event the PDE shall proceed to the next best evaluated bid to make a similar determination of that Bidder’s capabilities to perform satisfactorily.    3. Post-qualification will be conducted in accordance to the PPDA Act, 2003. |
| **40. Determination of Best Evaluated Bid** |
| The best evaluated bid shall be the lowest priced bid which is eligible, administratively and technically compliant to the requirements specified in the bidding document. |
| **Award of Contract** |
| **41. Award Procedure and Notice of Best Evaluated Bidder** |

|  |  |  |
| --- | --- | --- |
| * 1. An award decision by the Contracts Committee is not a contract. The bidder with the best evaluated bid shall be awarded the contract following an adjudication by the Contracts Committee.   2. The PDE shall issue a Notice of Best Evaluated Bidder (NOBEB) within five (5) working days after the decision of the Contracts Committee to award a contract, deliver a copy of the notice to all bidders who participated in the bidding process, place such Notice on its notice board for display for ten (10) working days and publish it on the website of the Authority. The computation of the ten (10) working days shall commence from the next day following the display of the notice.   3. No contract shall be signed within the period of ten (10) working days after the date of display of the best evaluated bidder notice.   4. Negotiations will only be held in exceptional circumstances as provided for under the PPDA Act 2003. | | |
| **42. PDE’s Right to Accept Any Bid And to Reject Any or all Bids**  The PDE reserves the right to accept or reject any bid and to cancel the bidding process at any time prior to contract award, without thereby incurring any liability. | | |
| **43. Confirmation of Award** | | |
| An award shall be confirmed by a written contract signed by both the bidder and the PDE. | | |
| **44. Signing and Effectiveness of Contract** | | |
| * 1. On expiry of the ten (10) working day period after display of the best evaluated bidder notice and upon approval by the Attorney General where applicable, the PDE shall promptly sign a contract with the successful Bidder.   2. Failure by the successful bidder to promptly sign the contract shall constitute sufficient ground for annulment of the contract award decision and forfeiture of the Bid Security or execution of the Bid Securing Declaration. In that event, the PDE may award the Contract to the next best ranked bidder whose bid was evaluated at the financial comparison stage.   3. Effectiveness of the contract shall be subject to submission of a satisfactory performance security where applicable and any other conditions specified in the Contract.   4. A contract shall not be entered into by an Accounting Officer with a bidder during the period of administrative review as provided for under the PPDA Act, 2003. | | |
| **45. Debriefing of Bidders** | | |
| 45.1 The bidder shall be provided with information on the reasons for the failure of its bid in the notice of best evaluated bidder. | | |
| **46. Performance Security** | | |
| 46.1 Within twenty-one (21) calendar days after signing of the contract, the successful bidder shall where applicable, furnish to the PDE a Performance Security and, if required in the BDS, the Environmental and Social (ES) Performance Security in the amount stipulated in the SCC and in the form of an on demand Bank Guarantee as stipulated in Section 9, denominated in the type and proportions of the currencies of the Contract. | | |
| The Performance Security shall be issued by a Bank located in Uganda or a foreign Bank through correspondence with a Bank located in Uganda. |
| 46.2 Failure of the successful bidder to submit the above-mentioned Performance Security and, if required in the BDS, the Environmental and Social (ES) Performance Security, shall constitute sufficient ground for annulment of the contract award decision. In this case, or where the successful bidder fails to sign the contract as stated in ITB Clause 44.2, the successful Bidder’s Bid Security shall be forfeited or the conditions of the Bid Securing Declaration shall be executed. In that event, the PDE may award the contract to the next best ranked bidder whose bid was evaluated at the financial comparison stage. |
| **47. Administrative Review** |
| * 1. Bidders may seek an Administrative Review for any omission or breach by the PDE in accordance with the Public Procurement and Disposal of Public Assets Act, 2003, any regulations or guidelines made under the Act.   2. The PDE shall promptly provide a bidder who seeks administrative review with:      1. A summary of the evaluation process      2. A comparison of the tenders, proposals, or quotations including the evaluation criteria used, and      3. The reasons for rejecting the concerned bids. |

(d) The details of the applicable administrative review fees and the account to which the fees are to be paid

**Section 2: Bid Data Sheet**

| **Instructions to Bidders Reference** | **Data relevant to the ITB** |
| --- | --- |
| **ITB 1.1** | The Procuring and Disposing Entity is:- **KAMPALA CAPITAL CITY AUTHORITY** |
|  | The works consist of  **Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP**  **Lot 1: Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km)** |
| **ITB 1.1** | The Procurement Reference Number of the Contract is:  KCCA-GKMA/WRKS/2025-2026/00008/1 |
| **ITB 1.1** | The number and identification of lots comprising this Bidding Document is **LOT1**:  The minimum number of lots per bidder is 01, and maximum number of lots a bidder may bid for is 03.   * + - 1. ***Each Lot shall be a separate Contract***       2. ***Each Lot shall be submitted as a separate bid***       3. ***A bid shall be evaluated under the lot where it is received***       4. ***No bidder shall be awarded more than 1 Lot.***       5. ***If a bidder is evaluated as the best in more than one (01) Lot, the bidder will be awarded a contract for one (01) lot which gives the Entity the most optimal economic/financial benefit.*** |
| **ITB 6.2** | The minimum share of the partner in charge of a joint venture shall not be less than 51% of the total value of the Contract in addition to the requirements stated in ITB 6.2 |
| **ITB 9.3** | Kampala Capital City Authority *shall* be holding a pre-bid meeting **followed by SIT VISITS to the different Roads** as follows:  Address of the meeting shall be:  **Kampala Capital City Authority**  **Plot 1-3, Apolo Kaggwa Road,**  **P.O Box 7010, Kampala**  Location: **The Mayor’s Parlour, City Hall**  Date: 20th August 2025  Time: 11.00am  **Note**: Bidders are advised to send experienced and competent personnel for the site visits, for the purposes of assessing the risks, contingencies and other circumstances which may influence or affect the bid or the Works including, but not limited to, methods of construction of the various parts (components) of the Works, sources of materials and delivery of resources to Site. Bidders will be responsible for their transport and associated costs to the respective sites. |
| **ITB 9.5** | Site visit **SHALL** be a mandatory requirement. Kampala Capital City Authority shall issue a site visit certificate (signed by Chairperson of the pre-bid meeting) to the prospective bidders as proof of having satisfactorily visited the project site to obtain sufficient information to inform their bid. Certificates should be picked from entities according to the respective project locations. Guided site visits shall be conducted during official working hours in line with the schedule indicated in the Bid Notice or BDS. The site inspection certificate SHALL be part of the bid. |
| **ITB 12.1** | For clarification purposes only, the Procuring and Disposing Entity’s address is:  **Head** **Procurement & Disposal Department;**  **Kampala Capital City Authority**  Street Address: **Plot 1-3 Apolo Kaggwa**  Town/City: **Kampala**  PO Box No **7010, Kampala, Uganda**  Electronic mail address: [**procurement@kcca.go.ug**](mailto:procurement@kcca.go.ug) |
| **ITB 12.1** | The Procuring and Disposing Entity will respond to any request for clarification provided that such request is received no later than **3rd September 2025, 4:30 Pm** |
| **ITB 15.1** | The bidder shall submit with its bid the following additional documents:  The Bidder shall submit the following additional documents in its Bid:   1. **Evidence in form of signed contract agreements, with their corresponding completion certificates / Interim Payment Certificates or reference letters demonstrating good performance from all recent Employers within the last five (5) years to confirm satisfactory performance;** 2. **Where a Joint Venture is proposed, a copy of the Joint Venture Agreement entered into by all partners should be submitted; In the case of Bids submitted by a JV, a Power of Attorney from each member of the JV nominating a Representative in the JV and a Power of Attorney from the JV nominating a representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the JV;** 3. **Letter introducing the PDE to the bidder's bankers and authorizing the bank to provide necessary information;** 4. **Letters from insurance companies confirming that they are willing to provide the required insurance cover under the Contract if the Contractor is awarded the contract;** 5. **For contracts cited as specific experience, the bidder shall include in its bid the contact information including telephone numbers, email addresses and physical locations of previous Employers as well as the addresses and physical locations of the Works. All the Contact details must be reachable. Previous employers shall formally be contacted to confirm performance and given sufficient time to respond. Failure to reach any previous employer, and/or failure to receive timely response may result in disqualification of the bid prior to Contract Signature.** 6. **ESHS Code of Conduct for Contractor’s Personnel**   The bidder shall submit its Code of Conduct that will apply to the Contractor’s Personnel to ensure compliance with its Environmental, Social, Health and Safety (ESHS) obligations under the contract (sample has been provided under supplementary information).  In addition, the Bidder shall detail how this Code of Conduct will be implemented. This will include: how it will be introduced into conditions of employment/engagement, what training will be provided, how it will be monitored and how the Contractor proposes to deal with any breaches. The Contractor shall be required to implement the agreed Code of Conduct. The Code of Conduct shall cover, among others:   1. Code of conduct for Environment Restoration of construction and auxiliary sites. 2. Code of conduct for managing environment pollution. 3. Code of conduct for consistent use of Personal Protective Equipment. 4. Code of conduct for waste (solid, medical and hazardous waste) 5. Code of conduct for sanitation management 6. Anti-smoking code of conduct 7. Code of conduct for providing alternative access to business premises and or communities 8. Code of conduct for child protection and child labour 9. Code of conduct for eliminating and managing Gender Based Violence 10. Code of conduct for eliminating sexual harassment. 11. Anti-HIV and AIDS and Sexual Transmission Infection code of conduct 12. Labor Force Code of Conduct for recruitment, deployment and operationalization of Environment and Social Safeguard teams and disciplinary measures 13. Code of conduct for payment of workers, sub-contractors and suppliers of goods and services 14. Code of conduct on security personnel 15. Code of conduct for Emergency management 16. Code of conduct for managing cultural sensitivity 17. Code of conduct for managing stakeholder engagements, communications and public relations 18. Code of conduct for injurious compensation 19. Code of conduct on forced labour 20. Code of conduct on indigenous peoples 21. Code of conduct on third party contracted workers including suppliers 22. Code of conduct of non-discrimination and equal opportunity 23. Code of conduct on cultural heritage 24. Code of conduct for establishment of workers camp and 25. Decommissioning code of conduct. 26. **Environment and Social Management Plan (ESMP)**   The Contractor shall be required to submit for approval, and subsequently implement, the Contractor’s Environment and Social Management Plan that includes the Strategies and Implementation Plans described below**:**   1. Plan for establishment, operation and decommissioning of workers’ camp 2. Traffic management Plan and community safety plan to ensure safety of pedestrians and traffic from construction traffic 3. Boundary marking and protection strategy for mobilisation and 4. construction to prevent offsite adverse impacts. 5. Strategy for obtaining consents and /or permits prior to the start of relevant works such as opening of quarry and borrow pits 6. Gender management plan including Gender based violence and Sexual Exploitation and Abuse (GBV/SEA) prevention and response action. 7. Injurious Compensation Plan 8. Grievance Management Plan 9. Occupational Health and Safety 10. Child Protection Plan 11. HIV and AIDS and other STI Prevention and Management Plan 12. Waste (solid, medical and hazardous waste) Management and Disposal Plan 13. Human Resource Management Plan for recruitment, staff contracts, training, retention and exit of workers 14. Accident Prevention and Management Plan 15. Communication and Stakeholder engagement plan 16. Safe Accessibility Plan 17. Sanitation Management Plan 18. Physical-cultural resource management Plan 19. Project decommissioning Plan (including decommissioning for material sources sites, workers camp and material storage sites)   **AND ANY OTHER DOCUMENTS AS INDICATED UNDER SECTION 1: ITB 15, SECTION 3 AND SECTION 4, AND OTHERS PRESCRIBED BY THE REGULATIONS** |
| **ITB 17.6** | The Bid price shall be adjusted by the following factor(s): **N/A** |
| **ITB 18.2** | The Authority for specifying rates of exchange shall be **the Bank of Uganda**. |
| **ITB 18.3** | All bid prices shall be quoted in Uganda shillings |
| **ITB 19.1** | The Bid validity period shall be valid up to **5th February 2026** |
| **ITB 20.1** | A Bid Security **SHALL** be required. |
| **ITB 20.2** | The bid security shall be **in the form of an On-Demand Bank Guarantee from a reputable Commercial Bank recognized by Bank of Uganda**. Bid securities from Banks outside Uganda shall be issued through a Local Corresponding Bank  The amount and currency of Bid Security shall be **as below.**   |  |  |  |  | | --- | --- | --- | --- | | **No.** | **Procurement Reference Number** | **Subject Matter of Procurement** | **Bid Security** | | **Lot 1** | **KCCA-GKMA/**  **WRKS/2025-2026/00008/1** | **Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP**  **Lot 1: Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km)** | **UGX.600,000,000** | |
| **ITB 20.3** | The Bid Security shall be valid up to **4th March 2026** |
| **ITB 21.1** | Alternative Bids **shall not be considered.** |
| **ITB 22.1** | In addition to the original copy of the Bid, the number of copies is: **Five (5) bound and 1 (one) soft copy of the entire Bid on a USB drive or Flash disc**  **A soft copy of the bidder’s priced BoQ (MS Excel (xlx or xls) shall also be part of the submission.**  **All pages of the bid shall be numbered**  In the event of any discrepancy between the hardcopy and the soft copy, the hardcopy shall prevail. |
| **ITB 22.2** | The written confirmation of authorization to sign on behalf of the Bidder shall be:   1. **A Registered Power of Attorney specific to this procurement, If drawn and signed in Uganda; or a notarized Power of Attorney also specific to this procurement, if drawn and signed outside Uganda should be provided; and** 2. **In the case of Bids submitted by a Venture, Consortium or Association (JVCA) an undertaking signed by all parties shall:** 3. **state that all parties shall be jointly and severally liable, if so required in accordance with ITB 4.1(a), and** 4. **nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the parties of the Joint Venture, Consortium or Association (JVCA) during the bidding process and, in the event the Joint Venture, Consortium or Association (JVCA) is awarded the Contract, during contract execution**. |
| **ITB 23.1** | For bid submission purposes only, the Procuring and Disposing Entity’s address is:  **The Procurement & Disposal Department, Kampala Capital City Authority**  Street Address: **Plot 1-3 Apolo Kaggwa Road**  Town/City: **Kampala**  PO Box No **7010, Kampala, Uganda**  Room Number: **Room B117**  Date: **10th September 2025**, Time: **11.00am** |
| **ITB 24.1** | The deadline for bid submission is:  Date: **10th September 2025**, Time: **11.00am** |
| **ITB 27.1** | The bid opening shall take place at:  **Procurement & Disposal Department, Kampala Capital City Authority**  Street Address: **Plot 1-3 Apolo Kaggwa Road**  Town/City: **Kampala**  PO Box No **7010, Kampala, Uganda**  Room Number; **Room B117**  Date: **10th September 2025**, Time: **11.30a.m** |
| **ITB 38.1** | A margin of preference **SHALL NOT** apply. |
| **ITB 38.3** | The Bidder shall submit with its bid the following documents to evidence that they qualify for a margin of preference: **N/A** |
| **ITB 46.1** | The successful Bidder shall be required to submit an Environmental and Social (ES) Performance Security.  **The Environmental and Social Performance Security shall be 1% of the total contract value**  **The Performance Security shall be 4% of the total contract value** |

|  |
| --- |
| **Section 3: Evaluation Methodology and Criteria** |
| **Procurement Reference Number: KCCA-GKMA/WRKS/2025-26/00008/1** |
| **A. Evaluation Methodology** |
| **1. Methodology Used** |
| The evaluation methodology to be used for the evaluation of bids received shall be ***the Technical Compliance Selection (TCS) methodology***. |
| **2. Summary of Methodology** |
| * 1. The evaluation shall be conducted in four sequential stages –      1. A preliminary examination to determine the eligibility of bidders and the administrative compliance of bids received;      2. A detailed evaluation to determine the technical responsiveness of the eligible and compliant bids;      3. A financial comparison to compare costs of the eligible, compliant, responsive bids received and determine the best evaluated bid; and      4. Post qualification to confirm whether the best evaluated bidder has the capacity and resources to effectively execute the procurement   2. Failure of a bid at any stage of the evaluation shall prevent further consideration at the next stage of evaluation. Substantial responsiveness shall be considered a pass at the detailed evaluation stage. |
| **B. Preliminary Examination Criteria** |
| **3. Eligibility Criteria** |
| 3.1 The eligibility requirements shall be determined in accordance with ITB Clause 4; and |
| * 1. The documentation required to provide evidence of eligibility shall be:-      1. ***A copy of the bidder’s valid trading license or equivalent and a copy of the bidder’s certificate of registration or equivalent for bidders not currently registered with the Authority;***      2. ***A statement in the bid submission sheet that the bidder meets the eligibility criteria stated in ITB 4.1 and 4.4;***      3. ***A declaration in the bid submission sheet of nationality of the bidder;***      4. ***A declaration in the bid submission sheet that the bidder is not under suspension by the authority;***      5. ***Fulfilment of obligations to pay taxes evidenced by a valid tax clearance certificate (for a tax period ending 30 June 2025), or its equivalent addressed to Kampala Capital City Authority. Foreign firms shall submit an equivalent of Tax Clearance Certificates from their Countries of domicile.***      6. ***Fulfilment of obligations to pay Social security contributions in Uganda where applicable or its equivalent. This shall be evidenced by a valid National Social Security Certificate (for the period up to July 2025, at least)***      7. ***The Beneficial Ownership Declaration Form.*** The bidder shall submit details of the registration certificates and certificates of incorporation of the local company (ies) as well. |
| 3.3 For Joint Venture or Consortiums or Associations;   1. A registered Power of Attorney from each member or partner if drawn and signed in Uganda; or a notarized Power of Attorney if drawn and signed outside Uganda, nominating a representative to conduct all business on its behalf during the bid preparation, bidding process and contract execution in case of award of the contract. 2. The documentation in Section 3.2 for each member or partner and a copy of the Joint Venture / Consortium / Association Agreement which is legally binding on all partners or members stating that:    1. *The partners or members shall jointly submit a bid;*    2. *One of the parties will be nominated as lead member or partner to act for and on behalf of all members or partners;*    3. *The authorized representative of the lead member or partner who was granted power of attorney shall sign the bid;*    4. *In the event that the bid is successful, the contract shall be executed in the name of the Joint Venture (JV), Consortium or Association and each member or partner shall sign the contract agreement; and*    5. *All partners shall be jointly and severally liable for the implementation of the contract in accordance with the contract terms.* |
| **4. Administrative Compliance Criteria**  The evaluation of Administrative Compliance criteria shall be conducted in accordance with ITB Clause 34.3. In addition, the following shall be assessed for Administrative Compliance:   1. ***Code of Ethical Conduct in Business for Providers and Bidders*** 2. ***Original receipt for the purchase of Tender Documents.*** 3. ***The number of copies of the bid to be submitted are five (5) in addition to the original*** 4. ***Site visit Certificates from Kampala Capital City Authority depending on the location of the site visited, and in accordance with the corresponding Lot selected.*** |
| **C. Detailed Evaluation Criteria** |
| 1. **Assessment of Responsiveness**    1. The assessment of responsiveness will consider the following criteria:       1. Acceptance of the conditions of the proposed contract;       2. Acceptable completion schedule ***(all works including the mobilization shall be completed within 18months***);       3. Acceptability of the proposed program (work method and schedule), including relevant drawings and charts.   The Bidder will be required to submit the following to facilitate the evaluation process:   * Site Organisation - **In this section, the bidder is required to provide an organogram of the human resource that will execute this project. This should include both the Head Office and Site Office staff and the linkage between the site offices and head office.** * Method Statement - In this section, the bidder is required to give a detailed statement of how he intends to execute the project inclusive of but not limited to the following; **acquiring the necessary permits and permissions, relocation of utilities, erection of temporary site facilities and permanent civil works; including a methodology in working congested/busy urban environments. Bidder should demonstrate that they are able to work at night. For this Lot, the bidder shall demonstrate how they intend to implement the signalised junctions in the works.** * Mobilisation Schedule - In this section, the bidder is required to make a **detailed schedule of the mobilization and demobilization of all the necessary manpower and equipment**. This schedule should be produced in at least **MS Project 2016**; duration allocated to each task, indicating milestones, expected shipping time for oversees plant, equipment and materials and travel in and out of the country for the expected expatriate staff. A softcopy of this schedule should be attached in CD format to the bids * Construction Schedule - In this section, the bidder is required to make a **detailed schedule of the civil works construction phase**. This schedule should be produced in at least, **MS Project 2016**; well-resourced with the expected manpower and equipment expected to undertake each particular task, duration allocated to each task and indicating milestones. A softcopy of this schedule should be attached in CD format to the bids.   **6. Mobilization**  Evaluation of the responsiveness of the bid to the technical requirements will include an assessment of the bidder's capacity to mobilize key equipment and personnel for the contract consistent with its proposal regarding work methods, scheduling, and material sourcing in sufficient detail and fully in accordance with the requirements stipulated in Section 6 (Statement of Requirements).  7. Sustainable Procurement: Based on the following main considerations:   1. Socio-economic consideration: ESHS management strategies and implementation plans (ESHS MSIPs) including purpose, objectives/goals, ownership of the document. 2. Management structure; including Management framework/organization, key ESHS staffing and definition of duties and responsibilities; 3. ESHS analysis – comprehensiveness; including the detail of ESHS aspects, scope and internal controls 4. Supportive/incidental plans; including presentation in relative detail of;  * Community Management/engagement plan, strategy for acquisition of approvals (and demonstrated knowledge of these approvals), * Traffic Management Plan, Safety Plan, Labour Management Plan, Anti-Sexual Harassment strategy/Policy, Grievance Redress Mechanism, etc.  1. Environmentally and Socially Responsible Procurement: 2. **Ownership**   This refers to the structure and content of the ESHS documentation i.e. Management Strategies and Implementation Plans (MSIPs).  The documentation should clearly demonstrate the bidder’s ownership to their bid. This shall be shown by integration of safeguards, aspects including competent staffing into the bidders’ organogram at the project level, and/or within their structure at their headquarters. The documentation (MSIPs shall clearly demonstrate roles of safeguards team and other project technical staff in the implementation of the MSIPs. Ownership shall also be reflected in reference to the Bidder’s performance in safeguards management on previous assignments and reflection of ESHS management system as part of their performance culture. The bidder’s presentation of their specific experience shall include acquisition of statutory approvals from responsible lead agencies. Evidence of specific experience with safeguards management on the previous contracts, shall include but not limited to information as;  • Grievance management logs,  • Incident management logs,  • Copy of the incident root-cause analysis reports,  • Copy of the equipment maintenance logs,  • Equipment service logs  • Report on air quality and noise monitoring  • Responses to inspection reports, evidence of audit reports for support facilities  • Copies of the incident root-cause analysis;  • Response to the corrective action plan in the annual environmental compliance audits;  • Copies of ESHS inspection reports and responses from the Contractors on the corresponding actions taken;  • Minutes of the meetings by the Grievance Redress Committees  • Reports by the Safety Committees;  • Permits, approvals, certificates and licenses issued by the responsible lead agencies in line with the national enabling laws and regulations,  • Copies of responses to the “Notice to Correct”  • NEMA approval of the Final Environmental impact mitigation report   1. **Scope**   The scope relates to the level of detail and coverage of the project components. Bidders are required to adequately present the related national ESHS policy and legal framework, potential impacts and risks from the implementation of the proposed project and mitigation measures.  The scope shall also include the bidder’s coverage of support facilities including the Workers’ camps, equipment yards, material sources (stone quarries, borrow pits, sand quarries, material stockpiles, etc.); strategies for acquisition of statutory approvals, balanced presentation on ESHS and internal ESHS controls (monitoring and reporting mechanisms). |

#### Personnel and Equipment

#### Personnel: The bidder must demonstrate that it will have the personnel for the key positions that meet the following requirements. Bidders with ongoing works/projects in Uganda, they should provide evidence that the personnel proposed for this project are different from the ones on ongoing works. (This will be validated through post-qualification);

| **Item No.** | **Position/specialization** | **Relevant academic qualifications[[1]](#footnote-1)** | **Minimum years of relevant work experience (after graduation)** | **Total Work**  **Experience**  **(years) (after graduation)** | **Experience in a similar Position (years)** | **Quantity** |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Contractor’s Representative [Project Manager] | B.Sc. Civil Engineering or Equivalent; Registered/Chartered Engineer with a Valid practicing licence | 15 | 20 | 10 | 1 |
| 2 | Site/Earthworks Engineer | B.Sc. Civil Engineering or Equivalent; Registered/Chartered Engineer with a Valid practicing licence | 10 | 15 | 8 | 1 |
| 3 | Plant and Equipment Foreman | B.Sc. Engineering or Equivalent | 10 | 15 | 8 | 3 |
| 4 | Drainage and Structures Engineer | B.Sc. Civil Engineering or Equivalent; Registered/Chartered Engineer with a Valid practicing licence | 10 | 15 | 8 | 1 |
| 5 | Electrical Engineer | B.Sc. Electrical Engineering or Equivalent; Registered/Chartered Engineer with a Valid practicing licence | 10 | 15 | 5 | 1 |
| 6 | Quantity Surveyor | B.Sc. Quantity Surveying or Equivalent; Registered with a relevant body | 10 | 15 | 8 | 1 |
| 7 | Senior Land Surveyor | B.Sc. Surveying or Equivalent; Registered with a relevant body | 10 | 15 | 8 | 1 |
| 8 | Materials and Pavement Engineer/Quality Manager | B.Sc. Civil Engineering or Equivalent; Registered/Chartered Engineer with a Valid practicing licence | 10 | 15 | 8 | 1 |
| 9 | Environmental & Social Safeguards Manager | BSc. Environmental Science or Equivalent; Registered environmental practitioner | 8 | 10 | 5 | 1 |
| 10 | Environmental Officer | BSc. Environmental Science or Equivalent; | 8 | 10 | 5 | 1 |
| 11 | Health and Safety Officer | BSc. Health and Safety or equivalent/ Bachelors Degree and Certificate in Health and Safety | 8 | 10 | 5 | 22 |
| 12 | Social Development Officer | BA. Social Science, BA. Social Works and & Social Administration or Equivalent | 8 | 10 | 6 | 2[[2]](#footnote-2) |

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Forms included in Section IV, Bidding Forms.

#### Equipment

1. The bidder must demonstrate that it shall have access to the key equipment located within Uganda, Kenya or Tanzania, Rwanda, listed hereafter (either by ownership, lease, hire): Attach documentary evidence of ownership, lease, hire such as registration books, agreements). **Invoices, Bills of Lading and purchase orders shall not be considered as evidence of ownership.** **Bidders with ongoing works/projects in Uganda should provide evidence that the equipment proposed for this project is different from the ones on ongoing works. (This will be validated through post-qualification);**

| **No** | **Equipment Type and Characteristics** | **Minimum Number required** |
| --- | --- | --- |
| 1 | Hot Mix Plant (batch type only, with electronic & computer controls and vibratory screens. 60 tons/hour capacity | 1 |
| 2 | Stone crusher with screening unit (Minimum capacity 50 tons/ hour) | 1 |
| 3 | Asphalt Paver capable of laying 7 m width fitted with Electronic sensors for automatic level control | 1 |
| 4 | Crawler Dozer + Ripper D8, 250 to 350 HP | 2 |
| 5 | Wheel Front End Loader 170HP | 2 |
| 6 | Excavators 0.25 – 0.4 m3 SAE bucket 140 HP | 2 |
| 7 | Dump Truck (Tipper Truck) 10 – 15 m3 | 10 |
| 8 | Water Bowser 12,000 litres | 2 |
| 9 | Motor Grader 140 to 185HP | 2 |
| 10 | Smooth Wheeled Roller 10-12 tons | 2 |
| 11 | Vibrating Roller 12-14 tons | 2 |
| 12 | Pneumatic Tyred Roller up to 16 tons | 2 |
| 13 | Mechanical broom | 2 |
| 14 | Concrete mixer 0.5 – 1.0 m3 | 2 |
| 15 | Concrete Transit Mixer | 2 |
| 16 | Mobile Crane 40 tons | 2 |
| 17 | Bitumen Distributor 8000litres | 2 |
| 18 | Grid Roller 10 – 13.5 ton | 2 |
| 19 | Road Reclaimer/ Miller/ Pulvmixer | 1 |
| 20 | Low-bed | 1 |

The bidder shall provide further details of proposed items of equipment using the relevant Form in Section 4.

* 1. **Qualification**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Factor** | **Historical Contract Non-Performance** | | | | | |
| **Sub-Factor** | **Criteria** | | | | | **Documentation Required** |
| **Requirement** | **Bidder** | | | |
| **Single Entity** | **Joint Venture, Consortium or Association** | | |
| **All partners combined** | **Each partner** | **At least one partner** |
| *6.2.1 History of non- performing contracts* | Non-performance of a contract did not occur within the last **Five** years prior to the deadline for application submission, based on all information on fully settled disputes or litigation. | Must meet requirement by itself or as partner to past or  existing JV | N / A | Must meet requirement by itself or as partner to past or  existing JV | N / A | Form 5 |
| *6.2.2 Pending Litigation* | All pending litigation shall in total not represent more than **Twenty** percent (**20**%) of the Bidder’s net worth and  shall be treated as resolved against the Bidder**.** | Must meet requirement by itself or as partner to past or  existing JV | N / A | Must meet requirement by itself or as partner to  past or  existing JV | N / A | Form 5A |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Factor** | **Historical Contract Non-Performance** | | | | | |
| **Sub-Factor** | **Criteria** | | | | | **Documentation Required** |
| **Requirement** | **Bidder** | | | |
| **Single Entity** | **Joint Venture, Consortium or Association** | | |
| **All partners combined** | **Each partner** | **At least one partner** |
| *6.2.3 Declaration: Environmental, Social, Health, and Safety (ESHS) past*  *performance* | Declare any civil work contracts that have been suspended or terminated and/or performance security called by an employer for reasons related to the non- compliance of any environmental, or social, or health or safety requirements or safeguard in the **past five years1.** | Must make the declaration.  Where there are Specialized Sub- contractor/s, the Specialized Sub- contractor/s must also  make the declaration. | N/A | Each must  make the declaration.  Where there are Specialized Sub- contractor/s, the Specialized Sub- contractor/s must also  make the declaration. | N/A | Form 5B  ESHS Performance Declaration |

1 The Employer may use this information to seek further information or clarifications in carrying out its due diligence.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Factor** | **Financial Situation and Performance** | | | | | |
| **Sub-Factor** | **Criteria** | | | | | **Documentation Required** |
| **Requirement** | **Bidder** | | | |
| **Single Entity** | **Joint Venture, Consortium or Association** | | |
| **All partners combined** | **Each partner** | **At least one partner** |
| *6.2.4 Historical Financial Performance* | Submission of audited books of accounts or other financial statements acceptable to the Employer, for the last **Three** years (2021-2022, 2022-2023, 2023-2024) to demonstrate the current soundness of the bidders financial position and its prospective long term profitability. The books should have been audited by a certified accountant/firm. | Must meet requirement | N / A | Must meet requirement | N / A | Form 6 and audited financial statements |
| *6.2.5 Average Annual Turnover* | Minimum average annual turnover of  **Uganda shillings Seventy (70) Billion** calculated from total certified payments received for contracts in progress or completed, within the last **Three (3)** years | Must meet requirement | Must meet requirement | Must meet **thirty**  percent  (30%) of the requirement | Must meet **Seventy**  percent  (70%) of the requirement | Form 7 and audited financial statements |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Factor** | **Financial Situation and Performance** | | | | | |
| **Sub-Factor** | **Criteria** | | | | | **Documentation Required** |
| **Requirement** | **Bidder** | | | |
| **Single Entity** | **Joint Venture, Consortium or Association** | | |
| **All partners**  **combined** | **Each partner** | **At least one partner** |
| *6.2.6 Financial Resources* | The Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet:   1. the following cash-flow requirement:   **Uganda shillings 15 Billion**  **Every 4 months’** cycle and   1. the overall cash flow   requirements for this contract and its concurrent commitments. | Must meet requirement | Must meet requirement | N/A | Must meet the requirement | Form 8 and line of credit |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ***Factor*** | **Experience** | | | | | |
| ***Sub-Factor*** | ***Criteria*** | | | | | ***Documentation Required*** |
| ***Requirement*** | ***Bidder*** | | | |
| ***Single Entity*** | ***Joint Venture, Consortium or Association*** | | |
| ***All partners combined*** | ***Each partner*** | ***At least one partner*** |
| 6.2.7 General Experience | Experience under contracts in the role of contractor, subcontractor, or management contractor for at the last **Five (05)** years prior to the bid submission deadline, and with activity in at least  **Six** months in each year. | Must meet requirement | N / A | Must meet requirement | N / A | Form 9 and Certificates of Completion or Substantial Completion |
| 6.2.8 Specific Experience | (a) Participation as contractor, in at least **Two** contracts within the last **Five** years, each with a value of at least **Uganda Shillings seventy (70) billion**, that have been successfully and substantially completed (at least 80percent complete) in Sub-Saharan African countries and that are similar to the proposed Works. The similarity shall be based on the physical size, & complexity.  **Bidders with works contracts under GKMA-UDP should demonstrate that they have achieved at least 70% physical progress. Evidence shall be in form of the latest (June 2025) progress reports.** | Must meet requirement | Must meet requirements for all characteristics | Must meet **thirty**  percent  (40%) of the requirement | Must meet **Sixty**  percent  (60%) of the requirement | Form 10 and Certificates of Completion or Substantial Completion |

| ***Factor*** | **Experience** | | | | | |
| --- | --- | --- | --- | --- | --- | --- |
| ***Sub-Factor*** | ***Criteria*** | | | | | ***Documentation Required*** |
| ***Requirement*** | ***Bidder*** | | | |
| ***Single Entity*** | ***Joint Venture, Consortium or Association*** | | |
| ***All partners combined*** | ***Each partner*** | ***At least one partner*** |
|  | methods/technology or other characteristics as described in  Section 6, Statement of Requirements.  Scope of Works. The minimum key requirements shall include upgrading/ reconstruction of **not less than 8.0km** of roads in an urban environment, laying of crushed stone aggregate, Dense Bituminous Macadam (DBM), asphalt concrete and installation of solar street lights. |  |  |  |  |  |
| 6.2.9 Specific Experience | For the above or other contracts executed during the period stipulated in 6.2.8 (a) above, a minimum experience in the following key activities: | Must meet requirements | Must meet requirements | N / A | Must meet requirements | Form 10 and copies of the contracts providing the scope of the works |
| 1. Gravel fill and subgrade – **45,000m3** | 45,000m3 annual average | 45,000m3 annual average |  | 25,000m3 annual average |  |
| 1. Scarification and re-compaction of existing layers– **6,000 m3** | 6,000m3 annual average | 6,000m3 annual average |  | 3,000m3 annual average |  |
| 1. Crushed Stone Subbase or Base – **20,000m3** | 20,000m3 annual average | 20,000m3 annual average |  | 10,000m3 annual average |  |
| 1. Asphalt concrete Surfacing - **4,000m3** | 4,000m3 annual average | 4,000m3 annual average |  | 2,000m3 annual average |  |
| 1. Dense Bituminous Macadam (DBM)- **10,000m3** | 11,000m3 annual average | 11,000m3 annual average |  | 5,500m3 annual average |  |
| 1. Culvert installation – **12,000m** | 7,000m annual average- | 7,000m annual average |  | 3,500m annual average |  |
|  | 1. Street light installation- **500 Number** | 500 annual average | 500 annual average |  | 250 annual average |  |
| 6.2.10 Specific Experience-Environment and Social Activities | Experience in Implementing Environmental and social (ES) aspects in construction projects including but not limited to:   * Biodiversity, * Traffic management, * Child protection, * Consents and permits, * Occupational safety and health, * Grievance management, * Waste management and disposal, * HIV/AIDS and STIs, * Accident prevention and management, * Communication and stakeholder engagement, * Water resource protection,   Gender management. | Must meet requirements | Must meet requirements | N/A | N/A | Form 10B and evidence of efforts to attain compliance with ES requirements in previous contracts including but not limited to   * NEMA certificates, * Workplace registration certificates from MoGLSD, * Copies of Development permits, hoarding permits for auxiliary sites in the previous contracts. * Evidence/Documents as listed in section 7(ii) a) above |
|  | LOCAL CONTENT |  |  |  |  |  |
| 6.2.11 | In accordance with the PPDA guideline issued on 01 March 2017, and the local content Bill 2019, the bidder must submit evidence of a sub-contracting arrangement or other agreement with a local company or local companies (*A local company is defined as a company registered in Uganda and wholly owned by Ugandans*) that shall include details of the works with the local company/ies **amounting to at least 30% of the scope of contracted works.** | Must meet requirement | Must meet requirement | N/A | N/A | Form 11 |
| 6.2.12 | The bidder shall submit details of the registration certificates and certificates of incorporation of the local company (ies) | Must meet requirement | Must meet requirement | N/A | N/A | Form 11 |
| 6.2.13 | The local company in (ii) above shall submit particulars at least one Key Staff with at a degree in Engineering to be employed by the Local Company with an active role in the company’s site operations. | Must meet requirement | Must meet requirement | N/A | N/A | Form 11 |
| 6.2.14 | The Bidder shall submit details of previous construction experience gained by the Local company (ies) in road construction. | Must meet requirement | Must meet requirement | N/A | N/A | Form 9 and Certificates of Completion or Substantial Completion |
| 6.2.15 | The bidder shall submit copies of the sub-contract agreement with the local company/ies detailing the scope of works that are to be executed by the local company | Must meet requirement | Must meet requirement | N/A | N/A | Sub-contract agreements |

Bidder’s shall also provide information and documentation of:-

1. Authority to seek references from the bidder’s bankers; and
2. Proposals for subcontracting components of the works amounting to at least **30 percent** of the Contract Price.

|  |
| --- |
| **D. Financial Comparison Criteria** |
| **7. Costs to be included in the Bid Price** |
| * 1. The financial comparison shall be conducted in accordance with ITB Clause 37. The following costs shall be included in the bid price:      1. the total price given in the Activity Schedule/Bills of Quantities;      2. Day work.      3. the provision for contingencies in the Activity Schedule/ Bills of Quantities   2. The following costs shall be excluded from the bid price:      1. provisional sums;      2. the provision for contingencies in the Activity Schedule/ Bills of Quantities. |
| **8. Margin of Preference** |
| 8.1 For margin of preference for the purpose of bid comparison, the following procedures will apply: **N/A** |
|  |
|  |
|  |

|  |
| --- |
| 1. **Determination of Best Evaluated Bid or Bids**    1. Post qualification evaluation will be carried out on the lowest evaluated bidder as specified below: -   Legal Requirements – Due diligence shall be done to verify ownership of the company and its registration with appropriate body in the country of principal business.   * + 1. Technical Requirements–Due diligence shall be done to:        1. Verify and validate the bidder’s performance on previous indicated private and public contracts in the bidder’s submission.        2. Verify and validate current commitments and litigation record of the bidder.        3. The PDE shall carry out physical inspection of selected referenced projects to verify equipments, completion status, Human resource and any other key aspects.     2. Financial Requirements - Due diligence shall be done to verify and ascertain the bidder’s financial contracting capacity and bank commitment to provide a credit line to the bidder.   1. A bidder not meeting any of the above criteria shall be rejected. |
| 9.3 The bid with the lowest evaluated price, from among those which are eligible, compliant and substantially responsive and have passed the post-qualification shall be the best evaluated bid. If this Bidding Document includes more than one lot, the best evaluated bid shall be determined separately for each lot. |

|  |
| --- |
|  |
| **Additional Evaluation Criteria (If applicable)** |
| ***In addition to the evaluation criteria listed in Section 3, the following criteria may apply for the Procuring and Disposing Entities:***   1. **Multiple Contracts**   If permitted under additional criteria, this will be evaluated as follows: **N/A** |

**Section 4: Bidding Forms**

**Table of Forms**

[Bid Submission Sheet 64](#_TOC_250037)

[Code of Ethical Conduct in Business for Bidders and Providers 67](#_TOC_250036)

[Form of Bid Security ( Bank Guarantee) 69](#_TOC_250035)

[Form of Bid- Securing Declaration 71](#_TOC_250034)

[Technical Documentation 72](#_TOC_250033)

[Site Organization 74](#_TOC_250032)

[Method Statement 75](#_TOC_250031)

[Mobilization Schedule 76](#_TOC_250030)

[Construction Schedule 77](#_TOC_250029)

[Code of Conduct for Contractor’ s Personnel Form 78](#_TOC_250028)

[Forms for Key Personnel 82](#_TOC_250027)

[Form – 1: Proposed Personnel 83](#_TOC_250026)

[Form – 2: CV of Proposed Personnel 84](#_TOC_250025)

[Forms for Equipment 86](#_TOC_250024)

[FORM 3 86](#_TOC_250023)

[Qualification Forms 87](#_TOC_250022)

[Form 4 88](#_TOC_250021)

[Bidder Information Sheet 88](#_TOC_250020)

[Form 4 A 89](#_TOC_250019)

[Party to JV / Consortium / Association Information Sheet 89](#_TOC_250018)

[Form 5 90](#_TOC_250017)

[Historical Contract Non- Performance 90](#_TOC_250016)

[Form 5A 91](#_TOC_250015)

[Pending Litigation 91](#_TOC_250014)

[FORM 5 B 92](#_TOC_250013)

[Environmental, Social, Health and Safety Performance Declaration 92](#_TOC_250012)

[Form 6 95](#_TOC_250011)

[Current Contract Commitments / Works in Progress 95](#_TOC_250010)

[FORM 6 96](#_TOC_250009)

[Financial Situation 96](#_TOC_250008)

[Form 7 97](#_TOC_250007)

[Average Annual Turnover 97](#_TOC_250006)

[Form 8 98](#_TOC_250005)

[Financial Resources 98](#_TOC_250004)

[FORM 9 99](#_TOC_250003)

[Experience 99](#_TOC_250002)

[Form 10 100](#_TOC_250001)

[Specific Experience 100](#_TOC_250000)

*[This Bid Submission Sheet should be on the letterhead of the Bidder and should be signed by a person with the proper authority to sign documents that are binding on the Bidder]*

# Bid Submission Sheet

Date: *[insert date (as day, month and year) of Bid Submission]*

Procurement Reference No: *[insert Procurement Reference number]*

To: *[insert complete name of Procuring and Disposing Entity]*

We, the undersigned, declare that:

1. We have examined and have no reservations to the Bidding Document, including Addenda No.: *[insert the number and issue date of each Addenda]*;
2. We offer to execute in conformity with the Bidding Document and in accordance with the completion schedule specified in the Statement of Requirements and the terms and conditions of the Bidding Document, the following works *[insert a brief description of the Works]*;
3. The total price of our bid, excluding any discounts offered in item (d) below, is
4. The discounts offered and the methodologies for their application are:

Unconditional discounts. If our bid is accepted, the following discounts shall apply. *[Specify in detail each discount offered (eg amount/percentage) and the specific item of the Statement of Requirements to which it applies.]*

Methodology of application of the unconditional discounts. The unconditional discounts shall be applied using the following method: *[Specify precisely the method that shall be used to apply the discounts]*;

Cross discounts. If our bids for more than one lot are accepted, the following discounts shall apply. *[Specify precisely each discount offered (eg amount/percentage) and the conditions for its application.]*

Methodology of application of the cross discounts. The cross discounts shall be applied using the following method: *[Specify in detail the method that shall be used to apply the discounts]*;

1. Our bid shall be valid until the date specified in ITB Sub-Clause 19.1 and it shall remain binding upon us and may be accepted at any time before that date;
2. If our bid is accepted, we commit to obtain a Performance Security in accordance with the Bidding Document in the amount of *[insert amount in words and figures of the Performance Security]* for the due performance of the Contract;
3. We, including any subcontractors for any part of the contract resulting from this procurement process, are eligible to participate in public procurement in accordance with ITB Clause 4.1;
4. We, including any subcontractors for any part of the contract, have nationals from eligible countries *[insert the nationality of the Bidder, including that of all parties that comprise the Bidder, if the Bidder is a joint venture, consortium or association, and the nationality of each subcontractor]*;
5. We are eligible for a Margin of Preference in accordance with ITB Clause 38 and are eligible for inclusion in *[insert Group A or Group B as appropriate]* and enclose documentary evidence of our eligibility;

*[or]*

We are not eligible for a Margin of Preference in accordance with ITB Clause 38;

1. We have signed and undertake to abide by the Code of Ethical Conduct for Bidders and Providers during the procurement process and the execution of any resulting contract;
2. We accept the appointment of *[name proposed in Bid Data Sheet]* as the Adjudicator.

*[or]*

We do not accept the appointment of *[name proposed in Bidding Data]* as the Adjudicator, and propose instead that *[name]* be appointed as Adjudicator, whose daily fees and biographical data are attached.

1. We are not participating, as bidders, in more than one bid in this bidding process, other than alternative bids in accordance with the Bidding Document;
2. We, including any subcontractors, do not have any conflict of interest as stated in ITB

4.4 and are not associated, nor have been associated in the past, directly or indirectly, with the consultant or any other entity that has prepared the design, specifications, and other documents for the Project or that is being proposed as Project Manager for the Contract;

1. We, including any subcontractors for any part of the contract, have not been suspended by the Public Procurement and Disposal of Public Assets Authority in Uganda from participating in public procurement;
2. We understand that you are not bound to accept the lowest bid or any other bid that you may receive.

Signed: *[signature of person whose name is shown below]*

Name: *[insert complete name of person signing the bid]*

In the capacity of *[insert designation of person signing the bid]*

Duly authorised to sign the bid for and on behalf of: *[insert complete name of Bidder/Joint Venture]*

Dated on day of , *[insert date of signing]*

**Code of Ethical Conduct in Business for Bidders and Providers**

(Under Section 93 (2) of the Public Procurement and Disposal of Public Assets Act, 2003)

#### Ethical Principles

Bidders and providers shall at all times-

* 1. Maintain integrity and independence in their professional judgement and conduct;
  2. Comply with both the letter and the spirit of-
     1. The laws of Uganda; and
     2. Any executed contract.
  3. Avoid associations with businesses and organisations which are in conflict with this code.

#### Standards

Bidders and providers shall-

* 1. Strive to provide works, services and supplies of high quality and accept full responsibility for all works, services or supplies provided;
  2. Comply with the professional standards of their industry or of any professional body of which they are members.

#### Conflict of Interest

Bidders and providers shall not accept contracts which would constitute a conflict of interest with, any prior or current contract with any procuring and disposing entity. Bidders and providers shall disclose to all concerned parties those conflicts of interest that cannot reasonably be avoided or escaped.

#### Confidentiality and Accuracy of Information

* 1. Information given by bidders and providers in the course of procurement processes or the performance of contracts shall be true, fair and not designed to mislead.
  2. Providers shall respect the confidentiality of information received in the course of performance of a contract and shall not use such information for personal gain.

#### Gifts and Hospitality

Bidders and providers shall not offer gifts or hospitality directly or indirectly, to staff of a Procuring and Disposing Entity that might be viewed by others as having an influence on a procurement decision of the Entity.

#### Inducements

* 1. Bidders and providers shall not offer or give anything of value to influence the action of a public official in the procurement process or in contract execution.
  2. Bidders and providers shall not ask a public official to do anything which is inconsistent with the Act, Regulations, Guidelines or the Code of Ethical Conduct in Business.

#### Fraudulent Practices

Bidders and providers shall not-

* 1. Collude with other businesses and organisations with the intention of depriving a Procuring and Disposing Entity of the benefits of free and open competition;
  2. Enter into business arrangements that might prevent the effective operation of fair competition;
  3. Engage in deceptive financial practices, such as bribery, double billing or other improper financial practices;
  4. Misrepresent facts in order to influence a procurement process or the execution of a contract to the detriment of the Procuring and Disposing Entity; or utter false documents;
  5. Unlawfully obtain information relating to a procurement process in order to influence the process or execution of a contract to the detriment of the PDE; Withholding information from the PDE during contract execution to the detriment of the PDE.

I .................................................................. agree to comply with the above code of ethical conduct in business.

|  |  |  |
| --- | --- | --- |
|  |  |  |
| **AUTHORISED SIGNATORY** |  | **NAME OF BIDDER2** |

2 *If the bidder is a JV, Consortium or Association, state the name of the JV, Consortium or Association*

*[This Bid Security should be on the letterhead of the issuing Financial Institution and should be signed by a person with the proper authority to sign the Bid Security. It should be included by the Bidder in its bid, if so indicated in the BDS]*

# Form of Bid Security (Bank Guarantee)

Date: *[insert date (as day, month and year) of Bid Submission]*

Procurement Reference No.: *[insert Procurement Reference number]*

To: *[insert complete name of Procuring and Disposing Entity]*

Whereas, *[insert complete name of Bidder/Joint Venture/Consortium/Association]* (hereinafter called “the Bidder”) has submitted its bid dated *[insert date (as day, month and year) of bid submission]* for Procurement Reference number *[insert Procurement Reference number]* for the construction of *[insert brief description of the Works]*.

KNOW ALL PEOPLE by these presents that We *[insert complete name of institution issuing the Bid Security]* of *[insert city of domicile and country of nationality]* having our registered office at *[insert full address of the issuing institution]* (hereinafter called “the Guarantor”) are bound unto *[insert complete name of Procuring and Disposing Entity]* (hereinafter called “the Procuring and Disposing Entity”) in the sum of *[specify in words and figures the amount and currency of the Bid Security]* for which the Guarantor binds itself, its successors or assignees to make payment to the Procuring and Disposing Entity.

Sealed with the Common Seal of the said Guarantor this *[insert day in numbers]* day of *[insert month]*, *[insert year]*.

THE CONDITIONS of this obligation are:

1. If the bidder withdraws its bid during the period of bid validity specified in the bid submission sheet or as provided in ITB Sub-Clause 19.3 or refuses to accept the correction of its bid price pursuant to ITB Clause 32.5; or
2. If the bidder having been notified of the acceptance of its bid by the Procuring and Disposing Entity during the period of bid validity fails or refuses to:
   1. Sign the Contract in accordance with the ITB Clause 44.2, if required; or
   2. Furnish the Performance Security, in accordance with the ITB Clause 46.2, and, if required, the Environmental and Social (ES) Performance Security, in accordance with the Instructions to Bidders (“ITB”).

We undertake to pay to the Procuring and Disposing Entity up to the above amount upon receipt of its first written demand, without the Procuring and Disposing Entity’s having to substantiate its demand, provided that in its demand the Procuring and Disposing Entity states that the amount claimed by it is due to it, owing to the occurrence of one or more of the above conditions, specifying the occurred conditions.

This security shall remain in force up to and including *[insert date, (day, month and year) in accordance with ITB Clause 19.1 or 19.3]* and any demand in respect thereof should be received by the Guarantor no later than the above date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758, except that sub – article 20 (a) is hereby excluded.

Signed: *[insert signature of person whose name is shown below]*

Name: *[insert complete name of person signing the Bid Security]*

In the capacity of *[insert designation of person signing the Bid Security]*

Duly authorised to sign the Bid Security for and on behalf of: *[insert complete name of Financial Institution]*

Dated on day of (month), (year) *[insert date of signing]*

[Use Bidder’s Letterhead]

[Name of Bidder] [Physical Address of Bidder]

# Form of Bid-Securing Declaration

Date: *[insert date (as day, month and year)]*

Subject of procurement and Ref number.: *[insert reference number of procurement process]*

To: *[insert complete name of Procuring and Disposing Entity]*

I/We\*, the undersigned, declare as follows:

I/We\* understand that, according to the conditions of the Bidding Document, bids must be supported by a Bid Securing Declaration valid until the date indicated in the Bid Data Sheet (BDS).

I/We\* accept that I/we\* may be suspended by the Authority from being eligible for bidding in any public procurement or disposal process if we are in breach of our obligations under the conditions in the bidding document, because we:

1. Have withdrawn our bid during the period of bid validity specified by us in the bid Submission Sheet or as provided in ITB Sub-Clause 19.3 or have refused to accept the correction of our bid price pursuant to ITB Clause 32.5; or
2. Having been notified of the acceptance of our bid by the PDE during the period of bid validity, (i) fail or refuse to sign the Contract, if required, or (ii) fail or refuse to furnish the Performance Security, in accordance with the ITB 46.2 or and, if required, the Environmental and Social (ES) Performance Security.

I/We\* understand this Bid Securing Declaration shall cease to be valid if I am/we are\* not the successful bidder, upon the earlier of:

1. The expiry of the notice of best evaluated bidder without any pending administrative review application; or
2. Twenty eight days after the expiration of the validity of my/our\* bid.

Signed: *[insert signature of person whose name is shown below]* In the capacity of *[insert designation of person signing the Bid Securing Declaration]*

Name: *[insert complete name of person signing the Bid Securing Declaration]*

Duly authorized to sign the bid for and on behalf of: *[insert complete name of Bidder]*

Dated on day of (month), (year) *[insert date of signing]*

Corporate Seal (where appropriate)

*[Note: In case of a Joint Venture, Consortium or Association the Bid Securing Declaration must be in the name of all partners that submit the bid and signed by the representative duly authorized by the partners.]*

##### \*Please delete as appropriate

# Technical Documentation

* 1. Site Organization
  2. Method Statement
  3. Mobilization Schedule
  4. Construction Schedule
  5. Environmental and Social Management Strategies and Implementation Plans
  6. Code of Conduct for Contractor’s Personnel
  7. Equipment
  8. Key Personnel Schedule

**Site Organization**

**Provide a detailed description/illustration of the proposed site organization in terms of personnel, offices, materials storage, workshops etc. indicating all the key departments involved in the execution of works, their responsibilities and chains of command to ensure smooth implementation of the project. The site organization should also show how the contractor's site office, the Consultant and the Employer offices shall be coordinated as well as provide linkage between the project site and the bidder's Head Office to ensure efficient communication and faster decision making**

**Method Statement**

***Provide a detailed description of the proposed method statement to execute the works covering all the key activities expected in project implementation and how they are to be executed. Emphasis should also be put on quality assurance and compliance to environment and social safeguards of the project***

**Mobilization Schedule**

[In this section, the bidder is required to make a detailed schedule of the mobilization and demobilization of all the necessary manpower and equipment. This schedule should be produced in at least MS Project 2016; duration allocated to each task, indicating milestones, expected shipping time for oversees plant, equipment and materials and travel in and out of the country for the expected expatriate staff. A softcopy of this schedule should be attached in CD format to the bids].

In accordance with the Particular Conditions, the Contractor shall not carry out mobilization to Site unless the Engineer gives consent that appropriate measures are in place to address environmental and social risks and impacts, which as a minimum shall include applying the Management Strategies and Implementation Plans (MSIPs) and Code of Conduct for Contractor’s Personnel, submitted as part of the Bid and agreed as part of the Contract.

**Construction Schedule**

[In this section, the bidder is required to make a **detailed schedule of the civil works construction phase**. This schedule should be produced in at least **MS Project 2016** as a minimum; well-resourced with the expected manpower and equipment expected to undertake each particular task, duration allocated to each task and indicating milestones. A softcopy of this schedule should be attached in CD format to the bids].

Provide a detailed description/illustration of the proposed construction schedule. The construction schedule should conform to the proposed method statement and comply with the expected delivery schedule. The Construction schedule should demonstrate a logical sequence of the planned activities in each of the Entities

The construction schedule shall include the following key milestones:

* No-objection to the Contractor’s MSIPs, which collectively form the C-ESMP, in accordance with the Particular Conditions – Special provisions Sub-Clause 4.1.
* Constitution of the DAAB

**Code of Conduct for Contractor’s Personnel Form**

|  |
| --- |
| **Note to the Bidder**:  **The minimum content of the Code of Conduct Form as set out by the Employer shall not be substantially modified**. However, the Bidder may add requirements as appropriate, including to take into account Contract-specific issues/risks.  The Bidder shall initial and submit the Code of Conduct Form as part of its bid. |

**CODE OF CONDUCT FOR CONTRACTOR’S PERSONNEL**

We , [*enter name of Bidder*], undertake that once we are awarded the

contract for [*enter description of the works*] to be carried out at [*enter*

*the site and other locations where the works will be carried out*] shall implement measures to address environmental and social risks related to the works, including the risks of sexual exploitation and assault and gender-based violence.

This Code of Conduct is part of our measures to deal with environmental and social risks related to the works. It applies to all our staff, labourers and other employees at the Works Site or other places where the works would be carried out. It also applies to the personnel of each subcontractor and any other personnel assisting us in the execution of the Works. All such persons are referred to as “**Contractor’s Personnel”** and are subject to this Code of Conduct.

This Code of Conduct identifies the behavior that we require from all Contractor’s Personnel.

Our workplace is an environment where unsafe, offensive, abusive or violent behaviour will not be tolerated and where all persons should feel comfortable raising issues or concerns without fear of retaliation.

We shall take into consideration the issues (*including but not limited to labour influx, spread of communicable diseases, sexual harassment, illicit behaviour, crime and maintaining a safe environment*), impacts and mitigation measures identified in project reports e.g. ESIA/ESMP, any particular GBV/SEA requirements, consent/permit conditions, required standards including World Bank Group EHS Guidelines, relevant international conventions, standards or treaties; national, legal and regulatory requirements and standards and all relevant standards e.g. Workers’ Accommodation.

Name of Contractor: [insert name]

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: (day month year): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

#### REQUIRED CONDUCT

Contractor’s Personnel shall:

1. Carry out his/her duties competently and diligently;
2. Comply with this Code of Conduct and all applicable laws, regulations and other requirements, including requirements to protect the health, safety and well-being of other Contractor’s Personnel and any other person;
3. Maintain a safe working environment including by:
   1. Ensuring that workplaces, machinery, equipment and processes under each person’s control are safe and without risk to health;
   2. Wearing required personal protective equipment;
   3. Using appropriate measures relating to chemical, physical and biological substances and agents; and
   4. Following applicable emergency operating procedures.
4. Report work situations that he/she believes are not safe or healthy and remove himself/herself from a work situation which he/she reasonably believes presents an imminent and serious danger to his/her life or health;
5. Treat other people with respect, and not discriminate against specific groups such as women, people with disabilities, migrant workers or children;
6. Not engage in use of illegal substances;
7. Not engage in any form of sexual harassment including unwelcome sexual advances, requests for sexual favors, and other unwanted verbal or physical conduct of a sexual nature with other Contractor’s or Employer’s Personnel;
8. Not engage in Sexual Exploitation, which means any actual or attempted abuse of position of vulnerability, differential power or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another.
9. Not engage in Sexual Assault, which means sexual activity with another person who does not consent. It is a violation of bodily integrity and sexual autonomy and is broader than narrower conceptions of “rape”, especially because (a) it may be committed by other means than force or violence, and (b) it does not necessarily entail penetration.
10. Not engage in any form of sexual activity with individuals under the age of 18, except in case of pre-existing marriage;
11. Complete relevant training courses that will be provided related to the environmental and social aspects of the contract, including on health and safety matters, and Sexual Exploitation and Assault (SEA);
12. Report violations of this Code of Conduct; and
13. Not retaliate against any person who reports violations of this Code of Conduct, whether to us or the Employer, or who makes use of the [Project Grievance [Redress] Mechanism].

#### RAISING CONCERNS

If any person observes behavior that he/she believes may represent a violation of this Code of Conduct, or that otherwise concerns him/her, he/she should raise the issue promptly. This can be done in either of the following ways:

1. Contact [*enter name of the Contractor’s Social Expert with relevant experience in handling gender-based violence, or if such person is not required under the Contract, another individual designated by the Contractor to handle these matters*] in writing at this address …………………………[ ] or by telephone at [ ] or in person

at [ ]; or

1. Call […………………… ] to reach the Contractor’s hotline *(if any)* and leave a message.

The person’s identity will be kept confidential, unless reporting of allegations is mandated by the law. Anonymous complaints or allegations may also be submitted and will be given all due and appropriate consideration. We take seriously all reports of possible misconduct and will investigate and take appropriate action. We will provide warm referrals to service providers that may help support the person who experienced the alleged incident, as appropriate.

There will be no retaliation against any person who raises a concern in good faith about any behavior prohibited by this Code of Conduct. Such retaliation would be a violation of this Code of Conduct.

#### CONSEQUENCES OF VIOLATING THE CODE OF CONDUCT

Any violation of this Code of Conduct by Contractor’s Personnel may result in serious consequences, up to and including termination and possible referral to legal authorities.

#### FOR CONTRACTOR’S PERSONNEL:

I have received a copy of this Code of Conduct written in a language that I comprehend. I understand that if I have any questions about this Code of Conduct, I can contact

…………………………….. [*enter name of Contractor’s contact person with relevant experience in handling gender-based violence*] requesting an explanation.

Name of Contractor’s Personnel: [insert name]

Signature:

Date: (day month year):

Countersignature of authorized representative of the Contractor:

Signature: Date: (day month year):

**Environmental and Social Management Plan**

1. *The Bidder shall submit a comprehensive and concise* ***Environment Social Health and Safety Management Strategies and Implementation Plans (ESHS-MSIP)*** *as required by ITB 15.1 (i) of the BDS. These strategies and plans shall describe in detail the actions, materials, equipment and management processes etc. that will be implemented by the Contractor, and its subcontractors. In developing these strategies and plans, the Bidder shall have regard to the ESHS provisions of the contract including those as may be more fully described in the Statement of Requirements in Section 6*
2. *In addition, the Bidder shall submit an outline of the* ***Code of Conduct (ESHS)*** *in accordance with ITB 15.1(i) indicating how it will be implemented. This will include: what training will be provided to employees, how the Code of Conduct (ESHS) will be monitored and how the Contractor proposes to deal with any breaches and intended grievance redress mechanisms.*

# Forms for Key Personnel

**Form – 1: Proposed Personnel**

Bidders should provide the names of suitably qualified personnel to meet the specified requirements for each of the positions listed in Section 3: Evaluation Methodology and Criteria. The data on their experience should be supplied using the Form below for each candidate.

|  |  |
| --- | --- |
| 1. | Title of position |
| Name |
|  | Duration of commitment for this position |
| 2. | Title of position |
| Name |
|  | Duration of commitment for this position |
| 3. | Title of position |
| Name |
|  | Duration of commitment for this position |
| 4. | Title of position: |
| Name |
| Duration of commitment for this position |
| 5. | Title of position: Environmental Officer |
| Name |
| Duration of commitment for this position |
| 6. | Title of position: Social Development Officer |
| Name |
| Duration of commitment for this position |
| etc. | Title of position |
| Name |
| Duration of commitment for this position |

**Form – 2: CV of Proposed Personnel**

The bidder shall provide all the information requested below.

|  |  |  |
| --- | --- | --- |
| **Position** | | |
| **Personnel Information** | Name | Date of birth |
| Professional qualifications | |
| Academic qualifications | |
| **Present Employment** | Name of Employer | |
| Address of Employer | |
| Telephone | Contact (manager / personnel officer) |
| Fax | E-mail |
| Job title | Years with present Employer |

Summarize professional experience in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **From** | **To** | **Project** | **Role** | **Duration in**  **Involvement** | **Relevance**  **Experience** |
| *[Date, Month and Year]* | *[Date, Month and Year]* | *[main project details]* | *[role and responsibilities on the project]* | *[time in role*  *i.e. Months and Years]* | *[describe the experience relevant to*  *this position]* |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

**Declaration**

I, the undersigned *[insert name of “Key Personnel”]*, certify that to the best of my knowledge and belief, the information in reference to my data contained in the Forms for Key Personnel correctly describes myself, my qualifications and my experience.

I confirm that I am available as certified in the following table and throughout the expected time schedule for this position as provided in the bid:

|  |  |
| --- | --- |
| **Commitment** | **Details** |
| **Commitment to duration of contract:** | *[insert period (start and end dates) for which this*  *Contractor’s Key Personnel is available to work on this contract]* |

I understand that any misrepresentation or omission in this Form may:

1. Be taken into consideration during bid evaluation;
2. Result in my disqualification from participating in the procurement process.

**Name of Key Personnel: [*insert name*]**

Signature:

Date: (day, month, year):

#### Countersignature of authorized representative of the Bidder:

Signature: Date: (day month year):

# Forms for Equipment

The bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section 3: Evaluation Methodology and Criteria. A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the bidder. The bidder shall provide all the information requested below, to the extent possible:

**FORM 3**

|  |  |  |
| --- | --- | --- |
| Type of Equipment | | |
| Equipment Information | Name of manufacturer | Model and power rating |
| Capacity | Year of manufacture |
| Current Status | Current location | |
| Details of current commitments | |
| Source | Indicate source of the equipment   * Owned * Rented * Leased * Specially manufactured   (Attach evidence of ownership, lease or hire in the form of registration books, agreements or memoranda or purchaser order) | |




The following information shall be provided only for equipment not owned by the Bidder.

#### FORM 3A

|  |  |  |
| --- | --- | --- |
| Owner | Name of owner | |
| Address of owner | |
| Telephone | Contact name and title |
| Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project. (Attach evidence of lease or hire in the form of registration books, agreements  or memoranda or purchaser order) | |
|  |  | |
|  |  | |

# Qualification Forms

To establish its qualifications to perform the contract in accordance with Section 3: Evaluation Methodology and Criteria. The Bidder shall provide the information requested in the corresponding Information Sheets included hereunder:



**Form 4**

# Bidder Information Sheet

Date: Procurement Reference Number:

|  |
| --- |
| 1. Bidder’s Name1: |
| 2. In case of JV / Consortium / Association, state name of each party in Form 4A |
| 3. Bidder’s Country of Registration / Incorporation2: |
| 4. Bidder’s Year of Registration / Incorporation3: |
| 5. Bidder’s Address in Country of Registration / Incorporation4: |
| 6. Bidder’s Authorized Representative Information Name:  Address:  Telephone/Fax numbers: Email Address: |
| 7. Attached are copies of original documents of:  Certificate of Incorporation or Registration of firm named in 1, above.  In case of JV / Consortium / Association, the JV / Consortium / Association Agreement In case of government owned entity from the Procuring and Disposing Entity’s country,  documents establishing legal and financial autonomy and compliance with the principles of  commercial law. |

1In case of JV / Consortium / Association, Fill in Form 4A 2In case of JV / Consortium / Association, Fill in Form 4A 3In case of JV / Consortium / Association, Fill in Form 4A 4In case of JV / Consortium / Association, Fill in Form 4A

**Form 4 A**

# Party to JV / Consortium / Association Information Sheet

Date: Procurement Reference Number:

|  |
| --- |
| 1.`Legal Name of party to JV / Consortium / Association: |
| 2. Country of Registration of party to JV / Consortium / Association: |
| 3. Year of Registration of party to JV / Consortium / Association: |
| 4. Legal Address in Country of Registration for party to JV / Consortium / Association : |
| 6. Authorized Representative Information for party to JV / Consortium / Association Name:  Address:  Telephone/Fax numbers: Email Address: |
| 1. Attached are copies of original documents of:    * Certificate of Incorporation or Registration of firm named in 1, above.    * In case of government owned entity from the Purchaser’s country, documents establishing legal and financial autonomy and compliance with the principles of commercial law. |

**Form 5**

# Historical Contract Non-Performance

Bidder’s Name: Date:

JV/ Consortium / Association Partner Names: Procurement Reference No.:

|  |  |  |  |
| --- | --- | --- | --- |
| Non-Performing Contracts in accordance with the Technical Criteria | | | |
| * Contract non-performance did not occur during the stipulated period, in accordance with Sub-Factor 6.2.1 of Section III. * Contract non-performance during the stipulated period, in accordance with Sub-Factor   6.2.1 of Section III. | | | |
| Year | Outcome as Percent of  Total Assets | Contract Identification | Total Contract Amount |
|  |  | Contract Identification: Name of Employer: Address of Employer:  Matter in dispute: |  |

**Form 5A**

# Pending Litigation

|  |  |  |  |
| --- | --- | --- | --- |
| Pending Litigation, in accordance with Section III | | | |
| * No pending litigation in accordance with Sub-Factor 6.2.2 of Section III * Pending litigation in accordance with Sub-Factor 6.2.2 of Section III, as indicated below | | | |
| **Year** | **Outcome as Percent of Total Assets** | **Contract Identification** | **Total Contract Amount** |
|  |  | Contract Identification: Name of Employer:  Address of Employer:  Matter in dispute: |  |
|  |  | Contract Identification: Name of Employer:  Address of Employer:  Matter in dispute: |  |
|  |  | Contract Identification: Name of Employer:  Address of Employer:  Matter in dispute: |  |

**FORM 5 B**

# Environmental, Social, Health and Safety Performance Declaration

|  |  |  |  |
| --- | --- | --- | --- |
| **Environmental, Social, Health, and Safety Performance Declaration**  in accordance with Section III, Qualification Criteria, and Requirements | | | |
| * **No suspension or termination of contract**: An employer has not suspended or terminated a contract and/or called the performance security for a contract for reasons related to Environmental, Social, Health, or Safety (ESHS) performance since the date specified in Section III, Qualification Criteria, and Requirements, Sub-Factor 6.2.3. * **Declaration of suspension or termination of contract**: The following contract(s) has/have been suspended or terminated and/or Performance Security called by an employer(s) for reasons related to Environmental, Social, Health, or Safety (ESHS) performance since the date specified in Section III, Qualification Criteria, and Requirements, Sub-Factor 6.2.3. Details are described below: | | | |
| **Year** | **Suspended or terminated portion of contract** | **Contract Identification** | **Total Contract Amount (value, currency, exchange rate and UGX equivalent)** |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for suspension or termination: *[indicate main reason(s)]* | *[insert amount]* |
| *[insert year]* | *[insert amount and percentage]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for suspension or termination: *[indicate main reason(s)]* | *[insert amount]* |
| *…* | *…* | *[list all applicable contracts]* | *…* |
|  | | | |

|  |  |  |
| --- | --- | --- |
| **Performance Security called by an employer(s) for reasons related to ESHS Performance** | | |
| **Year** | **Contract Identification** | **Total Contract Amount (current value, currency, exchange rate and UGX equivalent)** |
| *[insert year]* | Contract Identification: *[indicate complete contract name/ number, and any other identification]*  Name of Employer: *[insert full name]*  Address of Employer: *[insert street/city/country]*  Reason(s) for calling of performance security: *[indicate main reason(s)]* | *[insert amount]* |
|  |  |  |

**Form 6**

# Current Contract Commitments / Works in Progress

*[The following table shall be filled in for the Bidder, each member of a Joint Venture / Consortium*

*/Association]*

Bidder’s Name: *[insert full name]*

Date: *[insert day, month, year]*

Joint Venture / Consortium / Association Member’s Name: *[insert full name]*

Proc. Reference No: *[insert Reference Number]*

*[*Bidders and each partner to a JV/ Consortium / Association should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued. *]*

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of contract | Employer, contact address/tel/fax | Value of outstanding work | Estimated completion date | Average monthly invoicing over  last six months (UGX /month) |
| 1. |  |  |  |  |
| 2. |  |  |  |  |
| 3. |  |  |  |  |
| 4. |  |  |  |  |
| 5. |  |  |  |  |
| etc. |  |  |  |  |

**FORM 6**

# Financial Situation

#### Historical Financial Performance

Bidder’s Name: Date:

JV/ Consortium / Association Partner Legal Name: Procurement Reference No.:

To be completed by the Bidder and, if JV/ Consortium / Association, by each partner

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial information in UGX  equivalent | Historic information for previous ( ) years (UGX equivalent in 000s) | | | | | | |
|  | Year 1 | Year 2 | Year 3 | Year … | Year n | Avg. | Avg.  Ratio |
| Information from Balance Sheet | | | | | | | |
| Total Assets (TA) |  |  |  |  |  |  |  |
| Total  Liabilities (TL) |  |  |  |  |  |  |
| Net Worth (NW) |  |  |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |  |  |
| Current Liabilities  (CL) |  |  |  |  |  |  |
| Information from Income Statement | | | | | | | |
| Total Revenue (TR) |  |  |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |  |
|  | | | | | | | |
|  | | | | | | | |
|  | | | | | | | |

* Attached are copies of financial statements (balance sheets, including all related notes, and income statements) for the years required above complying with the following conditions:
  + Must reflect the financial situation of the Bidder or partner to a JV, and not sister or parent companies
  + Historic financial statements must be audited by a certified accountant
  + Historic financial statements must be complete, including all notes to the financial statements
  + Historic financial statements must correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted)

**Form 7**

# Average Annual Turnover

Bidder’s Name: Date:

JV/ Consortium / Association Partner Name: Procurement Reference No.:

|  |  |  |
| --- | --- | --- |
| Annual turnover data (construction only) | | |
| Year | Amount and Currency | UGX equivalent |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
| \*Average Annual Construction Turnover |  |  |

\*Average annual turnover calculated as total certified payments received for work in progress or completed over the number of years specified in Section III, Sub-Factor 6.2.5, divided by that same number of years.

**Form 8**

# Financial Resources

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as indicated in Section 3: Evaluation Methodology and Criteria.

|  |  |
| --- | --- |
| Source of financing | Amount (UGX equivalent) |
| 1. |  |
| 2. |  |
| 3. |  |
| 4. |  |

**FORM 9**

**Experience**

**General Experience**

Bidder’s Name: Date:

JV/ Consortium / Association Partner Name: Procurement Reference No.:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Starting Month /**  **Year** | **Ending Month /**  **Year** | **Years\*** | **Contract Identification** | **Role of Bidder** |
|  |  |  | Contract name:  Brief Description of the Works performed by the Bidder:  Name of Employer: Address: |  |
|  |  |  | Contract name:  Brief Description of the Works performed by the Bidder:  Name of Employer: Address: |  |
|  |  |  | Contract name:  Brief Description of the Works performed by the Bidder:  Name of Employer: Address: |  |
|  |  |  | Contract name:  Brief Description of the Works performed by the Bidder:  Name of Employer: Address: |  |
|  |  |  | Contract name:  Brief Description of the Works performed by the Bidder:  Name of Employer: Address: |  |
|  |  |  | Contract name:  Brief Description of the Works performed by the Bidder:  Name of Employer: Address: |  |

\*List calendar year for years with contracts with at least nine (9) months activity per year starting with the earliest year

**Form 10**

# Specific Experience

Bidder’s Name: Date:

JV/ Consortium / Association Partner Name: Procurement Reference No.:

|  |  |  |  |
| --- | --- | --- | --- |
| **Similar Contract Number: *[insert specific number]* of *[insert total number of contracts* required.** | **Information** | | |
| Contract Identification |  | | |
| Award date Completion date |  | | |
|  |  | | |
| Role in Contract |   Contractor |  Management Contractor |   Subcontractor |
| Total contract amount |  | | UGX |
| If partner in a JV or subcontractor, specify participation of total contract amount | % |  | UGX |
| Employer’s Name: |  | | |
| Address:  Telephone/fax number: E-mail: |  | | |

### Form 10 A (cont.)

**Specific Experience (cont.)**

Bidder’s Name: Date:

JV/ Consortium / Association Partner Name: Procurement Reference No.:

|  |  |
| --- | --- |
| **Similar Contract No. *[insert specific number]* of *[insert total number of contracts]* required** | **Information** |
| Description of the similarity in accordance with Sub-Factor 6.2.8a) of Section 3: Evaluation Methodology and Criteria.: |  |
| Amount |  |
| Physical size |  |
| Complexity |  |
| Methods/Technology |  |
| Physical Production Rate |  |

**Form 10 A (b)**

**Specific Experience in in Managing Environmental and Social Safeguards Activities**

Bidder’s Name: Date:

JV/ Consortium / Association Partner Name: Procurement Reference No.:

|  |  |  |  |
| --- | --- | --- | --- |
|  | Information | | |
| Contract Identification |  | | |
| Award date Completion date |  | | |
| Role in Contract |   Contractor |  Management Contractor |   Subcontractor |
| Total contract amount |  | |  |
| If partner in a JV / Consortium / Association, specify participation of total contract amount | % |  |  |
| Employer’s Name: |  | | |
| Address:  Telephone/fax number: E-mail: |  | | |
| Description of the key activities in accordance with Sub-Factor 6.2.10 of Section 3: |  | | |

**Form 10 (b) (cont.)**

**Specific Experience in Managing Environmental and Social Safeguards Activities (cont.)**

Bidder’s Name: Date:

JV/ Consortium / Association Partner Name: Procurement Reference No.:

|  |  |
| --- | --- |
|  | Information |
| Description of the key activities in accordance with Sub-Factor 6.2.10 b) of Section III: |  |
|  |  |
|  |  |
|  |  |
|  |  |
|  |  |

We, the undersigned, declare that the information contained in and attached to these forms is true and accurate as of the date of bid submission:

Signed: *[signature of person whose name and capacity are shown below]*

Name: *[insert complete name of authorized person signing the Qualification Form]*

Duly authorised to sign the Qualification Form for and on behalf of: *[insert complete name of Bidder or name of Joint Venture/ Consortium / Association]*

Dated on day of , *[insert day / month / year of signing]*

**Form 11**

**LOCAL CONTENT COMPLIANCE**

*Bidders should provide information on their agreements with a Local Company(ies) to sub-contract* ***at least 30%*** *of the value of the works.*

*Part A: Details of Local Company (ies) and Works sub-contracted*

|  |  |  |  |
| --- | --- | --- | --- |
| **Name of Local Company** | **Authorised Representative** | **Works to be subcontracted** | **Estimated Percentage of the Value of works (%)** |
| 1….. |  | 1. ….. 2. …. |  |
| 2…… |  |  |  |

*Part B: Previous experience of Local Company (ies) in road construction*

|  |  |  |  |
| --- | --- | --- | --- |
| **Starting**  **Month**  **Year** | **Ending**  **Month**  **Year** | **Contract Identification and Name**  **Name and Address of Employer (Include Telephone Number and Email address)**  **Brief Description of works done by the Local Company** | **Role of Local Company** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

|  |
| --- |
| **Attached are copies of the following original documents**   * Articles of incorporation or constitution of the Local company (ies) showing full ownership by Ugandan(s) * Certificate showing registration of the Local Company (ies) with PPDA list of providers * CV and registration certificates of at least one Professional/ registered Engineer employed by the Local Company with an active role in the company’s site operations * Letter of intent to subcontract |

**Section 5: Eligible Countries**

**Procurement Reference Number: KCCA-GKMA/WRKS/2025-2026/00008/1**

All countries are eligible except countries subject to the following provisions. A country shall not be eligible if:

1. As a matter of law or official regulation, the Government of Uganda prohibits commercial relations with that country, provided that the Government of Uganda is satisfied that such exclusion does not preclude effective competition for the provision of supplies or related services required; or
2. By an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the Government of Uganda prohibits any import of Supplies from that country or any payments to persons or entities in that country.

**PART 2 - Statement of Requirements** **Section 6: Statement of Requirements**

**Contents**

[**Scope of Works 107**](#_bookmark60)

[**Technical Specifications 117**](#_bookmark61)

[**Environmental, Social, Health and Safety Requirements 118**](#_bookmark62)

[**Drawings 130**](#_bookmark63)

[**Activity Schedule/ Bills of Quantities 131**](#_bookmark64)

[**Activity Schedule 132**](#_bookmark65)

[**Bill of Quantities 133**](#_bookmark66)

[**Completion Schedule 134**](#_bookmark67)


[**Supplementary Information 135**](#_bookmark68)

**Scope of Works**

**Lot 1:** Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km)

* 1. **OLD KIREKA ROAD**


Old Kireka Road is a paved road located in the Nakawa D division of Kampala Capital City area, and in Kira Municipality. It starts at Old Portbell Road (bugolobi) and ends at Bweyoregere Joka’s Hotel near Nambole stadium The total length is 6.2Km. The Kireka link road has a 0.4km link to Kireka trading centre. This is called Kireka Link. The road is generally in a poor condition characterized by dust, cracks, eroded road surface with multiple potholes and eroded walkways. The road has open drains on either side. It is located in a predominantly commercial area with an average carriageway width of 8.5m and a thin wearing course. There have been some recent renovations (pothole patching) on the main road. Figure 1 below shows the location of Old Kireka Road.




**Figure 1: Location of Old Kireka Road**

**Typical Road Cross-sections**

A typical cross-section that caters for all needs of the users of the road has been proposed. The typical cross-sections proposed have also been influenced by available right of way along the project road. The typical cross-sections proposed are presented in Figure 2 below.







**Figure 2: Typical cross sections along Old Kireka Road**

* 1. **LANCE ROAD**

Lance Road is a gavel/ unpaved road located in the Nakawa division of Kampala Capital City area, with 0.9km length starting at Butabika Road and ending in Kasokoso.

The roads have an average carriageway width of 5.2m and traverse a flat to rolling landscape through a combination of residential areas, businesses plots. Most of the road sections lack well-defined shoulders and walkways, which poses accident risks to motorists and pedestrians. Horizontal and vertical curves dot its alignment, some acceptable but many of which need significant improvement to ensure optimal sight distances and overall road safety.


The roads are characterized by non-existent drainage infrastructure in most of the road sections.



**Figure 3: Location of Lance Road**

**Typical Road Cross-sections**

A typical cross-section that caters for all needs of the users of the road has been proposed. The typical cross-sections proposed have also been influenced by available right of way along the project road. The typical cross-sections proposed are presented in Figure 4 below.



**Figure 4: Typical cross section Lance Road**

1. **Public Utilities Infrastructure Relocation**

There are three categories of public utility services infrastructure that may require relocations from the construction prism of the project roads under design. These include water and sewerage infrastructure under NWSC, Electricity supply infrastructure under UMEME and Telecommunications infrastructure under different industry players.

**DESCRIPTION OF WORKS FOR KAMPALA CAPITAL CITY AUTHORITY ROADS**

The works on the project roads include earthworks for widening, minor improvements to alignment geometry and side drains, construction of a gravel Sub-base, construction of a base course with crushed stone material on all roads, construction of wearing course of Asphalt concrete, Installation of culverts and various ancillary road works. The road works in the planned road rehabilitation / construction projects will entail the following activities:

* Route survey and mapping to clearly identify the areas of all road alignments. This will even serve to show the properties as well as features that the road project will impact on;
* Clearance of the contractor’s campsite for the storage of plants, equipment, workshop, field laboratory, construction materials and related equipment storage;
* Construction of the support facilities in the campsite. Such facilities include access roads to the camp site, sanitary provisions, and a perimeter fence among others;
* Earthworks including cut and fill in the various areas will be needed for the formation of proper alignment levels as indicated in the design drawings.
* The material supply sites will be cleared of the vegetation and the over burden materials which will all be stock piled for the restoration of borrow pits after road works;
* The transportation of the road construction materials. The routes to be used by the trucks currently exist. Minimal negative impact to the environment shall be ensured. during the transportation of the materials, it is desired that the trucks be covered by tarpaulins to minimize wind blowing off loose soils from the trucks;
* Widening of existing carriage way and embankment to give a final cross section as shown in the drawings. Where existing carriageway is to be raised, fill as required, and where it is to be lowered, cut as required;
* Gravel sub-base, Crushed stone base and Asphalt Concrete as shown in drawings for project Roads;
* Grading and compaction of the road in layers using specified mechanical procedures and to the specifications;
* Installation of drainage infrastructures such as open channel covered by concrete slabs, culverts depending on the need of the specific points along all project roads as indicated in the drawings;
* Roadside drainage including kerb inlets to installed culverts;
* Replacement of all drainage structures on all roads;
* Construction of manholes including heavy duty covers on all project roads as shown in the drawings;
* Installation of road furniture within the furniture zone including street lights, garbage collection bins;
* Importation of loam soil and Grassing and planting of trees with in the furniture zone as detailed in the drawings for each project road;
* Addition of approved sand blinding layer to existing surface for construction of paved sidewalk. Surfacing of sidewalks with concrete slabs as shown in the drawings for each project road;
* Installation of kerbs as per kerb schedule in the drawings for all project roads;
* Construction of longitudinal utility service ducts underneath the furniture zone as shown in the drawings;
* Installation of transverse utility ducts as instructed by the Engineer;
* Provision of a traffic management system for safe accommodation of traffic during construction;
* Implementation of Health & Safety and environmental protection plans;
* Ancillary road works including, road signs, road studs, raised pedestrian crossings and road marking on all project roads as per drawings;
* Installation of traffic signals and
* Any other operation ancillary to the main works through day works.

The Works detailed above are only indicative of the Scope of Works associated with this contract and the Engineer may, where necessary, substitute some of the Works with others within the project areas without substantially altering the overall Scope of the Works. Work shall be measured and paid using the relevant rates and prices in the Bill of Quantities.

The speed limit will be sign posted at the specified limit of 50 km/hour as these roads have a relatively high volume of pedestrian traffic, particularly school children. Raised pedestrian crossings will be installed at specific sections of the roads to ensure safety. New road signs will be erected in accordance with the drawings and specified road sign standards.

The Engineer/Project Manager and the Client are to provide guidance and closely monitor works.

The employer shall be at liberty to negotiate the final scope of works pursuant to Public Procurement and Disposal of Public Assets) Regulations 2014.

The Works detailed above are only indicative of the Scope of Works associated with this contract and the Engineer may, where necessary, substitute some of the Works with others within the project areas without substantially altering the overall Scope of the Works. Work shall be measured and paid using the relevant rates and prices in the Bill of Quantities.

* 1. **WATER FOR CONSTRUCTION PURPOSES**

The contractor will be required to identify in conjunction with the Regional Water Office, suitable areas for drawing water for the works without interfering with the existing domestic and agricultural water supplies. Boreholes or small weirs at suitable locations on water courses may be needed in some places.

The Contractor must make adequate provision in his bid for all negotiations and procurement of water for construction activities, and all related costs will be deemed to be included in his tendered rates.

* 1. **DRAWINGS**

The reduced scale drawings issued with the bidding documents are for bidding purposes only. The Contractor will be supplied with two (2) full size A1paper prints of each of the approved Construction Drawing at contract commencement.

Any information in the possession of the Contractor that is required by the Resident Engineer to complete his as-built drawings must be supplied to the Resident Engineer before a Taking-Over Certificate is issued.

Only figured dimensions must be used and Drawings must not be scaled unless required by the Engineer. The Engineer will supply any figured dimensions that may have been omitted from the Drawings.

The levels given on the Structural Drawings are subject to confirmation on the Site and the Contractor shall submit all levels to the Engineer for confirmation before he commences construction of any structure. The Contractor shall also check all clearances given on the Drawings and shall inform the Engineer of discrepancies.

* 1. **SITE FACILITIES**

(a) Contractor’s Construction Camp

The Contractor must make his own arrangements for a suitable site for his construction camp and accommodation for his personnel. The location of the Contractor's site office and construction camp site will be subject to the approval of the Engineer, as well as any local authority.

(b) Power and Other Service

The Contractor must make his own arrangements concerning the supply of electrical power and all other services. No direct payment will be made for the provision of electrical and other services. The cost of providing these services will be deemed to be included in the rates and amounts tendered for the various items of work for which these services are required.

The Engineer/ Consultant will provide their own facilities (transport and office and consumables)

* 1. **CONSTRUCTION IN CONFINED AREAS**

It may be necessary for the Contractor to work in confined areas. Except in the case of structures and for specific items for which the restricted areas are defined in the project specifications, no additional payment will be made for work in" restricted areas" as described in Section 6100 of the General Specifications. In certain areas the width of the fill material and pavement layers may reduce to zero and the working space may be confined. The method of construction in these confined areas depends on the Contractor's construction plant. However ,the Contractor must note that measurement and payment will be in accordance with the specified cross-sections and dimensions, irrespective of the methods used to achieve these cross-sections and dimensions, and that the rates and amounts tendered will be deemed to include full compensation for any special equipment or construction methods or for any difficulty encountered in working in confined areas and narrow widths ,and at or around obstructions, and that no extra payment will be made nor will any claim for payment be considered on account of these difficulties.

* 1. **SECURITY**

The Contractor shall be responsible for the security of his personnel and construction plant on and around the Site of the Works and for the security of his camp, and no claims in this regard will be considered by the Employer.

* 1. **SURVEY & SETTING OUT OF THE WORK**

The geometric design shown on the drawings is based on a centre line and cross-section survey carried out during the detailed design stage. No staking or setting-out, other than the reference benchmarks, has been carried out. The Contractor shall use the set benchmarks for execution of the Works.

The Contractor shall be responsible for staking the centre line of the road together with the PI, BC and Eco fall horizontal curves, from the coordinates and level data provided on the construction drawings. Before commencing earthworks, the Contractor shall provide the Engineer with verification of existing ground levels, from cross-sections based on the staked centre line defined in the Drawings, taken at 20m intervals.

* 1. **ACCOMMODATION OF TRAFFIC**

Accommodation of traffic on this Contract will generally be achieved by reconstruction of the existing paved and gravel sections using half width construction of. Temporary diversions shall only be allowed over limited portions of the project length where half width construction is not considered practicable or safe.

Traffic shall be accommodated as specified and, in a manner, approved by the Engineer. It should be noted that penalties as specified in Section 1515 of Section VI, Part B: Technical Specifications. Requirements will be applied for in adequate accommodation of traffic by the Contractor.

The Contractors shall always be aware of the public’s right-of-way on public roads and he shall make use of approved methods to control the movement of his equipment and vehicles so as not to cause a hazard on the road.

The Contractor’s staff shall be fully trained before any road closure is made.

* 1. **SUBMISSION OF QUALITY ASSURANCE PLAN**

A quality assurance plan complying with the Employer’s specifications shall be submitted with the programme as required by Sub Clause 1205 Workmanship & Quality Control of the particular specification of the Conditions of Particular Application.

**Technical Specifications**

*[In drafting of the Specification, care must be taken when drafting the PDE’s Requirements to ensure that the requirements are not restrictive. Recognized international standards should be used as much as possible for the description of goods, materials and workmanship. Where other particular standards are specified, it should be stated that goods, materials and workmanship meeting other authoritative standards and which promise to ensure equal or higher quality than the standards specified, will also be acceptable. Where a brand name of a product is specified it should always be qualified with the terms “or equivalent”.]*

**Technical specifications are provided as Volume 3 of the Bid Document**

**Environmental, Social, Health and Safety Requirements**

# ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN

## Overview

This section presents the Environmental and Social Management and Monitoring Plan (ESMP) developed to guide environmental and social management for the proposed Roads, divided into three project phases (Pre-construction, Construction, and Operational or demobilization phases). The ESMP is designed to mitigate negative impacts and enhance positive benefits of the proposed project.

The ESMP comprises a series of individual plans that outline the scope of environmental, social and health management pertaining to compliance with applicable regulatory requirements. It transfers the findings and recommendations of the ESIA into clear measures for the management and monitoring of impacts during the three project implementation phases. Where potential impacts of moderate or higher significance were identified by the ESIA team, mitigation measures were recommended to avoid or reduce the negative impact, or enhance the positive impact. The commitments of the ESMP are summarized therein.

## Objectives of the ESMP

Key objectives of the ESMP are to:

* Facilitate compliance with applicable acts, regulations and guidelines;
* Recognize that social responsibility and environmental management are among the highest corporate priorities;
* Assign clear accountability and responsibility for environmental protection and social responsibility to management and employees;
* Facilitate environmental and social planning through project life cycle;
* Provide a process for achieving targeted performance levels;
* Provide appropriate and sufficient resources, including training, to achieve targeted performance levels on an on-going basis; and
* Evaluate environmental performance and social responsibility against existing environmental and other policies, objectives and targets and seek improvement where appropriate.

**Bidders are instructed to take into consideration the provisions of the ESMP for the projects. The details of the ESMP are in the Tables below.**

**Environmental and social management plan**

| **Ref.** | **Environmental Risk/Impact** | **Impact and Mitigation/Enhancement Commitments** | **Monitoring Indicators** | **Monitoring Frequency** | **Responsible Party for monitoring** | |
| --- | --- | --- | --- | --- | --- | --- |
| 1. **PRE-CONSTRUCTION PHASE** | | | | | | |
| **1.1.** | **IMPACTS ON THE SOCIO-ECONOMIC ENVIRONMENT** | | | | | |
| 1.1.1 | **POSITIVE IMPACTS** | | | | | |
| 1.1.1.1 | Short-term employment | * Contractor shall advertise available job opportunities through Local leaders. * Non-skilled jobs shall be reserved for interested residents along the roads; * Only trained and professional drivers shall drive the investigation teams. * Training workers of any development is key to their safety. All workers shall be inducted on safety issues before they commence their investigations * Project workers and communities shall be inducted and sensitized on protection of children and criminal effects of sexual engagement with children including street kids as a result of the road project; | * Notices on project jobs displayed in public places. * Recommendation letters for local people * No. of females employed. | monthly | Kampala Capital City Authority | |
| 1.1.1.2 | Income streams to project small-scale business owners | * Timely payments to the local business owners (e.g. eateries, transport operators) to enable maximum benefits to the local population; * Ensure adequate sensitization of the host communities including local business owners to prepare them for the construction phase opportunities. | * No. of local businesses supported | Monthly | Kampala Capital City Authority | |
| **1.1.2** | **NEGATIVE IMPACTS** | | | | | |
| 1.1.2.1 | Risk of increased spread of communicable diseases | * Adherence to WHO SOPs by the general public and in particular employees while in public. * Worker should and sign and adhere to the code of conduct. * Sensitize workers on risks of spread of communicable diseases. * Provide safe drinking water. | * No. of sensitization meetings done * Availability of clean safe drinking water | Weekly | Kampala Capital City Authority | |
| 1.1.2.2 | Occupational Health and Safety | * All people carrying out investigations should wear high visibility vests. * Only trained and professional drivers to drive the investigation teams. * First Aid kits shall be carried by the investigation teams during the surveys. * The investigation team shall be observant of any pits within their areas of investigation. * All workers should be inducted on safety issues before they commence their investigations | * No. of workers with PPE; * First Aid kits in place; * No. of workers inducted | Monthly | Kampala Capital City Authority | |
| 1.1.2.3 | Speculation and manipulation | * Contractor/Kira Municipality shall sensitize and provide project stakeholders with project information to prevent speculation and manipulation | No. of sensitization meetings held | Monthly | Kampala Capital City Authority | |
| 1. **CONSTRUCTION PHASE IMPACTS** | | | | | | |
| * 1. **IMPACTS ON THE SOCIO-ECONOMIC ENVIRONMENT** | | | | | | |
| **2.1.1** | **POSITIVE IMPACTS** | | | | | |
| 2.1.1.1 | Creation of Employment Opportunities | * The Contractor will involve local leaders in the recruitment process to ensure adequate dissemination of information on available job opportunities to the local communities. * Available job opportunities be disclosed in public places/notices. * The contractor will accord equal job opportunity to men and women with respect of level of skills required and take measures to increase the number of women employed such as encouraging women to apply, using selection criterion that promotes gender balance and providing a conducive work environment (flexible working hours, support for breast feeding women). * Workers and communities are inducted and sensitized on protection of children and criminal effects on sexual engagement of children including street children as a result of the road project; * The program will ensure that the national Labor laws and Employment Act are adhered to (including aspects of child labor requirements); * Efforts will be made to employ disadvantaged groups of people in the ZOI especially the youth and women | * Notices on project jobs displayed in public places. * Recommendation letters for employment for local people * No. of females employed | Monthly | Kampala Capital City Authority  MoKCC&MA | |
| 2.1.1.2 | Increase Income to Service Providers/ Suppliers. | * Acquisition of sources of materials or land where materials are sourced shall be based on a willing-seller willing-buyer agreement or resettlement action planning as applicable. * All contracts for material source areas shall be witnessed by Local Council chairpersons and spousal consent shall be sought. * Prompt payment of service providers/suppliers | * Purchase orders from local suppliers * Supply contracts with local services providers | Monthly | Kampala Capital City Authority  MoKCC&MA | |
| 2.1.1.3 | Short-term Roadside Business Opportunities and Creation of Market for Local Goods/Services and Secondary Businesses | * The contractor shall control dust by sprinkling water during road construction to avoid contamination of goods and service areas, and nuisance to potential customers and vendors. * Maintain access to vending points and service areas throughout construction and maintenance. * Ensure that regular business dealers and most especially food vendors are registered for identity and avoidance of unfair treatment by workers, such as denial of payment entitlements; * Prompt payment of service providers/suppliers * Sourcing of locally available materials from the project are community members | * Water sprinkled along the road * Maintained access to vending points * Coexistence of roadside businesses * Service provider agreements available * No. of service providers promptly paid | Weekly | Kampala Capital City Authority  MoKCC&MA  Contractor | |
| 2.1.1.4 | Skills Development among Local Residents | * The contractor will employ a big percentage of the workforce from project area. * Sensitize people especially youths on non-monetary benefits accruing to employment on road construction project including skills development. * Design employment contracts that guarantee employees progressive placements to facilitate skills development | * No. of locals employed * No. of trainings conducted * No. of workers promoted | Monthly | Kampala Capital City Authority  MoKCC&MA | |
| **2.1.2** | **NEGATIVE IMPACTS** | | | | | |
| 2.1.2.1 | Risk of land take | * The project has on-going community engagement process geared towards addressing land access in the project. * Undertake comprehensive community sensitization in regard to project objectives, target beneficiaries and make the part of the project from project onset to completion. * The program shall seek consent from property owners before road construction activities. * The project works are to be cautious of trees and in case they are inevitably lost, that loss would be compensated through a tree planting. * Management of complaints (including training of GRCs) and compensation of PAPs whenever necessary | * Sensitization of local communities on land requirements for the project * Replacement of damaged properties like perimeter walls, structures, trees, etc. | Monthly | Kampala Capital City Authority  MoKCC&MA | |
| 2.1.2.2 | Occupational Health and Safety Impact | * The contractor should develop a comprehensive Occupational health and Safety plan and enforce its implementation. * Undertake training of staff on safety procedures and precautions. * Provide appropriate PPE (reflectors, safety shoes, ear muffs, gloves, goggles, and others) to all workers and ensure that these are always used correctly. * Employ site HSE officers to regularly undertake safety inspections and trainings for the project activities. * Institute and implement an Emergency Response Plan in case of emergence incidences at the site such as identification of a referral hospital in area vicinity, have an ambulance in place, display emergency contacts and designate and communicate to all project workers’ emergency assembly points by installing visible signage. * Occasionally undertake emergency drills to train workers on emergencies incidences management and response. * Speed limits shall be attached to vehicles that will use the road * Incorporate speed control measures such as humps into the road design; * Post reflective, directional and warning signs for road diversions to be put at reasonable distances ahead of the diversion roads; * Materials hauled by heavy trucks shall be covered with a tarpaulin; * Pedestrian walkways/shoulders, cycle ways, efficient pedestrian crossing signals at all the intersections, guard rails on the sides of the carriageway, safe stopping/parking spaces/lay-bys to be incorporated into road designs; * Visible road signs shall be deployed warning road users about on-going road construction works; * Warning signs shall be placed on vehicles moving bitumen and fuel; * A public road safety awareness programme shall guide workers and local communities in safety. Regular safety talks shall be made to workers, with institute strict punitive measures for non-compliance with safety rules; * Screening concrete barricades and warning conspicuous tapes in and around disturbed and excavated areas to control access & minimize pit-falls/ accidents for both workers and the general public. | * Training Records * PPE available and used * Fully stocked first aid kit in place * A trained First Aider in place * Traffic signs, barriers, and flaggers deployed in work sections * Traffic control measures enforced * No. of boda-bodas sensitized * Emergency response plan implemented | Weekly | Kampala Capital City Authority  MoKCC&MA | |
| 2.1.2.3 | Traffic Holdups and safety hazards | * Install warning signage e.g., speed limits, diversions and children crossing. * Adopt a clear vehicle maintenance schedule to ensure proper functioning of all trucks and vehicles to eliminate noxious fumes and gaseous emission associated with malfunction of motor vehicles. * Ensure optimum loading capacity to save on unnecessary trips of heavy loading vehicles. * Installation of speed guards in haulage fleet. * Labelling of haulage trucks with highly visible numbers for easy recognition in case of an accident or bad driving. * Install a tracking system to monitor speed and location of vehicles * The Contractor shall be required to put in place a procedure for hiring competent drivers and operator. | * Traffic signs, barriers and flag persons deployed * Traffic measures followed * No. sensitization meetings held * Emergency response plan implemented | Weekly | Kampala Capital City Authority  UPF | |
| 2.1.2.4 | Risk of HIV/AIDS spread | * Ensure opportunities for local community members employment are given to area residents to minimize risks due to relocation of people outside their homes/families. * Implement HIV/AIDS prevention awareness and treatment campaigns. * Undertake sensitization of workers on the need for responsible code of conduct to regulate behavior within the local communities, including use of abusive language, prostitution, alcohol, and drug abuse among others; and * Give priority to skilled and unskilled local labor during project recruitment process. | * Signed COC available * No. sensitization meeting * Condoms provided * IEC material on HIV/AIDS spread and prevention displayed | Monthly | Kampala Capital City Authority  MoKCC&MA | |
| 2.1.2.4 | Risks of Fire Outbreaks | * Procure and install adequate fire-fighting equipment (extinguishers) in construction vehicles and at storage yards, ensure they are routinely serviced to always ensure their efficiency and functionality. * Fire risks can be minimized by application of measures for prevention and control of all highly flammable products. * Develop a fire action plan that will be communicated to all workers. * Regularly train all workers in fire prevention and containment procedures. * Ensure all fire hazards are mapped out and all workers are informed of potential fire hazards. * Put in place sand buckets and water storage tanks filled with water all the time for use in fire containment in case of a fire outbreak. * Place signs in visible areas within project site such as those displaying hazard warnings and deterring anyone from smoking in fire risk areas. | * No. of trainings held * Firefighting equipment installed * Emergency exit routes designated * Assembly point designated | Weekly | Kampala Capital City Authority  MoKCC&MA | |
| 2.1.2.5 | Impacts on Public Health and Safety | * All construction excavations and trenches should be well and distinctly marked and bounded with reflective material. * Monitoring of road safety and air quality conditions shall be undertaken; * The public will be encouraged to report any such lapses to NEMA, and local authorities and the contractor shall be held liable for any act of omission and / or commission. * Ensure that the workers are adequately protected from exposure to excessive dust and noise, or injury through provision of appropriate gear including earmuffs, masks, safety boots, and safety helmets. * Ensure training of workers on the value and use of PPE and the consequences of failing to use the equipment. * Materials at the site and during transportation should be protected through methods such as covering using tarpaulins, and sprinkling of water to avoid being dispersed by wind; * Frequent watering of areas under construction and other areas of settlements and trading centers. * Ensure to regulate material hauling traffic speed and install appropriate road signage at critical sections to minimize dust and minimize safety risks. * Further, temporary speed humps should be placed at regular intervals along habited sections of the road. Speed limits in such places shall be 30 km/hr and frequency of vehicular movements and application of water at periodic intervals on opened up surfaces will control and reduce the generation of high quantities of dust considered as nuisance. * Maintenance and the planting of trees will be done to maintain good air quality within the surrounding environs. * A programme of servicing for all vehicles and equipment parts shall be drawn up and implemented. This programme will ensure that engines of all vehicles and equipment are maintained for optimum performance. * The work schedules for workers will also be designed to limit the exposure time. As a rule, no worker shall be exposed to noise level greater than 70 dB (A) for a duration exceeding 8 hours per day. | * Traffic signs, barriers and flag persons deployed * Traffic measures followed * No. sensitization meetings held * Service tags * Emergency response plan implemented * Work schedule * Presence of barriers between works and schools * No. sensitization meeting | Weekly | Kampala Capital City Authority;  MoKCC&MA | |
| 2.1.2.5 | Disruption of existing utilities along the road | * The contractor and utility service providers shall mark out utility lines where they exist within the operation zone before operations commence. * Affected services shall be assessed and restored to ensure limited inconvenience to the public. * The Contractor will engage the utility service providers before commencement of the works. | * Utility services marked out * Interrupted services * Utility services providers engaged | Monthly | Contractor  Kampala Capital City Authority | |
| 2.1.2.6 | Destruction of physical cultural resources | * Work must immediately stop along that section, and the Supervising Engineer, Department of Museums and Antiquities and NEMA immediately informed to take a decision on the way forward. * Care must be taken during the excavation of borrow pits to avoid family or clan graveyards. The contractor shall be guided to assess the proximity of borrow pits to graveyards before negotiation with the land owners. * A Chance finds procedure will be prepared to clearly defined steps to manage chance findings on the projects; | * A chance finds procedure is in place; * Procedural steps are clearly known by the project staff in the event of chance finds | Daily, and weekly | Supervising Consultant, Kampala Capital City Authority,  MoKCC&MA | |
|  | Ground vibrations and noise emissions | * Fitting silencers/ mufflers on project machinery during operations shall be required; * Regular servicing, maintenance and appropriate repair of haulage vehicles and construction machinery with potential to generate noise; * Temporary noise barriers during construction at hotspots to shield receptors such as schools, health centers shall be established whenever necessary to limit noise and dust emissions. * Permanent noise barrier at hotspots should be considered, following the assessment of the impact severity, * Construction activities near sensitive receptors such as health centers, hotel service centers will be limited to day time only, at regulated level. * Flagmen shall be deployed and standard road signage posted to control traffic speed and noise around schools, churches, and mosques at all times * The Contractor shall conduct regular noise monitoring and produce monthly noise monitoring records; * Stone crushing plants should be operated according to manufacturer’s specifications; * Appropriate PPE (ear muffs etc.) shall be provided to the staff at the work sites and contractors shall ensure that wearing of the ear protection device by workers is mandatory; especially for those operating close to the noisy machines; * No worker should be exposed to noise level greater than 70 dB (A) for a duration exceeding 8 hours per day | * Noise emissions managed; * Equipment/machinima in good working conditions with minimal noise impact; * Workers provided with adequate safety gear; * Monthly noise monitoring reports in place |  |  | |
| 2.2 | * POTENTIAL IMPACTS ON THE BIOPHYSICAL ENVIRONMENT | | | | | |
| 2.2.1 | **NEGATIVE IMPACTS** | | | | | |
| 2.2.1.1 | Potential clearance of vegetation | * Vegetation clearance and excavation works should be limited to the areas marked for the road works. * Progressive re-vegetation should be implemented through measures such grass planting and planting native trees on the road reserves. * Endangered/vulnerable plant species (Mvule) such as those noted during the baseline vegetation surveys should be replanted elsewhere within the jurisdiction of MoKCC&MA | * Number trees marked and reserved * Number of trees planted | Monthly | Kampala Capital City Authority  Contractor  MoKCC&MA | |
| 2.2.1.2 | Soil disturbance and erosion | * Provide soil conservation structures on areas prone to soil erosion (road banks) to reduce impact by the run-off. * Limit site clearance to sections needed for the project to reduce vegetation loss and exposing the sites to erosion. * Sites should be adequately restored to ensure re-vegetation and re-grassing. * Install suitable gulley traps and check dams along roadside drains. * Institute regular monitoring of roads construction activities to underpin appropriate and effective control measures of erosion especially during rainy/wet conditions. * The road maintenance should address issues of siltation on road channels. | * Availability of drainage channels * Soil erosion structures in place * Restored eroded surfaces | Weekly | Kampala Capital City Authority  Contractor  MoKCC&MA | |
| 2.2.1.3 | Impact of poorly managed cut-to-spoil | * Some of the cut to spoil can be used as a fill material with the approval of the Engineer, however, excess of it shall be disposed in areas approved by the Engineer. * Some of the cut to spoil material can be used in restoration works especially in borrow pit areas to aid re-vegetation; and * Excess cut to spoil can be disposed in approved areas after acquisition of the letter of “No Objection” from NEMA. | * Designated cut-to-spoil holding areas * Soil erosion incidences * Poorly piled cut-to-spoil and overburden | Monthly | Kampala Capital City Authority  MoKCC&MA | |
| 2.2.1.4 | Risk of soil pollution/contamination | * All waste lubricants and oils shall be collected and recycled or disposed of offsite to approved sites of disposal by a NEMA certified waste handler. * Central points for refueling of vehicles and machinery shall be established; * The floors of refueling points shall be bunded/lined with impervious material; * Plastic sheeting shall be placed under hazardous material and their storage areas to collect and retain leaks and spills; * Contaminated storm water at oil storage areas shall be drained/led into ditches and ponds with oil traps (interceptors); * Contaminated and worn plastic sheeting shall be packed into drums and disposed in approved waste disposal sites by a NEMA certified waste handler; * Avoid spilling of surfacing materials such as bitumen on surfaces outside the project site meant for bitumen spray. During transportation, bitumen should be well packed to avoid spillages; * Bitumen shall not be applied on the carriage ways during strong winds, or heavy rains; * Unused bitumen should be collected for safe handling (stored in designated locations) and future use, and shall not be discharged into side drains; * Regular servicing and maintenance of vehicles and construction machinery to prevent spillage of fuel and oils; * An oil spill Contingent Plan shall be developed and followed. * A proper waste management Plan shall be developed and followed; * Spilling of surfacing materials such as bitumen on surfaces outside the project site meant for bitumen spray shall be avoided. During transportation, bitumen shall be well packed to avoid spillages. | * Lubricants and oils collected and properly disposed of; * Refueling points have bunded floors; * Bitumen is well packed during transportation to avoid spillage; * A Waste Management Plan is in place |  |  |  |
| 2.2.1.5 | Impacts on landscape and aesthetics | * All quarries and borrow pits opened up by Contractors shall be restored with spoil material from the road cuts and top soil initially removed from the quarry and borrow pit sites * Improve the sites aesthetics on completion of site preparation works by landscaping and greening of open areas. * Limit tree felling and vegetation stripping outside the earmarked road sites. * Cuts at material sources should not exceed the angle of repose which could lead to rock falls, slips and land slides | * Restored facilities * Planted and spared trees * Enhanced/maintained area aesthetics | Monthly | Kampala Capital City Authority  MoKCC&MA | |
| 2.2.1.6 | Construction and domestic waste generation | * Undertake sensitization of all workers on proper waste management practices. * All hazardous wastes shall be batched and stored in leak proof containers set on screed or concrete platform sheltered from adverse weather conditions. * The contractor shall explore avenues for reuse or recycling of wastes. Where the community expresses interest, the contractor shall use appropriate and safe approaches to waste disposal that benefit local communities. * The contractor shall procure the services of a NEMA licensed waste handler to evacuate, transport and dispose of hazardous wastes * Concrete waste and damaged or rejected concrete products shall be reused where possible as fill material where specifications allow, however, where such products cannot be reused, they will be used as backfill material for borrow pit and quarry restoration. * All excavated spoil and scarified asphalt pavement waste shall be blended to provide fill materials where specifications allow. However, scarified pavement waste and spoil shall be used to backfill the quarry source areas during restoration. | Waste collection bins in place  Open waste dumping and burning  Clean construction site  Contracted licenced waste handler  Waste management signage in place | Weekly | Kampala Capital City Authority  MoKCC&MA | |
| 2.2.1.7 | Potential Introduction of Invasive Plant Species | * Transfer of spoil across vegetation zones shall be limited to dumpsites. The Environment team shall identify suitable sites for spoiling in all vegetation zones identified. * Equipment shall be washed before they are moved between borrow areas. * When invasive species are introduced to new areas, they will be manually removed and transported for disposal * The project staff (both technical and non-technical staff) will be sensitized against introducing and controlling of invasive alien species. Any invasive species observed by workers during project implementation shall be reported to the project supervisor | * No. dumpsite available and used * Equipment cleaned | Monthly | Kampala Capital City Authority  MoKCC&MA | |
| 2.2.1.8 | Negative impact on air quality  Dust generation | * All the machinery shall be kept in good working order. * Switch off all machinery when not in use; and * Ensure that all project equipment is serviced on a regular basis. * Dust suppression measures (water sprinkling) on roads and soil/murram stockpiles should be implemented where appropriate. * Unpaved roads in settled-in areas and used by haulage trucks during road construction should be sprinkled with water during hot and dry weather (using water browsers); * Cover and/or maintain appropriate freeboard on trucks hauling any lose material such as murram and compacting soil that could produce dust during haulage process. * Landscaping to be carried out after construction and should include trees, grasses and shrubs whichever is appropriate in order to maintain air shed purification functions and soil stabilization; * During construction, the speed of material haulage trucks and other vehicles along the project road and along any road diversions shall be restricted to reduce dust emissions; * Erodible material stockpiles shall be distant from sensitive establishments such as classrooms, hostels, hotels and supermarkets to reduce dust emissions; * The contractor should consider nuisance dust monitoring along access routes, borrow pit sites and project road. | * Records of air quality monitoring * Maintenance tags * PPE available and used * Idling of machinery * Records of air quality monitoring * Trucks covered * Speed limit signs available and respected * Maintenance logs * Full PPE used * Idling of machinery avoided | Weekly; monthly | Implementing Entities such as Kampala Capital City Authority, MoKCC&MA | |
| 1. **OPERATION PHASE IMPACTS** | | | | | | |
| * 1. **IMPACTS ON THE SOCIO-ECONOMIC ENVIRONMENT** | | | | | | |
| * + 1. **POSITIVE IMPACTS** | | | | | | |
| 3.1.1.1. | Improved traffic flow and mobility | * The traffic signals shall be effectively linked together to enhance their collective efficiency. * Given the magnitude of changes likely to be made at the road intersections, appropriate signage shall be installed to guide traffic effectively. * Increase in traffic policing shall be required to reduce the “new road effect” associated with over speeding with associated elevated risk of accidents. * Routinely maintain the roads and ensure that the drainage systems are operational * Ensure that communities do not dump waste within the roads through sensitization * Fixed the damaged sections of the roads as soon as possible. | * Traffic signals perform efficiently; * Improved traffic flow; * Increased traffic and business activities * Fixed road damages | Weekly | MoKCC&MA and Kampala Capital City Authority | |
| 3.1.1.2. | Improved Road Aesthetics | * Routinely maintain the roads and ensure that the drainage systems are operational * Ensure that communities do not dump waste within the roads through sensitization * The damage sections of the roads shall be fixed as soon as possible. * Proper maintenance of the vegetation planted through landscaping shall be emphasized | * Clean roads without Waste dumping | Annually | Kampala Capital City Authority  Local leaders | |
| 3.1.1.3 | Improved access to Markets and travel time | * Routinely maintain the roads and ensure that the drainage systems are operational * Sensitization to address communities dumping waste within the roads * Fixed the damage sections of the roads as soon as possible. | * Well maintained road network * Fixed road damages | Annually | Kampala Capital City Authority  Local Leaders | |
| 3.1.1.4 | Improvement in Social Service Delivery | * Routine road maintenance to ensure operational drainage systems * Prohibit communities from waste dumping on the roads via sensitization * Fixed the damage sections of the roads as soon as possible. | * Road well maintained * Clean roads with Waste dumping contained | Annually | Kampala Capital City Authority  Local leadership | |
| * + 1. **NEGATIVE IMPACTS** | | | | | | |
| 3.1.2.1. | New Road Effect” Leading to Accidents | * Accident hotspots will be marked with appropriate road signs and safety structures/ furniture. * Road signage should be installed and maintained to retain visibility * Promote road safety campaign and enforce traffic regulations. * Enforce road use regulations by traffic police for motorists and road users. * Introduce speed calming measures at busy social service centers including schools, health facilities, trading centers and markets at both approaches. | * Installed road signage * Accident on the road * Road humps installed * Speed limits installed | Monthly | Kampala Capital City Authority  UPF | |
| 3.1.2.2. | Induced Development | * Kiira Municipality shall develop physical plans for the trading centers where none exist to ensure planned development. The plans shall be implemented to avoid unplanned development in trading centers traversed by roads. | * Physical Development Plans implemented | Monthly | Kampala Capital City Authority  Local leaders | |
| * 1. **POTENTIAL IMPACT ON THE BIOPHYSICAL ENVIRONMENT** | | | | | | |
| * + 1. **POSITIVE IMPACT** | | | | | | |
| 3.2.1.1 | Impact on drainage and reduction of flooding events | * Contractors should ensure that cut-off drains are not directed into residential and commercial buildings close to the project sites | * Improved drainage systems along the road infrastructure | Annually | MoKCC&MA, Kampala Capital City Authority | |
| * + 1. **NEGATIVE IMPACT** | | | | |  | |
| 3.2.2.1 | Impact on Visual and Aesthetic quality | * Trees should be planted to compensate for vegetation clearance as a fundamental step in enhancing the scenic view of the project area. * Sensitive areas such as schools, hospitals, etc. opened to public view shall be provided with a fence to avoid general public view and reduce exposure to noise and dust from construction activities | * Compensatory tree planting; * Sensitive receptors protected | Monthly | MoKCC&MA, Kampala Capital City Authority and | |
| 3.2.2.2 | Project Decommissioning | * Obsolete equipment, trucks and machinery shall be removed from sites. * Makeshift access roads and haulage routes to storage sites and borrow pits shall be closed and scarified in consultation with authorities. * Backfill all openings with soil and leftover murram * Plant fast-growing trees and grasses to stabilize cut slopes especially along road banks and seeding of the final reclaimed surface with native spp. * Fencing off the re-vegetated areas should be provided until the reinstated vegetation has reached maturity. | * Restored ancillary sites * Registered complaints * Public health and safety incidents | Annually | Kampala Capital City Authority  Local Leaders,  MoKCC&MA | |

**Drawings**

*[Insert here a list of Drawings. The actual Drawings, including site plans, should be attached to this section or annexed in a separate folder].*

Drawings are attached as **Volume 4** f the Bid Documents.

**Activity Schedule/ Bills of Quantities**

|  |
| --- |
| **Activity Schedule** |
| Date: *[insert date (as day, month and year) of Bid Submission]*  Procurement Reference No.:*[insert Procurement Reference number]* |
| Name of Bidder: *[Insert the name of the Bidder/Joint Venture/Consortium/Association]* |

|  |  |  |
| --- | --- | --- |
| **Item number** | **Activity Description** | **Amount in Ug. Sh** |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

Signed: *[signature of person whose name and capacity are shown below]*

Name: *[insert complete name of person signing the bid]*

In the capacity of *[insert legal capacity of person signing the bid]*

Duly authorised to sign the bid for and on behalf of: *[insert complete name of Bidder/Joint Venture/Consortium/Association]*

Dated on day of , *[insert date of signing]*

|  |
| --- |
| **Bill of Quantities**  **Detailed BoQs are provided as Volume 2 of this Document**  ***Note that each page of the BoQs should be signed by the authorized representative of the Bidder*** |
| Date: *[insert date (as day, month and year) of Bid Submission]*  Procurement Reference No.:*[insert Procurement Reference number]* |
| Name of Bidder: *[Insert the name of the Bidder/Joint Venture/Consortium/Association]* |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Item number** | **Description of Works** | **Unit** | **Quantity** | **Rate** | **Amount** |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  | ***Grand Total:*** | | |  |

Signed: *[signature of person whose name and capacity are shown below]*

Name: *[insert complete name of person signing the bid]*

In the capacity of *[insert legal capacity of person signing the bid]*

Duly authorised to sign the bid for and on behalf of: *[insert complete name of Bidder/Joint Venture/Consortium/Association]*

Dated on day of , *[insert date of signing]*

**Supplementary Information**

**NONE**

**PART 3 - Contract**

**Section 7: General Conditions of Contract for the Procurement of Works**

**Table of Clauses**

1. [**General 13**](#_bookmark71)**6**
   1. [Definitions 136](#_bookmark72)
   2. [Contract Documents 138](#_bookmark73)
   3. [Interpretation 138](#_bookmark74)
   4. [Language 139](#_bookmark75)
   5. [Joint Venture, Consortium or Association 139](#_bookmark76)
   6. [Eligibility 139](#_bookmark77)
   7. [Notices 139](#_bookmark78)
   8. [Governing Law 140](#_bookmark79)
   9. [Scope of the Works 140](#_bookmark80)
   10. [Project Manager’s Decisions 140](#_bookmark81)
   11. [Delegation 140](#_bookmark82)
   12. [Subcontracting 140](#_bookmark83)
   13. [Other Contractors 140](#_bookmark84)
   14. [Contractor’s Personnel 140](#_bookmark85)
   15. [PDE’s and Contractor’s Risks 141](#_bookmark86)
   16. [PDE’s Risks 141](#_bookmark87)
   17. [Contractor’s Risks 141](#_bookmark88)
   18. [Insurance 142](#_bookmark89)
   19. [Site Investigation Reports 142](#_bookmark90)
   20. [Queries About the Special Conditions of Contract 142](#_bookmark91)
   21. [Contractor to Construct the Works 142](#_bookmark92)
   22. [Works to be Completed by the Intended Completion Date 142](#_bookmark93)
   23. [Approval by the Project Manager 142](#_bookmark94)
   24. [Safety and Safety Procedures 143](#_bookmark95)
   25. [Discoveries 143](#_bookmark96)
   26. [Possession of the Site 143](#_bookmark97)
   27. [Access to the Site 143](#_bookmark98)
   28. [Contractor’s Equipment 143](#_bookmark99)
   29. [Protection of the Environment 143](#_bookmark100)
   30. [Prohibition of Harmful Child Labour 144](#_bookmark101)
   31. [Health and Safety 144](#_bookmark102)
   32. [Instructions, Inspection and Audits 144](#_bookmark103)
   33. [Disputes 144](#_bookmark104)
   34. [Procedure for Settling Disputes 145](#_bookmark105)
   35. [Replacement of Adjudicator 145](#_bookmark106)
2. [**Time Control 105**](#_bookmark107)
3. [Program 145](#_bookmark108)
4. [Extension of the Intended Completion Date 146](#_bookmark109)
5. [Acceleration 146](#_bookmark110)
6. [Delays Ordered by the Project Manager 146](#_bookmark111)
7. [Management Meetings 146](#_bookmark112)
8. [Early Warning 146](#_bookmark113)
9. [**Quality Control 147**](#_bookmark114)
10. [Identifying Defects 147](#_bookmark115)
11. [Tests 147](#_bookmark116)
12. [Correction of Defects 147](#_bookmark117)
13. [Uncorrected Defects 147](#_bookmark118)
14. [**Cost Control 147**](#_bookmark119)
15. [Bill of Quantities or Activity Schedule 147](#_bookmark120)
16. [Changes in the Bill of Quantities or Activity Schedule 147](#_bookmark121)
17. [Variations 148](#_bookmark122)
18. [Payments for Variations 148](#_bookmark123)
19. [Payment Certificates 149](#_bookmark124)
20. [Issue of Interim Payment Certificates 149](#_bookmark125)
21. [Payments 150](#_bookmark126)
22. [Compensation Events 150](#_bookmark127)

[54. Tax 151](#_bookmark128)

1. [Currencies 151](#_bookmark129)
2. [Price Adjustment 152](#_bookmark130)
3. [Retention 153](#_bookmark131)
4. [Liquidated Damages 153](#_bookmark132)
5. [Bonus 153](#_bookmark133)
6. [Advance Payment 153](#_bookmark134)
7. [Performance Security and ES Performance Security 154](#_bookmark135)
8. [Day works 154](#_bookmark136)
9. [Cost of Repairs 154](#_bookmark137)
10. [**Finishing the Contract 154**](#_bookmark138)
11. [Completion 154](#_bookmark139)
12. [Taking Over 155](#_bookmark140)
13. [Final Account 155](#_bookmark141)
14. [Operating and Maintenance Manuals 155](#_bookmark142)
15. [Termination 155](#_bookmark143)
16. [Payment upon Termination 156](#_bookmark144)
17. [Release from Performance 156](#_bookmark145)

A. General

1. **Definitions**
   1. The following words and expressions shall have the meanings hereby assigned to them:
      1. “Activity Schedule” means the priced and completed Activity Schedule, forming part of the Bid, which provides a breakdown of the Contract Price by work elements for a Lump Sum Contract.
      2. “Adjudicator” is the person appointed jointly by the Procuring and Disposing Entity and the Contractor to resolve disputes in the first instance.
      3. “Admeasurement Contract” means a Contract under which the Works are executed on the basis of agreed rates and prices in a Bill of Quantities and payment is made for the quantity of work actually executed.
      4. “Bill of Quantities” means the priced and completed Bill of Quantities forming part of the Bid, which provides the agreed rates and prices for payment for an Admeasurement Contract.
      5. “Compensation Events” are those defined in Clause 44 hereunder.
      6. “Completion Date” is the date of completion of the Works as certified by the Project Manager.
      7. “Contract” is the agreement between the Procuring and Disposing Entity and the Contractor to execute, complete, and maintain the Works.
      8. “Contractor” is a person or corporate body whose Bid to carry out the Works has been accepted by the Procuring and Disposing Entity and is named as such in the Agreement, and means Provider as defined in the Public Procurement and Disposal of Public Assets Act, 2003.
      9. “Contractor’s Bid” is the bid submitted to the Procuring and Disposing Entity by the Contractor who signed the contract for the works .
      10. “Contract Price” is the price stated in the Agreement and thereafter as adjusted in accordance with the provisions of the Contract.
      11. “Days” are working days; “months” are calendar months.
      12. “Dayworks” are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant.
      13. “Defect” is any part of the Works not completed in accordance with the Contract.
      14. “Defects Liability Certificate” is the certificate issued by the Project Manager upon correction of defects by the Contractor.
      15. “Defects Liability Period” is the period calculated from the Completion Date, during which the Contractor must rectify defects.
      16. “Drawings” include calculations and other information provided or approved by the Project Manager for the execution of the Contract.
      17. “Procuring and Disposing Entity” is the party named in the Agreement, who employs the Contractor to carry out the Works and means Procuring and Disposing Entity as defined in the Public Procurement and Disposal of Public Assets Act, 2003.
      18. “Equipment” is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works.
      19. “written” or “in writing” means type-written, printed or electronically made, and resulting in a permanent record
      20. “GCC” means the General Conditions of Contract.
      21. “Initial Contract Price” is the Contract Price listed in the Agreement.
      22. “Intended Completion Date” is the date on which it is intended that the Contractor shall complete the Works.
      23. “Lump Sum Contract” means a Contract under which the Works are executed for an all inclusive fixed total amount, as defined in the Activity Schedule.
      24. “Materials” are all supplies, including consumables, used by the Contractor for incorporation in the Works.
      25. “Plant” is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function.
      26. “Project Manager” is the person named in the SCC (or any other competent person appointed by the Procuring and Disposing Entity and notified to the Contractor, to act as a representative of the Contract Manager) who is responsible for supervising the execution of the Works and administering the Contract. The
      27. (za) “Contract Manager” is the person appointed by the Accounting Officer from the user department or another Procuring and Disposing Entity to manage the contract.
      28. (aa) “Provisional Sum” means a sum included in the Contract and so designated in the Bill of Quantities or Activity Schedule for the provision of supplies, works or services or for contingencies to be expended for the execution of the Works in whole or part at the direction of the Project Manager.
      29. (bb)“SCC” means the Special Conditions of Contract. (cc) “Site” is the area defined as such in the SCC.
      30. (dd)“Site Investigation Reports” are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site.
      31. (ee) “Specification” means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager.
      32. (ff) “Start Date” is the latest date by when the Contractor shall commence execution of the Works and is specified in the SCC.
      33. (gg) A “Subcontractor” is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site.
      34. (hh)“Temporary Works” are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works.
      35. (ii) “Variation” is an instruction given by the Project Manager which varies the Works. (jj) “Works” are what the Contract requires the Contractor to construct, install, and turn
      36. over to the PDE, as defined in the SCC.
      37. (kk) “ESHS” means environmental, social (including sexual exploitation and abuse (SEA) and gender based violence (GBV)), health and safety.
2. **Contract Documents**
   1. The documents forming the Contract shall be interpreted in the following order of priority:
      1. Agreement,
      2. Contractor’s Bid,
      3. Special Conditions of Contract,
      4. General Conditions of Contract,
      5. Scope of Works,
      6. Drawings,
      7. Bill of Quantities or Activity Schedule, as appropriate; and
      8. any other document listed in the SCC as forming part of the Contract.
   2. Subject to the order of precedence set forth in Sub-Clause 2.1, all documents forming the Contract (and all parts thereof) are intended to be correlative, complementary, and mutually explanatory
3. **Interpretation**
   1. If the context so requires it, singular means plural and vice versa
   2. Contract

The Contract constitutes the whole agreement between the PDE and the Provider and supersedes all communications, negotiations and agreements (written or oral) of parties with respect thereto made prior to the date of Contract.

* 1. Amendment

No amendment or other variation of the Contract shall be valid unless it is in writing, is dated, expressly refers to the Contract, and is signed by a duly authorised representative of each party thereto.

* 1. Non-waiver
     1. Subject to GCC Sub-Clause 32.4(b) below, no relaxation, forbearance, delay, or indulgence by either party in enforcing any of the terms and conditions of the Contract or the granting of time by either party to the other shall prejudice, affect, or restrict the rights of that party under the Contract, neither shall any waiver by either party of any breach of Contract operate as waiver of any subsequent or continuing breach of Contract.
     2. Any waiver of a party’s rights, powers, or remedies under the Contract must be in writing, dated, and signed by an authorised representative of the party granting such waiver, and must specify the right and the extent to which it is being waived.
  2. Severability

If any provision or condition of the Contract is prohibited or rendered invalid or unenforceable, such prohibition, invalidity or unenforceability shall not affect the validity or enforceability of any other provisions and conditions of the Contract

* 1. These General Conditions of Contract shall apply in their entirety, except where alternative options are specified for different types of contract. Where alternative options are specified:
     1. Option 1 shall apply to Admeasurement Contracts; and
     2. Option 2 shall apply to Lump Sum Contracts.
  2. For purposes of interpreting these Conditions of Contract, the type of contract is as specified in the SCC.
  3. If sectional completion is specified in the SCC, references in the Conditions of Contract to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works).

1. **Language**
   1. The Contract as well as all correspondence and documents relating to the Contract exchanged by the Provider and the PDE, shall be written in English. Supporting documents and printed literature that are part of the Contract may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified, in which case, for purposes of interpretation of the Contract, this translation shall govern.
   2. The Provider shall bear all costs of translation to the governing language and all risks of the accuracy of such translation.
2. **Joint Venture, Consortium or Association**

Unless otherwise specified in the SCC, if the Provider is a JV, consortium, or association, all of the parties shall be jointly and severally liable to the PDE for the fulfilment of the provisions of the Contract and shall designate one party to act as a leader with authority to bind the JV, consortium, or association. The composition or the constitution of the JV, consortium, or association shall not be altered without the prior consent of the PDE.

1. **Eligibility**
   1. The provider and its subcontractors shall have the nationality of an eligible country. A provider or subcontractor shall be deemed to have the nationality of a country if it is a citizen or constituted, incorporated, or registered, and operates in conformity with the provisions of the laws of that country.
2. **Notices**
   1. Any notice given by one party to the other pursuant to the Contract shall be in writing to the address specified in the SCC. The term “in writing” means communicated in written form (e.g. by mail, e-mail, fax, including if specified in the BDS, distributed or received through the electronic-procurement system used by the PDE) with proof of receipt.
   2. A notice shall be effective when delivered or on the notice’s effective date, whichever is later.
3. **Governing Law**

The Contract shall be governed by and interpreted in accordance with the laws of Uganda.

1. **Scope of the Works**
   1. The works and related services to be provided shall be as specified in the SORs and other provisions of the contract
2. **Project Manager’s Decisions**
   1. Except where otherwise specifically stated, the Project Manager will decide contractual matters between the PDE and the Contractor in the role representing the PDE.
   2. The Project Manager will obtain the PDE’s approval for any of the decisions specified in the SCC.
3. **Delegation**
   1. The Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor in writing, and may cancel any delegation after notifying the Contractor.
4. **Subcontracting**
   1. Unless otherwise specified in the SCC, the Contractor may subcontract with the approval of the Project Manager, but may not assign the Contract without the approval of the PDE in writing. Subcontracting shall not alter the Contractor’s obligations.
   2. Any further conditions relating to subcontracting shall be as specified in the SCC.
5. **Other Contractors**
   1. The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the PDE between the dates given in the Schedule of Other Contractors, if such Schedule is specified in the SCC. The Contractor shall also provide facilities and services for them as described in the Schedule. The PDE may modify the Schedule of Other Contractors, and shall notify the Contractor of any such modification.
6. **Contractor’s Personnel**
   1. If the Schedule of Key Personnel is specified in the SCC, the Contractor shall employ the key personnel named in the Schedule, or other personnel approved by the Project Manager, to carry out the functions stated in the Schedule. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule.
   2. The Project Manager may require the Contractor to remove (or cause to be removed) any person employed on the Site or Works, including the Contractor’s Representative if applicable, who:
7. Persists in any misconduct or lack of care,
8. Carries out duties incompetently or negligently,
9. Fails to conform with any provisions of the Contract,
10. Persists in any conduct which is prejudicial to safety, health, or the protection of the environment, or
11. Based on reasonable evidence, is determined to have engaged in Fraud and Corruption during the execution of the Works.
12. Undertakes behaviour which breaches the Code of Conduct (ESHS) (e.g. spreading communicable diseases, sexual harassment, gender based violence (GBV), sexual exploitation or abuse, illicit activity or crime).”
    1. The Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract. If appropriate, the Contractor shall then appoint (or cause to be appointed) a suitable replacement person.
13. **PDE’s and Contractor’s Risks**
    1. The Procuring and Disposing Entity carries the risks which the Contract states are Procuring and Disposing Entity’s risks, and the Contractor carries the risks which the Contract states are Contractor’s risks.
14. **PDE’s Risks**
    1. From the Start Date until the Defects Correction Certificate has been issued, the following are PDE’s risks:
       1. The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to:
          1. Use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works; or
          2. Negligence, breach of statutory duty, or interference with any legal right by the PDE or by any person employed by or contracted to him except the Contractor.
       2. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the PDE or in the PDE’s design, or due to war or radioactive contamination directly affecting the country where the Works are to be executed.
    2. From the Completion Date until the Defects Correction Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is an Procuring and Disposing Entity’s risk except loss or damage due to:
       1. A defect which existed on the Completion Date;
       2. An event occurring before the Completion Date, which was not itself an PDE’s risk; or
       3. The activities of the Contractor on the Site after the Completion Date.
15. **Contractor’s Risks**
    1. From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) which are not the Procuring and Disposing Entity’s risks are the Contractor’s risks.
16. **Insurance**
    1. The Contractor shall provide, in the joint names of the PDE and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the SCC for the following events which are due to the Contractor’s risks:
       1. Loss of or damage to the Works, Plant, and Materials;
       2. Loss of or damage to Equipment;
       3. Loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and
       4. personal injury or death.
    2. Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date. All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred.
    3. If the Contractor does not provide any of the policies and certificates required, the PDE may effect the insurance which the Contractor should have provided and recover the premiums the PDE has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due.
    4. Alterations to the terms of an insurance shall not be made without the approval of the Project Manager.
    5. Both parties shall comply with any conditions of the insurance policies.
17. **Site Investigation Reports**
    1. The Contractor, in preparing the Bid, shall rely on any Site Investigation Reports referred to in the SCC, supplemented by any information available to the Bidder.
18. **Queries About the Special Conditions of Contract**
    1. The Project Manager will clarify queries on the SCC.
19. **Contractor to Construct the Works**
    1. The Contractor shall construct and install the Works in accordance with the Specifications and Drawings.
20. **Works to be Completed by the Intended Completion Date**
    1. The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date specified in the SCC.
21. **Approval by the Project Manager**
    1. All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Project Manager before use.
    2. The Contractor shall be responsible for design of Temporary Works and shall submit

Specifications and Drawings showing the proposed Temporary Works to the Project Manager. The Project Manager shall approve such Specification and Drawing if they comply with the Specifications and Drawings in the Statement of Requirements.

* 1. The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works.
  2. The Contractor shall obtain approval of third parties to the design of the Temporary Works, where required.

1. **Safety and Safety Procedures**
   1. The Contractor shall be responsible for the safety of all activities on the Site.
   2. The Contractor shall ensure the safety procedures:
      1. comply with all applicable safety regulations,
      2. take care for the safety of all persons entitled to be on the Site,
      3. use reasonable efforts to keep the Site and Works clear of unnecessary obstruction so as to avoid danger to these persons,
      4. provide fencing, lighting, guarding and watching of the Works until completion and taking over, and
      5. provide any Temporary Works (including roadways, footways, guards and fences) which may be necessary, because of the execution of the Works, for the use and protection of the public and of owners and occupiers of adjacent land.
2. **Discoveries**
   1. Anything of historical or other interest or of significant value unexpectedly discovered on the site shall be the property of the PDE. The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them.
3. **Possession of the Site**
   1. The PDE shall give possession of all parts of the site to the Contractor. If possession of a part is not given by the date stated in the SCC, the PDE will be deemed to have delayed the start of the relevant activities, and this will be a Compensation Event.
4. **Access to the Site**
   1. The Contractor shall allow the Project Manager and any person authorised by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out.

**28. Contractor’s Equipment**

28.1 The Contractor shall be responsible for all Contractor’s Equipment. When brought on to the Site, Contractor’s Equipment shall be deemed to be exclusively intended for the execution of the Works. The Contractor shall not remove from the Site any major items of Contractor’s Equipment without the consent of the Project Manager. However, consent shall not be required for vehicles transporting Goods or Contractor’s Personnel off Site.

**29. Protection of the Environment**

29.1 The Contractor shall take all reasonable steps to protect the environment (both on and off

the Site) and to limit damage and nuisance to people and property resulting from pollution, noise and other results of his operations. The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws.

**30. Prohibition of Harmful Child Labour**

30.1 The Contractor shall not employ children in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with, the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Children below the age of 18 years shall not be employed in dangerous work.

**31. Health and Safety**

* 1. The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. The Contractor shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Project Manager may reasonably require.
  2. The Contractor shall conduct HIV-AIDS awareness programmes to reduce the risk of the transfer of the HIV virus between and among the Contractor’s Personnel and the local community, to promote early diagnosis and to assist affected individuals. The Contractor shall throughout the contract: (i) conduct Information, Education and Communication (IEC) campaigns, at least every six month, addressed to all the Site staff and labourers (including all the Contractor's employees, all Subcontractors and any other Contractor’s or PDE’s personnel employees, and all truck drivers and crew making deliveries to Site for construction activities) and to the immediate local communities, concerning the risks, dangers and impact, and appropriate avoidance behaviour with respect to Sexually Transmitted Diseases (STD) - or Sexually Transmitted Infections (STI) in general and HIV/AIDS.

**32. Instructions, Inspection and Audits**

* 1. The Contractor shall carry out all instructions of the Project Manager which comply with the applicable laws where the Site is located.
  2. The Contractor shall at all reasonable times allow personnel from PDE to have full access to all parts of the Site and to all places from which natural Materials are being obtained, and during production, manufacture and construction (at the Site and elsewhere), to examine, inspect, measure and test the materials and workmanship, and to check the progress of manufacture of Plant and production and manufacture of Materials.
  3. The Contractor shall permit the Government of Uganda personnel to inspect the Contractor’s accounts and records relating to the performance of the Contract and to have them audited by auditors appointed by the Government, if so required by the Government.

**33. Disputes**

33.1 If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to any Adjudicator appointed under the

contract within 14 days of the notification of the Project Manager’s decision.

**34. Procedure for Settling Disputes**

* 1. Unless otherwise specified in the SCC, the procedure for disputes shall be as specified in GCC 34.2 to 34.4.
  2. Any Adjudicator appointed under the contract shall give a decision in writing within 28 days of receipt of a notification of a dispute, providing that he is in receipt of all the information required to give a decision.
  3. Any Adjudicator appointed under the contract shall be paid by the hour at the rate specified in the SCC, together with reimbursable expenses of the types specified in the SCC, and the cost shall be divided equally between the PDE and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within 28 days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above 28 days, the Adjudicator’s decision will be final and binding.
  4. Any arbitration shall be conducted in accordance with the Arbitration and Conciliation Act 2000 or such other formal mechanism specified in the SCC, and in the place shown in the SCC.

1. **Replacement of Adjudicator**
   1. Should the Adjudicator resign or die, or should the PDE and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator will be jointly appointed by the PDE and the Contractor. In case of disagreement between the PDE and the Contractor, within 30 days, the Adjudicator shall be designated by the Appointing Authority designated in the SCC at the request of either party, within 14 days of receipt of such request.

**B. Time Control**

1. **Program**
   1. Within the time stated in the SCC, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works.
   2. An update of the Program shall be a program showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities.
   3. The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the SCC. If the Contractor does not submit an updated Program within this period, the Project Manager may withhold the amount stated in the SCC from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Program has been submitted.
   4. The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events.
2. **Extension of the Intended Completion Date**
   1. The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost.
   2. The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date.
3. **Acceleration**
   1. When the PDE wants the Contractor to finish before the Intended Completion Date, the Project Manager will obtain priced proposals for achieving the necessary acceleration from the Contractor. If the PDE accepts these proposals, the Intended Completion Date will be adjusted accordingly and confirmed by both the PDE and the Contractor.
   2. If the Contractor’s priced proposals for an acceleration are accepted by the PDE, they are incorporated in the Contract Price and treated as a Variation.
4. **Delays Ordered by the Project Manager**
   1. The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works.
5. **Management Meetings**
   1. Either the Project Manager or the Contractor may require the other to attend a management meeting. The business of a management meeting shall be to review the plans for remaining work and to deal with matters raised in accordance with the early warning procedure detailed in GCC 41.
   2. The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the PDE. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting.
6. **Early Warning**
   1. The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible.
   2. The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager.

**C. Quality Control**

1. **Identifying Defects**
   1. The Project Manager shall check the Contractor’s work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor’s responsibilities. The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect.
2. **Tests**
   1. If the Project Manager instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect, the test shall be a Compensation Event.
3. **Correction of Defects**
   1. The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, specified in the SCC. The Defects Liability Period shall be extended for as long as Defects remain to be corrected.
   2. Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice.
4. **Uncorrected Defects**
   1. If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will pay this amount.

**D. Cost Control**

**46. Bill of Quantities or Activity Schedule**

**Option 1: Admeasurement Contracts - Bill of Quantities**

* 1. The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor.
  2. The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item.

**Option 2: Lump Sum Contracts – Activity Schedule**

* 1. The Contractor shall provide updated Activity Schedules within 14 days of being instructed to by the Project Manager. The activities on the Activity Schedule shall be coordinated with the activities on the Program.
  2. The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately.

**47. Changes in the Bill of Quantities or Activity Schedule**

**Option 1: Admeasurement Contracts – Changes in the Bill of Quantities**

* 1. If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds one percent (1%) of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change.
  2. The Project Manager shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the PDE.
  3. If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities.

**Option 2: Lump Sum Contracts – Changes in the Activity Schedule**

47.4 The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion. Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule.

**48. Variations**

**Option 1: Admeasurement Contracts – Variations**

48.1 All Variations shall be included in updated Programs produced by the Contractor.

**Option 2: Lump Sum Contracts – Variations**

48.2 All Variations shall be included in updated Programs and Activity Schedules produced by the Contractor.

**49. Payments for Variations**

**Option 1: Admeasurement Contracts – Payment for Variations**

* 1. The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. The Project Manager shall assess the quotation, which shall be given within seven days of the request or within any longer period stated by the Project Manager and before the Variation is ordered.
  2. If the work in the Variation corresponds with an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in Sub-Clause 46.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work.
  3. If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs.
  4. If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event.
  5. The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning.

**Option 2: Lump Sum Contracts – Payment for Variations**

49.6 The Contractor shall provide the Project Manager with a quotation for carrying out the

Variation when requested to do so by the Project Manager. The Project Manager shall assess the quotation, which shall be given within seven days of the request or within any longer period stated by the Project Manager and before the Variation is ordered.

* 1. If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs.
  2. If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event.
  3. The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning.

1. **Payment Certificates**
   1. The Contractor shall submit to the Project Manager statements of the estimated value of the work executed less the cumulative amount certified previously. Unless otherwise specified in the SCC, such statements shall be submitted monthly.
   2. The Project Manager shall check the Contractor’s statement and certify the amount to be paid to the Contractor.
   3. The value of work executed shall be determined by the Project Manager.
   4. The value of work executed shall comprise the value of:
      1. The quantities of the items in the Bill of Quantities completed for Admeasurement Contracts; or
      2. Completed (fully or partially) activities in the Activity Schedule for Lump Sum contract activities.
   5. The value of work executed shall include the valuation of Variations and Compensation Events.
   6. The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information.

**51. Issue of Interim Payment Certificates**

* 1. No amount will be certified or paid until the PDE has received and approved the Performance Security and, if applicable, the ES Performance Security. Thereafter, the Project Manager shall, within 28 days after receiving a Statement and supporting documents, deliver to the PDE and to the Contractor an Interim Payment Certificate which shall state the amount which the Project Manager fairly determines to be due, with all supporting particulars for any reduction or withholding made by the Project Manager on the Statement if any.

An Interim Payment Certificate shall be withheld for any of the following reasons:

* + 1. if anything supplied or work done by the Contractor is not in accordance with the Contract, the cost of rectification or replacement may be withheld until rectification or replacement has been completed;
    2. if the Contractor was or is failing to perform any work in accordance with the Contract, and had been so notified by the Project Manager, the value of this work may be withheld until the it has been performed and/or
    3. if the Contractor was, or is, failing to perform any ESHS obligations or work

under the Contract, the value of this work or obligation, as determined by the Engineer, may be withheld until the work or obligation has been performed, and/or the cost of rectification or replacement, as determined by the Engineer, may be withheld until rectification or replacement has been completed. Failure to perform includes, but is not limited to the following:

1. Failure to comply with any ESHS obligations or work described in the Statements of Requirements which may include: working outside site boundaries, excessive dust, failure to keep public roads in a safe usable condition, damage to offsite vegetation, pollution of water courses from oils or sedimentation, contamination of land e.g. from oils, human waste, damage to archeology or cultural heritage features, air pollution as a result of unauthorized and/or inefficient combustion;
2. Failure to regularly review Environmental and Social Management Plan and/or update it in a timely manner to address emerging ESHS issues, or anticipated risks or impacts;
3. Failure to implement the Environmental and Social Management Plan e.g. failure to provide required training or sensitization;
4. Failing to have appropriate consents/permits prior to undertaking Works or related activities;
5. Failure to submit the relevant reports of the Environmental and Social Management Plan, or failure to submit such reports in a timely manner;
6. Failure to implement remediation as instructed by the Engineer within the specified timeframe (e.g. remediation addressing non-compliance/s).
   1. If an amount certified is increased in a later certificate or as a result of an award by the Adjudicator or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause. Interest shall be calculated from the date upon which the increased amount would have been certified in the absence of dispute.
   2. Unless otherwise stated, all payments and deductions will be paid or charged in the proportions of currencies comprising the Contract Price.
   3. Items of the Works for which no rate or price has been entered in will not be paid for by the PDE and shall be deemed covered by other rates and prices in the Contract.
7. **Payments**
   1. Payments shall be adjusted for deductions for advance payments and retention. The Procuring and Disposing Entity shall pay the Contractor the amounts certified by the Project Manager within 30 days of the date of each certificate. If the PDE makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing for each of the currencies in which payments are made.
8. **Compensation Events**
   1. The following shall be Compensation Events:
      1. The PDE does not give access to a part of the Site by the Site Possession Date stated in the SCC.
      2. The PDE modifies the Schedule of Other Contractors in a way that affects the work of the Contractor under the Contract.
      3. The Project Manager orders a delay or does not issue Drawings, Specifications, or

instructions required for execution of the Works on time.

1. The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects.
2. The Project Manager unreasonably does not approve a subcontract to be let.
3. Ground conditions are substantially more adverse than could reasonably have been assumed before signing of the Agreement from the information issued to bidders (including the Site Investigation Reports), from information available publicly and from a visual inspection of the Site.
4. The Project Manager gives an instruction for dealing with an unforeseen condition, caused by the PDE, or additional work required for safety or other reasons.
5. Other contractors, public authorities, utilities, or the PDE does not work within the dates and other constraints stated in the Contract, and they cause delay or extra cost to the Contractor.
6. The advance payment is delayed.
7. The effects on the Contractor of any of the PDE’s Risks.
8. The Project Manager unreasonably delays issuing a Certificate of Completion.
9. Other Compensation Events described in the SCC or determined by the Project Manager shall apply.
   1. If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended. The Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended.
   2. As soon as information demonstrating the effect of each Compensation Event upon the Contractor’s forecast cost has been provided by the Contractor, it shall be assessed by the Project Manager, and the Contract Price shall be adjusted accordingly. If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. The Project Manager will assume that the Contractor will react competently and promptly to the event.
   3. The Contractor shall not be entitled to compensation to the extent that the Procuring and Disposing Entity’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager.
10. **Tax**
    1. The Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the date 28 days before the submission of bids for the Contract and the date of the last Completion certificate. The adjustment shall be the change in the amount of tax payable by the Contractor, provided such changes are not already reflected in the Contract Price or are a result of Clause 56.
11. **Currencies**
    1. Where payments are made in currencies other than Uganda Shillings, the exchange rates used for calculating the amounts to be paid shall be the exchange rates stated in the Contractor’s Bid.
12. **Price Adjustment**
    1. Prices payable to the Provider, as stated in the Contract, shall be subject to adjustment during performance of the Contract to reflect changes in the cost of labour and material components in accordance with the formula:



ΔP = adjustment amount payable to the Provider.

P0 = Contract Price (base price).

a = fixed element representing profits and overheads included in the Contract Price and generally in the range of five (5) to fifteen (15) percent.

b = estimated percentage of labour component in the Contract Price.

c = estimated percentage of material component in the Contract Price.

L0, L1 = labour indices applicable to the appropriate industry in the country of origin on the base date and date for adjustment, respectively.

M0, M1 = material indices for the major raw material on the base date and date for adjustment, respectively, in the country of origin.

The coefficients a, b, and c shall be specified by the procuring and disposing entity in the bidding documents. The sum of the three coefficients should be one (1) in every application of the formula.

The Bidder shall indicate the source of the indices and the base date indices in his bid. Base date = thirty (30) days prior to the deadline for submission of the bids.

Date of adjustment = weeks prior to date of shipment (representing the mid- point of the period of manufacture).

The above price adjustment formula shall be invoked by either party subject to the following further conditions:

* + 1. Price adjustment will be applied only if the resulting increase or decrease is more than percent of the Contract Price.

***[Two (2) percent would be an acceptable percentage.]***

* + 1. No price adjustment shall be allowed beyond the original delivery dates unless specifically stated in the extension letter. As a rule, no price adjustment shall be allowed for periods of delay for which the Provider is entirely responsible. The PDE will however be entitled to any decrease in the prices of the supplies and services subject to adjustment.
    2. The total adjustment under this clause shall be subject to a ceiling of plus or minus percent of the Contract Price.

***[Ten (10) percent would be an acceptable percentage.]***

* + 1. If the currency in which the Contract Price P0 is expressed is different from the currency of origin of the labour and material indices, a correction factor will be applied to avoid incorrect adjustments of the Contract Price. The correction factor shall correspond to the ratio of exchange rates between the two currencies on the base date and the date for adjustment as defined above.
  1. No price adjustment shall be payable on the portion of the Contract Price paid to the Provider as advance payment.
  2. If the value of the index is changed after it has been used in a calculation, the calculation shall be corrected and an adjustment made in the next payment certificate. The index value shall be deemed to take account of all changes in cost due to fluctuations in costs.

1. **Retention**
   1. If so stated in the SCC, the PDE shall retain from each payment due to the Contractor the proportion stated in the SCC until Completion of the whole of the Works.
   2. On completion of the whole of the Works, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected.
   3. On completion of the whole Works, the Contractor may substitute retention money with an “on demand” Bank guarantee.
2. **Liquidated Damages**
   1. If so stated in the SCC, the Contractor shall pay liquidated damages to the PDE at the rate per day stated in the SCC for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the SCC. PDE may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities.
   2. If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in Sub-Clause 52.1.
3. **Bonus**
   1. If so stated in the SCC, the Contractor shall be paid a Bonus calculated at the rate per working day stated in the SCC for each day (less any days for which the Contractor is paid for acceleration) that the Completion is earlier than the Intended Completion Date. The Completion Date shall be certified in accordance with GCC 64.1.
4. **Advance Payment**
   1. If so stated in the SCC, the PDE shall make advance payment to the Contractor of the amounts stated in the SCC within the period stated in the SCC, against provision by the Contractor of an on demand Bank Security in a form and by a bank acceptable to the PDE in amounts and currencies equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest will not be charged on the advance payment.
   2. The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilisation expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager.
   3. The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, as specified in the SCC, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, Bonuses, or Liquidated Damages.
5. **Performance Security and ES Performance Security**
   1. If so stated in the SCC, the Contractor shall, within twenty-one (21) calendar days of signing the contract, provide a Performance Security and, if applicable, an Environmental and Social, (ES) Performance Security for compliance with the Contractor’s ESHS obligations for the due performance of the Contract. The Performance Security and the ES Performance Security shall be in the amount specified in the SCC and shall be denominated in the currency in which the Contract Price is payable.
   2. The proceeds of the Performance Security and, if applicable, the ES Performance Security shall be payable to the PDE as compensation for any loss resulting from the Contractor’s failure to complete its obligations under the Contract.
   3. The Performance Security and, if applicable, the ES Performance Security shall be in the form stipulated in Section 9 of the bidding document.
   4. The Performance Security and, if applicable, the ES Performance Security to the PDE shall be valid until a date 28 days from intended completion date stated in the SCC.
6. **Day works**
   1. If applicable, the Day works rates in the Contractor’s Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way.
   2. All work to be paid for as Day works shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two days of the work being done.
   3. The Contractor shall be paid for Day works subject to obtaining signed Day works forms.
7. **Cost of Repairs**
   1. Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions.

**E. Finishing the Contract**

1. **Completion**
   1. The Contractor shall request the Project Manager to issue a certificate of Completion of

the Works, and the Project Manager will do so upon deciding that the work is completed.

1. **Taking Over**
   1. The PDE shall take over the Site and the Works within seven days of the Project Manager’s issuing a certificate of Completion.
2. **Final Account**
   1. The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate.
3. **Operating and Maintenance Manuals**
   1. If “as built” Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the SCC.
   2. If the Contractor does not supply the Drawings and/or manuals by the dates stated in the SCC, or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount stated in the SCC from payments due to the Contractor.
4. **Termination**
   1. The PDE or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract.
   2. Fundamental breaches of Contract shall include, but shall not be limited to, the following:
      1. the Contractor stops work for 28 days when no stoppage of work is shown on the current Program and the stoppage has not been authorised by the Project Manager;
      2. the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days;
      3. the PDE or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation;
      4. a payment certified by the Project Manager is not paid by the PDE to the Contractor within 84 days of the date of the Project Manager’s certificate;
      5. the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager;
      6. the Contractor does not maintain a Security, which is required; and
      7. the rate of progress of the Works at any time during the period of the Contract is such that the completion of the Works will, as measured against the current Program, be delayed by the number of days for which the maximum amount of liquidated damages can be imposed.
      8. if the Contractor in the judgement of the PDE has engaged in corrupt, fraudulent, collusive or coercive practices in competing for or in the executing the contract.

For the purposes of this paragraph:

1. “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value, to influence the action of a public official in the procurement process or in contract execution; and
2. “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation;
3. “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party;
4. “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party;
   1. When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under Sub-Clause 68.2 above, the Project Manager shall decide whether the breach is fundamental or not.
   2. Notwithstanding the above, the PDE may terminate the Contract for convenience.
   3. If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible.
5. **Payment upon Termination**
   1. If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the SCC. Additional Liquidated Damages shall not apply. If the total amount due to the PDE exceeds any payment due to the Contractor, the difference shall be a debt payable to the PDE.
   2. If the Contract is terminated for the PDE’s convenience or because of a fundamental breach of Contract by PDE, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate.
6. **Release from Performance**
   1. If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the PDE or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made.

**Section 8: Special Conditions of Contract**

The following Special Conditions of Contract (SCC) shall supplement the General Conditions of Contract (GCC). Whenever there is a conflict, the provisions herein shall prevail over those in the GCC.

| **GCC Clause Reference** | **Special Conditions** |
| --- | --- |
|  | Procurement Reference No: **KCCA-GKMA/WRKS/2025-2026/00008/1** |
| **GCC 1(dd)** | The Sites are located in:  The Nakawa Division of Kampala Capital City as defined in Drawings  **Lot 1:** Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km) |
| **GCC 1(gg)** | The Start Date shall be: **As per commencement letter** |
| **GCC 1(z)** | The Project Manager: **Shall be a Consultant to be appointed by the Accounting Officer of the PDE** |
| **GCC 1(aa)** | The Contract Manager/ Contract Management team is: **To be appointed by the Accounting Officer of the PDE**  **The Contract Management Team shall include GKMA Infrastructure Development Specialist(s)** |
| **GCC2.1** | The following documents also form part of the Contract:   1. Agreement, 2. Contractor’s submitted Bid document, 3. Special Conditions of Contract, 4. General Conditions of Contract, 5. Scope of works and technical specifications 6. Drawings, 7. Bill of Quantities or activity schedule as appropriate 8. Work Program; 9. Key Personnel; 10. Key Equipment; 11. Performance Guarantee; 12. ESHS Performance Guarantee 13. Advance Payment Guarantee; 14. Registered Power of Attorney; 15. Contracts Committee Approval of the Contract Document; 16. Notice of Best Evaluated Bidder 17. Solicitor General’s Clearance of the Contract Document |
| **GCC 3.7** | This Contract is an **Admeasurement** Contract. |
| **GCC 3.8** | Sectional completion **will not be** permitted : Unless upon approval of the Contract Management Team |
| **GCC 7.1** | For **notices**, the PDE’s address shall be:  **The Executive Director**  Address**: Kampala Capital City Authority**  **Plot 1-3 Apolo Kaggwa Road**  Town/City: **Kampala**  Postal Code/PO Box: **7010, Kampala, Uganda**  Telephone : **+256 312 009000**  Electronic mail address: [**info@kcca.go.ug**](mailto:info@kcca.go.ug)  For **notices**, the Contractor’s address shall be:  Attention: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Street Address: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Floor/Room number: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Town/City: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  P. O. Box: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Country: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Telephone: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  Electronic mail address: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| **GCC 9** | The Works consist of:  **Lot 1:** Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km)  **The scope of works includes:**   1. General 2. Drainage 3. Earthworks and Pavement Layers of Gravel or Crushed Stone 4. Bituminous Layers and Seals including DBM works 5. Ancillary Roadworks 6. Structures 7. Tolerances, Testing and Quality Control 8. Dayworks 9. Streetlighting |
| **GCC 10.2** | The PDE’s specific approval is required for: **Varying the works with respect to:**   1. **Time;** 2. **Cost;** 3. **Quality; and** 4. **Any other variation** 5. **Any amendment in the design of the Project.** 6. **Issuing instructions to the Contractor that will have financial effects on the contract price** 7. **Granting extension of contract period** 8. **Issuing instructions that may vary significantly the scope and quality of the contract works** 9. **Issuing instructions for expending the prime cost sums included in the contract sum**   **NB. This requirement shall be waived on emergency affecting safety of personnel or the works on adjacent property**  **The request for approval shall be communicated to PDE through the Project Manager who will verify the reasons given for approval and forward them for the PDEs’ consideration.** |
| **GCC 12.1** | GCC12.1 on sub-contracting is modified as follows: **N/A** |
| **GCC 12.2** | The following conditions shall apply to subcontracting:  **“Foreign providers shall be required to reserve at least 30% of the value of works through subcontracting of sub-works and supply of materials, equipment and services to national and resident providers”.**  Definitions that PDEs must to take note of;   1. “**Foreign Provider**” means a provider not incorporated in Uganda 2. **“National Provider”** means a provider registered in Uganda and wholly owned and controlled by Ugandans 3. **“Resident provider”** means a provider incorporated in Uganda for at least two years at the time of submission of the bid and is not a national provider   **The Contractor shall not subcontract works greater than 40% of the Contract Price to a single subcontractor and the total subcontracted works shall not exceed 50% of the Contract Price.**  **The contractor shall not impose inequitable conditions on his appointed subcontractor and shall pay all subcontractors promptly for work performed by the subcontractor** |
| **GCC 13** | The Schedule of Other Contractors **SHALL NOT FORM** part of the Contract. |
| **GCC 14.1** | The Schedule of Key Personnel shall form part of the Contract. |
| **GCC 18.1** | The minimum insurance covers shall be:  (a) The minimum cover for insurance of the Works, Plant and Materials is: **110% of the Contract Value**  (b) The maximum deductible for insurance of the Works, Plant and Materials is: **UGX 150 million maximum deductible**  (c) The minimum cover for insurance of Equipment is: **100% of the value of equipment required for the performance of the contract.**  (d) The maximum deductible for insurance of Equipment is: **UGX90 million**  (e) The minimum cover for insurance of property is: **UGX600million**  (f) The maximum deductible for insurance of property is: **UGX600million**  (g) The minimum cover for personal injury or death insurance is: **as per statute (Workers Compensation Act, Cap. 225)**  (h) The maximum deductible for personal injury or death insurance is **UGX450million** |
| **GCC 19** | Site Investigation Report(s) **is not** part of the contract. |
| **GCC 22** | The Intended Completion Duration for the whole of the Works shall be: **18 calendar months** from commencement date. |
| **GCC 26** | The Site Possession Date shall be: **As communicated by the Project Manager.** Sectional Handover of the site corridors shall be instructed by the Project Manager. |
| **GCC 29** | **ESHS Management Strategies and Implementation Plans**  The Contractor shall not carry out any Works, including mobilization and/or pre-construction activities (e.g. limited clearance for haul roads, site accesses and worksite establishment, geotechnical investigations or investigations to select ancillary features such as quarries and borrow pits), unless the Project Manager (with the endorsement of the Environmental Officer and the Community Development Officer) is satisfied that appropriate measures are in place to address environmental, social, health and safety risks and impacts. At a minimum, the Contractor shall apply the Management Strategies and Implementation Plans and Code of Conduct submitted as part of the Bid and agreed as part of the Contract. The Contractor shall submit, on a continuing basis, for the Project Manager’s prior approval, such as supplementary Management Strategies and Implementation Plans as are necessary to manage the ESHS risks and impacts of ongoing works. These Management Strategies and Implementation Plans collectively comprise the Contractor’s Environmental and Social Management Plan (C-ESMP). The C-ESMP shall be approved prior to the commencement of construction activities (e.g. excavation, earthworks, bridge and structure works, stream and road diversions, quarrying or extraction of materials, concrete batching and asphalt manufacture). The approved C-ESMP shall be reviewed, periodically (but not less than every six (6) months), and updated in a timely manner, as required, by the Contractor to ensure that it contains measures appropriate to the Works activities to be undertaken. The updated C-ESMP shall be subject to prior approval by the Project Manager.”  Should the Contractor not comply with the instructions of the Engineer a penalty as specified in note (iv) above for payment item 17.01 will apply. In the event that these items are not priced, the engineer will deduct **Ush500,000 per day** until such a time as the contractor is compliant  In the case of continued failure (i.e. beyond two consecutive months) to comply with the environmental conditions of contract and the provisions contained in the Approved Contractor’s Environmental and Social Management Plan (i.e. beyond two months) the Engineer will deduct an additional **USh1,000,000 per day** from the certificate until such a time as the Contractor is compliant |
| **GCC 34.1** | The procedure for settling disputes shall be: by Adjudication, and Arbitration....as specified in GCC 34.2 to 34.4. |
| **GCC 34.2** | The Appointing Authority for the Adjudicator is: **President of Uganda Institution of Professional Engineers. (UIPE).** The Adjudicator shall be a team of three (3) members. |
| **GCC 34.3** | Fees and types of reimbursable expenses to be paid each Adjudicator: **UGX 200,000 Per Hour** |
| **GCC 34.4** | The arbitration shall be conducted in accordance with the Arbitration and Conciliation Act 2000 of Uganda.  Arbitration shall take place at: **Kampala, Uganda** |
| **GCC 35** | The Appointing Authority for the Adjudicator is: **President of Uganda Institution of Professional Engineers. (UIPE),**  **Adress:**  **Kyambogo-Gloucester Ave**  **Tel: +256414287292**  **Email: info@uipe.co.ug** |
| **GCC 36.1** | The Contractor shall submit the Program for the Works within **Twenty Eight (28) calendar** days of contract signature. |
| **GCC 36.3** | The period between Program updates is **Thirty (30) calendar** days.  The amount to be withheld for late submission of an updated Program is: **UGX** **Fifty Million (50,000,000)** |
| **GCC 44.1** | The Defects Liability Period is **365** days. |
| **GCC 50.1** | Statements of estimated value of works executed shall be on **a monthly** basis. The minimum value of work in an Interim Payment Certificate shall be **2%** of the Contract sum |
| **GCC 53.1(l)** | The following events shall also be Compensation Events: **NONE** |
| **GCC 56.1** | The Contract **is not** subject to price adjustment in accordance with GCC 56 of the General Conditions of Contract, and the following information regarding coefficients **not** apply.  The coefficients for adjustment of prices are: N/A  (a) For currency:  (i) N/A percent nonadjustable element (coefficient A).  (ii)N/A percent adjustable element (coefficient B).  (b) For currency:  (i) N/A percent nonadjustable element (coefficient A).  (ii) N/A percent adjustable element (coefficient B). |
| **GCC 56.1** | The Index I for local currency will be: N/A  The Index I for the specified international currency will be: N/A  The Index I for currencies other than the local currency and the specified international currency will be: N/A |
| **GCC 57.1** | The proportion of payments retained is **Ten** percent (**10%)** |
| **GCC 58.1** | The liquidated damages for the whole of the Works are **0.05% of contract price** per day.  The maximum amount of liquidated damages for the whole of the Works is 5 Percent (**5%)** of the final Contract Price. |
| **GCC 59** | The Bonus for the whole of the Works is **zero (0) percent of final Contract Price** per day. The maximum amount of Bonus for the whole of the Works is **zero (0) Percent** of the final Contract Price. |
| **GCC 60.1** | The Advance Payment will be equivalent to **20% of the Accepted Contract Price (VAT exclusive)** and will be paid in the same currencies and proportions as the Contract Price.  It will be paid to the Contractor within **thirty (30) calendar days of the submission of an acceptable advance payment bank guarantee.** |
| **GCC 60.3** | The Advance Payment will be repaid by deducting equal amounts from payments due to the Contractor each month during the period starting **when the Contractor has executed 30% value of works and ending when the Contractor has executed 80% value of work.** |
| **GCC 61.1** | A Performance Security **SHALL** be required.  A Performance Security shall be for 4**%** of the Contract Price.  An ES Performance Security **SHALL** be required.  The ES Performance Security shall be for **1%** of the Contract Price. |
| **GCC 61.3** | The standard form of Performance Security and ES Performance Security acceptable to the PDE shall be an Unconditional Bank Guarantee in the format presented in Section 9 of the Bidding Documents. |
| **GCC 67.1** | The date by which “as-built” drawings are required is: **45 days following practical completion of the project**  The date by which operating and maintenance manuals are required is: **45 days following practical completion of the project** |
| **GCC 67.2** | The amount to be withheld for failing to produce “as-built” drawings and/or operating and maintenance manuals by the date required is **50,000,000 (fifty million) Uganda Shillings.** |
| **GCC 69.1** | The percentage to apply to the value of the work not completed, representing the PDE’s additional cost for completing the Works, is: **10% of accepted contract price**. |

**Section 9: Contract Forms**

**Table of Forms**

[**Contract Agreement 17**](#_bookmark148)**1**

[**Performance Security 17**](#_bookmark149)**4**

[**Environmental and Social (ES) Performance Security 17**](#_bookmark150)**6**

[**Advance Payment Security 178**](#_bookmark151)

**Contract Agreement**

Procurement Reference No: **KCCA-GKMA/WRKS/2025-2026/00008/1**

THIS CONTRACT AGREEMENT made this \_\_\_\_\_\_day of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_,

2024, between **KAMPALA CAPITAL CITY AUTHORITY** of **Plot 1-3 Apolo Kaggwa Road, P.O. Box 7010, Kampala, Uganda** (hereinafter “the Procuring and Disposing Entity -PDE”), of the one part, and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

of

Contractor”), of the other part.

(hereinafter “the

Whereas the PDE is desirous that the Contractor executes **Construction of Batch 1B Roads in Kampala Capital City Authority under GKMA-UDP [Lot 1: Old Kireka Road (6.2Km) + Kireka Link (0.4Km) + Lance Road (0.9Km)]** (hereinafter called “the Works”) and the PDE has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein for the Contract Price of Uganda Shillings *.*

NOW THIS CONTRACT AGREEMENT WITNESSETH AS FOLLOWS:

1. In this Contract Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Contract referred to.
2. The following documents shall be deemed to form and be read and construed as part of this Agreement. This Contract Agreement shall prevail over all other Contract documents.
   1. the Contractor’s Bid;
   2. the Special Conditions of Contract;
   3. the General Conditions of Contracts;
3. the Scope of works;
4. the Drawings; and
5. the completed Schedules.
6. In consideration of the payments to be made by the PDE to the Contractor as indicated in this Contract, the Contractor hereby covenants with the Procuring and Disposing Entity to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.
7. The PDE hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein the Contract Price of

or such other sum as may become payable under the provisions of the Contract, at the times and in the manner prescribed by the Contract.

1. The Contract Price or such other sum as may be payable shall be paid in

Uganda Shillings,

.

in

and in

IN WITNESS whereof the parties thereto have caused this Contract to be executed in accordance with the law specified in the Special Conditions of Contract on the day, month and year indicated above.

Signed by (for the Procuring and Disposing Entity) Name: Position:

In the presence of:

Name: Position: Signed by (for the Contractor)

Name: Position:

In the presence of:

Name: Position:

**Performance Security**

*[The Performance Security should be on the letterhead of the issuing Financial Institution and should be signed by a person with the proper authority to sign documents that are binding on the Financial Institution. The draft is for an unconditional Security. The amount of the guarantee must represent the percentage of the Contract Price specified in the Contract, and should be denominated either in the currency(ies) of the Contract or in a freely convertible currency acceptable to the Procuring and Disposing Entity].*

Date: *[insert date (as day, month and year) of Performance Security]*

Procurement Reference No: *[insert Procurement Reference Number]*

To: *[insert complete name and address of Procuring and Disposing Entity]*

WHEREAS *[insert name and address of Contractor]* (hereinafter called “the Contractor”) has undertaken, pursuant to the Contract referenced above, dated *[insert date (as day, month and year) of contract]* to execute *[insert brief description of Works]* (hereinafter called “the Contract”);

AND WHEREAS it has been stipulated by you in the aforementioned Contract that the Provider shall furnish you with a demand guarantee issued by a financial institution for the sum specified therein as security for compliance with the Provider’s performance obligations in accordance with the Contract;

AND WHEREAS the undersigned *[insert complete name of Guarantor]*, legally domiciled in *[insert complete address of Guarantor]*, (hereinafter the “Guarantor”}, have agreed to give the Contractor a security;

THEREFORE WE hereby affirm that we are Guarantors and responsible to you, on behalf of the Contractor, up to a total of *[insert currency and amount of Guarantee in words and figures]*, such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand declaring the Contractor to be in default under the Contract, without cavil or argument, any sum or sums within the limits of *[insert currency and amount of Guarantee in words and figures]* as aforesaid without your needing to prove or to show grounds or reasons for your demand or the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall remain in force up to and including  *[insert date: day, month, year]*

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758, except that Sub-article 20(a) is hereby excluded.

Name: *[insert complete name of person signing the Performance Security]*

In the capacity of *[insert legal capacity of person signing the Performance Security]*

Signed: *[signature of person whose name and capacity are shown above]*

Duly authorised to sign the Performance Security for and on behalf of: *[insert complete name of Financial Institution]*

Dated on day of , *[insert date of signing]*

* *Insert the date twenty eight (28) days after the intended completion date as stated in SCC 22.1. In the event of an extension of the intended completion date, the Entity shall request for an extension of this guarantee from the contractor. The request for extension shall be in writing and must be made prior to the expiration date stated in the guarantee.*

**Environmental and Social (ES)**

**Performance Security**

*[The Environmental and Social Performance Security should be on the letterhead of the issuing Financial Institution and should be signed by a person with the proper authority to sign documents that are binding on the Financial Institution. The draft is for an unconditional Security. The amount of the guarantee must represent the percentage of the Contract Price specified in the Contract, and should be denominated either in the currency(ies) of the Contract or in a freely convertible currency acceptable to the Procuring and Disposing Entity].*

Date: *[insert date (as day, month and year) of ES Performance Security]*

Procurement Reference No: *[insert Procurement Reference Number]*

To: *[insert complete name and address of Procuring and Disposing Entity]*

WHEREAS *[insert name and address of Contractor]* (hereinafter called “the Contractor”) has undertaken, pursuant to the Contract referenced above, dated *[insert date (as day, month and year) of contract]* to execute *[insert brief description of Works]* (hereinafter called “the Contract”);

AND WHEREAS it has been stipulated by you in the aforementioned Contract that the Provider shall furnish you with a demand guarantee issued by a financial institution for the sum specified therein as security for compliance with the Provider’s performance obligations in accordance with the Contract;

AND WHEREAS the undersigned *[insert complete name of Guarantor]*, legally domiciled in *[insert complete address of Guarantor]*, (hereinafter the “Guarantor”}, have agreed to give the Contractor a security;

THEREFORE WE hereby affirm that we are Guarantors and responsible to you, on behalf of the Contractor, up to a total of *[insert currency and amount of Guarantee in words and figures]*, such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand declaring the Contractor to be in default under the Contract, without cavil or argument, any sum or sums within the limits of *[insert currency and amount of Guarantee in words and figures]* as aforesaid without your needing to prove or to show grounds or reasons for your demand or the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed thereunder or of any of the Contract documents which may be made between you and the Contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall remain in force up to and including  *[insert date: day, month, year]*

This guarantee is subject to the Uniform Rules for Demand Guarantees ICC Publication No. 758, except that sub - article 20(a) is hereby excluded.

Name: *[insert complete name of person signing the Performance Security]*

In the capacity of *[insert legal capacity of person signing the Performance Security]*

Signed: *[signature of person whose name and capacity are shown above]*

Duly authorised to sign the Performance Security for and on behalf of: *[insert complete name of Financial Institution]*

Dated on day of , *[insert date of signing]*

* *Insert the date twenty eight (28) days after the intended completion date as stated in SCC 22.1. In the event of an extension of the intended completion date, the Entity shall request for an extension of this guarantee from the contractor. The request for extension shall be in writing and must be made prior to the expiration date stated in the guarantee.*

**Advance Payment Security**

*[The Advance Payment Security should be on the letterhead of the issuing Financial Institution and should be signed by a person with the proper authority to sign documents that are binding on the Financial Institution. The amount of the security is to be inserted by the Financial Institution and must represent the amount of the Advance Payment and be denominated either in the currency(ies) of the Advance Payment as specified in the Contract, or in a freely convertible currency acceptable to the PDE].*

Date: *[insert date (as day, month, and year) of Payment Security]*

Procurement Reference No.: *[insert Procurement Reference Number]*

To: *[insert complete name and address of Procuring and Disposing Entity]*

In accordance with the payment provision included in the Contract referenced above, in relation to advance payments, *[insert complete name and address of Contractor]* (hereinafter called “the Contractor”) shall deposit with the PDE a Bank Guarantee to guarantee its proper and faithful performance of the obligations imposed by said Clause of the Contract, in the amount of *[insert currency and amount of guarantee in words and figures].*

We, the undersigned *[insert complete name of Guarantor]*, legally domiciled in *[insert full address of Guarantor]* (hereinafter “the Guarantor”), as instructed by the Contractor, agree unconditionally and irrevocably to guarantee as primary obligator and not as surety merely, the payment to the PDE on its first demand without whatsoever right of objection on our part and without its first claim to the Contractor, in the amount not exceeding *[insert currency and amount of guarantee in words and figures]*.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between the PDE and the Contractor, shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Security shall remain valid and in full effect from the date of the advance payment under the Contract until the PDE receives full repayment of the same amount from the Contractor.

Name: *[insert complete name of person signing the Payment Security]*

In the capacity of *[insert legal capacity of person signing the Payment Security]*

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758, except that Sub-article 20(a) is hereby excluded.

Signed: *[signature of person whose name and capacity are shown above]*

Duly authorized to sign the Payment Security for and on behalf of: *[insert complete name of the Financial Institution]*

Dated on day of , *[insert date of signing]*

1. This shall include professional memberships with legally enforceable codes [↑](#footnote-ref-1)
2. One per active site [↑](#footnote-ref-2)